## 2022
Project Name | Project Eng | Case # | Subdivision | Applicant | Engineer | Infrastructure Submitted | Date Submittal Received | Date Distr. | Inspector Comments Received | BTU Comments Received | Dev Srvcs Comments Received | Drainage Comments Recv'd | Fire Comments Recv'd | Traffic Comments Recv'd | Water Comments Received | FP Coord Comments Received | Date Comments Prepared | Comments Sent to Applicant / Engineer | Status | Gross Review Days | Met Deadline? | Add'l Comments
Pinemont | KCS | FP21-25 | Pinemont Subd., Blk 1-5 45 Lts | Sharaj Holdings Inc | J4 Engineering | Revised (Digital) CP | 2022-01-04 | 2022-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | 2022-01-10 | Approved | 6 | Yes | Rev #3
Pinemont | KCS | FP21-25 | Pinemont Subd., Blk 1-5 45 Lts | Sharaj Holdings Inc | J4 Engineering | Revised (Digital) EE | 2022-01-04 | 2022-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | 2022-01-10 | Approved | 6 | Yes | Rev #3
American Lumber | BMG | SP21-40 | Bryan Ind'l Park Ph 2, Blk 5 Lt 3 | Zenith Co | Schultz Engineering | Digital DR | 2022-01-10 | 2022-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-11 | 2022-01-11 | Comments | 1 | Yes | Rev #1
Academy Preserve | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | Digital EE | 2022-01-12 | 2022-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-21 | N/A | 2022-02-01 | 2022-02-01 | Comments | 19 | No | Digital Copy Recv'd on 1/10/22; FP submitted to SDRC on 1/12/22 (dms)
Academy Preserve | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | 1 CP | 2022-01-12 | 2022-01-12 | 2022-01-21 | N/A | N/A | N/A | N/A | 2022-01-21 | 2022-01-21 | N/A | 2022-02-01 | 2022-02-01 | Comments | 19 | No | Hard Copy & Digital Copy Recv'd on 1/11/22; FP submitted to SDRC on 1/12/22 (dms)
Academy Preserve | KCS | MP21-06 | Academy Preserve Ph 1&2, 55 Lts | Fenikes Holdings LLC | RME Engineering | Digital DR | 2022-01-12 | 2022-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-01 | 2022-02-01 | Comments | 19 | No | Digital Copy Recv'd on 1/10/22; FP Submitted to SDRC on 1/12/22 (dms)
Academy Preserve | KCS | MP21-06 | Academy Preserve Ph 1&2, 55 Lts | Fenikes Holdings LLC | RME Engineering | Digital UR | 2022-01-12 | 2022-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-21 | N/A | 2022-02-01 | 2022-02-01 | Comments | 19 | No | Digital Copy Recv'd on 1/10/22; FP submitted to SDRC on 1/12/22 (dms)
American Lumber | BMG | SP21-40 | Bryan Ind'l Park Ph 2, Blk 5 Lt 3 | Zenith Co | Schultz Engineering | Digital DR | 2022-01-13 | 2022-01-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-18 | 2022-01-18 | Approved | 4 | Yes | Rev #2
Piccolo Bldgs | REG | SP21-31 | Bryan Original Townsite, Blk 134 Lts 2, 9&10 | NN Out Properties Ltd | J4 Engineering | Revised (Digital) DR | 2022-01-14 | 2022-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-26 | 2022-01-26 | Approved | 11 | Yes | Rev #1
Piccolo Bldgs | REG | SP21-31 | Bryan Original Townsite, Blk 134 Lts 2, 9&10 | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2022-01-14 | 2022-01-18 | 2022-01-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-26 | 2022-01-26 | Comments | 11 | Yes | Rev #1; Digital Copy Recv'd on Same Day (dms)
Austin's Colony Ph 21A | KCS | FP19-28 | Austin's Colony Ph 21A, Blks 1-3 65 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2022-01-25 | 2022-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | Comments | 10 | Yes | Rev #2
Austin's Colony Ph 21A | KCS | FP19-28 | Austin's Colony Ph 21A, Blks 1-3 65 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) EE | 2022-01-25 | 2022-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | Comments | 10 | Yes | Rev #2
Austin's Colony Ph 21A | KCS | FP19-28 | Austin's Colony Ph 21A, Blks 1-3 65 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2022-01-25 | 2022-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | Comments | 10 | Yes | Rev #2
Sundown Subd | REG | FP21-22 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Digital SR | 2022-02-02 | 2022-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | N/A | 2022-02-15 | 2022-02-15 | Approved | 13 | Yes | N/A
Sundown Subd | REG | FP21-22 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Digital WR | 2022-02-02 | 2022-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | N/A | 2022-02-15 | 2022-02-15 | Approved | 13 | Yes | N/A
Sundown Subd | REG | FP21-22 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) CP | 2022-02-02 | 2022-02-02 | 2022-02-08 | N/A | N/A | N/A | N/A | 2022-02-08 | 2022-02-04 | N/A | 2022-02-14 | 2022-02-14 | Comments | 12 | Yes | Rev #1; Digital Copy Recv'd on 2/1/22 (dms)
Sundown Subd C-Store | REG | SP21-48 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) DR | 2022-02-02 | 2022-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-15 | 2022-02-15 | Comments | 13 | Yes | Rev #1
Majestic Pointe Ph 1 | BMG PSE | FP21-15 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) DR | 2022-02-03 | 2022-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | 2022-02-23 | Comments | 20 | No | Rev #3; Drainage Report was not up to BCS Guidelines & did not match the plans (PSE)
Majestic Pointe Ph 1 | BMG PSE | FP21-15 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) CP | 2022-02-03 | 2022-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-09 | N/A | 2022-02-23 | 2022-02-23 | Comments | 20 | No | Rev #3; Drainage Report was not up to BCS Guidelines & did not match the plans (PSE)
Pleasant Hill Amenity Center | KCS | SQ22-01 | Pleasant Hill Ph 1, Blk 6 Lt 1 | WBW Development Group LLC | Yalgo Engineering | SQ Permit | 2022-02-03 | 2022-02-03 | N/A | N/A | 2022-02-04 | 2022-02-09 | 2022-02-03 | N/A | 2022-02-09 | N/A | 2022-02-09 | 2022-02-09 | Comments | 6 | Yes | N/A
Pleasant Hill Amenity Center | KCS | SQ22-01 | Pleasant Hill Ph 1, Blk 6 Lt 1 | WBW Development Group LLC | Yalgo Engineering | SQ Permit | 2022-02-11 | 2022-02-11 | N/A | N/A | N/A | 2022-02-11 | N/A | N/A | N/A | N/A | 2022-02-11 | 2022-02-11 | Approved | 0 | Yes | N/A
Sundown Subd | REG | FP21-22 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) CP | 2022-02-15 | 2022-02-15 | 2022-02-21 | N/A | N/A | N/A | N/A | 2022-02-16 | 2022-02-21 | N/A | 2022-02-21 | 2022-02-21 | Comments | 6 | Yes | Rev #2; Digitial Copy Recv'd on 2/14/22 (kml)
Austin's Colony Ph 21A | KCS | FP19-28 | Austin's Colony Ph 21A, Blks 1-3 65 Lts | Carrabba Family Ltd | J4 Engineering | Revised (Digital) CP | 2022-02-16 | 2022-02-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | 2022-02-22 | Approved | 6 | Yes | N/A
Sundown Subd | REG | FP21-22 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) DR | 2022-02-16 | 2022-02-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-21 | 2022-02-21 | Comments | 5 | Yes | Rev #3
Sundown Subd C-Store | REG | SP21-48 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | TxDOT Permit | 2022-02-16 | 2022-02-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | 2022-02-24 | Emailed to TxDOT | 8 | Yes | N/A
Highkland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Digital TIA | 2022-02-17 | 2022-02-17 | N/A | N/A | N/A | N/A | N/A | 2022-02-25 | N/A | N/A | 2022-03-01 | 2022-03-01 | Comments | 12 | Yes | Copied WPK 2/17/22 (ccp)
Academy Preserve | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | Digital CP | 2022-02-21 | 2022-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | N/A | 2022-02-25 | 2022-02-25 | Comments | 4 | Yes | Rev #2
Academy Preserve | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | Digital UR | 2022-02-21 | 2022-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | N/A | 2022-02-25 | 2022-02-25 | Comments | 4 | Yes | Rev #2
Academy Preserve | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | Digital EE | 2022-02-21 | 2022-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-25 | 2022-02-25 | Comments | 4 | Yes | Rev #2
Academy Preserve | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | Digital DR | 2022-02-21 | 2022-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-25 | 2022-02-25 | Comments | 4 | Yes | Rev #2
Piccolo Bldgs | REG | SP21-31 | Bryan Original Townsite, Blk 134 Lts 2, 9&10 | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2022-02-22 | 2022-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-22 | 2022-02-22 | Approved | 0 | Yes | Rev #2
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Digital DR | 2022-02-23 | 2022-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-07 | 2022-03-07 | Comments | 12 | Yes | Digital Copy Recv'd on 1/25/22 (dms)
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Digital EE | 2022-02-23 | 2022-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-25 | N/A | 2022-03-07 | 2022-03-07 | Comments | 12 | Yes | Digital Copy Recv'd on 1/25/22 (dms)
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | 1 CP | 2022-02-23 | 2022-02-23 | 2022-03-03 | N/A | N/A | N/A | N/A | N/A | 2022-02-25 | N/A | 2022-03-07 | 2022-03-07 | Comments | 12 | Yes | Digital Copy Recv'd on 1/25/22; Waited on Hard Copy (dms)
Rudder Pointe Ph 5&6 | KCS | FP22-04 | Rudder Pointe Ph 5&6, Blk 1-5 90 Lts | Bord Development | McClure & Browne | Digital DR | 2022-03-01 | 2022-03-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-16 | Comments | 15 | No | Comments were prepared on time, but not sent out until the 16th as we had an in person mtg on this date to discuss drainage to ensure no add'l comments arised (KCS)
Rudder Pointe Ph 5&6 | KCS | FP22-04 | Rudder Pointe Ph 5&6, Blk 1-5 90 Lts | Bord Development | McClure & Browne | Digital EE | 2022-03-01 | 2022-03-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-16 | Comments | 15 | No | Comments were prepared on time, but not sent out until the 16th as we had an in person mtg on this date to discuss drainage to ensure no add'l comments arised (KCS)
Rudder Pointe Ph 5&6 | KCS | FP22-04 | Rudder Pointe Ph 5&6, Blk 1-5 90 Lts | Bord Development | McClure & Browne | 1 CP | 2022-03-01 | 2022-03-02 | 2022-03-14 | N/A | N/A | N/A | N/A | 2022-03-08 | 2022-03-09 | N/A | 2022-03-15 | 2022-03-16 | Comments | 15 | No | Digital Copy Recv'd on Same Day (ccp); Comments were prepared on time, but not sent out until 16th due to in-person mtg on this date to discuss drainage to ensure no add'l comments arised (KCS)
Rudder Pointe Ph 5&6 | KCS | FP22-04 | Rudder Pointe Ph 5&6, Blk 1-5 90 Lts | Bord Development | McClure & Browne | Digital WL | 2022-03-01 | 2022-03-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-09 | N/A | 2022-03-15 | 2022-03-16 | Comments | 15 | No | Comments were prepared on time, but not sent out until the 16th as we had an in person mtg on this date to discuss drainage to ensure no add'l comments arised (KCS)
Rudder Pointe Ph 5&6 | KCS | FP22-04 | Rudder Pointe Ph 5&6, Blk 1-5 90 Lts | Bord Development | McClure & Browne | Digital SL | 2022-03-01 | 2022-03-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-09 | N/A | 2022-03-15 | 2022-03-16 | Comments | 15 | No | Comments were prepared on time, but not sent out until the 16th as we had an in person mtg on this date to discuss drainage to ensure no add'l comments arised (KCS)
Corporate Center Office | REG | SP22-04 | Park Hudson Ph 6, Blk 3 Lt 5 | Builder 10 Construction | McClure & Browne | 1 DL | 2022-03-02 | 2022-03-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-11 | 2022-03-11 | Comments | 9 | Yes | N/A
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | 1 CP | 2022-03-03 | 2022-03-03 | 2022-03-15 | N/A | N/A | N/A | N/A | 2022-03-08 | 2022-03-07 | N/A | 2022-03-15 | 2022-03-15 | Comments | 12 | Yes | Digital Copy Recv'd on Same Day (ccp)
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | 1 EE | 2022-03-03 | 2022-03-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-15 | Comments | 12 | Yes | N/A
Copperfield Dr Off-Site Drainage | ZFK | SP21-13 | Park Hudson Ph 4, Blk 4 Lt 3R | Legacy BTX Holdings LP | Walker Partners | Revised (Digital) CP | 2022-03-03 | 2022-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-03 | N/A | 2022-03-03 | 2022-03-03 | Comments | 0 | Yes | Rev #3 Digital Copy Recv'd on 12/12/22 comments returned 12/19/22
Copperfield Dr Off-Site Drainage | ZFK | SP21-13 | Park Hudson Ph 4, Blk 4 Lt 3R | Legacy BTX Holdings LP | Walker Partners | Revised (Digital) EE | 2022-03-03 | 2022-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-06 | N/A | 2022-03-08 | 2022-03-08 | Approved | 5 | Yes | Rev #2
Academy Preserve Ph 2 | KCS | FP22-05 | Academy Preserve Ph 2, Blk 1 3&4 40 Lts | Fenikes Holdings LLC | RME Engineering | 1 CP | 2022-03-04 | 2022-03-04 | 2022-03-16 | N/A | N/A | N/A | N/A | 2022-03-08 | 2022-03-07 | N/A | 2022-03-18 | 2022-03-18 | Comments | 14 | Yes | Digital Copy Recv'd on 3/3/22
Academy Preserve Ph 2 | KCS | FP22-05 | Academy Preserve Ph 2, Blk 1 3&4 40 Lts | Fenikes Holdings LLC | RME Engineering | Digital EE | 2022-03-04 | 2022-03-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-07 | N/A | 2022-03-18 | 2022-03-18 | Comments | 14 | Yes | N/A
AMA Towing | REG | SP22-08 | Parkwood Estates Ph 2, Lt 4 Blk 1 | Elite Business Services LLC | J4 Engineering | 1 CP | 2022-03-04 | 2022-03-04 | 2022-03-08 | N/A | N/A | N/A | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-14 | Comments | 10 | Yes | Digital Copy Recv'd on 3/3/22; Waited on Hard Copy (ccp)
AMA Towing | REG | SP22-08 | Parkwood Estates Ph 2, Lt 4 Blk 1 | Elite Business Services LLC | J4 Engineering | Digital EE | 2022-03-04 | 2022-03-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-14 | 2022-03-14 | Approved | 10 | Yes | Pending CP Approval (reg)
AMA Towing | REG | SP22-08 | Parkwood Estates Ph 2, Lt 4 Blk 1 | Elite Business Services LLC | J4 Engineering | Digital DR | 2022-03-04 | 2022-03-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-14 | 2022-03-14 | Comments | 10 | Yes | Distributed hard copy 3/14/22 (ccp) grading onto neighboring property & concern for capacity of downstream conveyance (reg)
Rudder Pointe Ph 5&6 | KCS | SQ22-02 | Rudder Pointe Ph 5&6, Blk 1-5 90 Lts | BORD Development | McClure & Browne | SQ Permit | 2022-03-04 | 2022-03-04 | N/A | N/A | 2022-03-09 | 2022-03-09 | UKN | N/A | UKN | UKN | 2022-03-14 | 2022-03-14 | Approved | 10 | Yes | N/A
Academy Preserve Ph 1 | KCS | FP22-01 | Academy Preserve Ph 1, Blks 1-3 25 Lts | Fenikes Holdings LLC | RME Engineering | Digital UR | 2022-03-07 | 2022-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | N/A | 2022-03-15 | 2022-03-15 | Approved | 8 | Yes | Rev #3
Academy Preserve Ph 2 | KCS | FP22-05 | Academy Preserve Ph 2, Blk 1 3&4 40 Lts | Fenikes Holdings LLC | RME Engineering | Digital UR | 2022-03-07 | 2022-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | N/A | 2022-03-15 | 2022-03-15 | Approved | 8 | Yes | Rev #3
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Digital CP | 2022-03-07 | 2022-03-14 | 2022-03-21 | N/A | N/A | N/A | N/A | 2022-03-21 | 2022-03-21 | N/A | 2022-03-21 | 2022-03-21 | Comments | 14 | Yes | Ater reviewing all submittals for past couple of weeks, I noticed this was missed during intake (dms)
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) EE | 2022-03-11 | 2022-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-24 | 2022-03-24 | Comments | 13 | Yes | Rev #1; comments slightly delayed due to plans not being routed right away to water/traffic; plans were routed to them 3/21/22 (KCS)
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2022-03-11 | 2022-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-24 | 2022-03-24 | Comments | 13 | Yes | Rev #1; comments slightly delayed due to plans not being routed right away to water/traffic; plans were routed to them 3/21/22 (KCS)
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2022-03-11 | 2022-03-21 | N/A | N/A | N/A | N/A | N/A | 2022-03-24 | 2022-03-21 | N/A | 2022-03-24 | 2022-03-24 | Comments | 13 | Yes | Rev #1; comments slightly delayed due to plans not being routed right away to water/traffic; plans were routed to them 3/21/22 (KCS)
Bonham Intermediate School | PSE | SP21-22 | BISD Subd (Stephen F Austin) | BISD-Jeff Windsor | Jones & Carter | Revised (Digital) DR | 2022-03-11 | 2022-03-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-19 | 2022-04-19 | Approved | 40 | No | Rev #7 - Waiting on answer to questions about Bus Barn - Revised plans & drainage after construction had started
Bonham Intermediate School | PSE | SP21-22 | BISD Subd (Stephen F Austin) | BISD-Jeff Windsor | Jones & Carter | Revised (Digital) CP | 2022-03-11 | 2022-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-19 | 2022-04-19 | Approved | 40 | No | Rev #7 - Waiting on answer to questions about Bus Barn - Revised plans & drainage after construction had started
AMA Towing | REG | SP22-08 | Parkwood Estates Ph 2, Lt 4 Blk 1 | Elite Business Services LLC | J4 Engineering | 1 DR | 2022-03-14 | 2022-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-14 | 2022-03-14 | Comments | 0 | Yes | N/A
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | 1 CP | 2022-03-14 | 2022-03-14 | 2022-03-23 | N/A | N/A | N/A | N/A | 2022-03-23 | 2022-03-25 | N/A | 2022-03-25 | 2022-03-25 | Comments | 11 | Yes | Digital Copy Recv'd on 3/10/22; Waited on Hard Copy (ccp)
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | 1 EE | 2022-03-14 | 2022-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | N/A | 2022-03-25 | 2022-03-25 | Comments | 11 | Yes | Digital Copy Recv'd on 3/10/22 (ccp)
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | 1 DR | 2022-03-14 | 2022-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-25 | 2022-03-25 | Comments | 11 | Yes | Digital Copy Recv'd on 3/10/22 (ccp)
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | TxDOT Permit | 2022-03-14 | 2022-03-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-15 | Emailed to TxDOT | 1 | Yes | N/A
Sundown Subd C-Store | REG | SP21-48 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) DR | 2022-03-21 | 2022-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-23 | 2022-03-23 | Approved | 2 | Yes | Rev #4
Sundown Subd C-Store | REG | SP21-48 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) CP | 2022-03-21 | 2022-03-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-23 | 2022-03-23 | Comments | 2 | Yes | Rev #3
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Revised (Digital) CP | 2022-03-23 | 2022-03-23 | N/A | N/A | N/A | N/A | N/A | 2022-03-30 | 2022-03-30 | N/A | 2022-03-31 | 2022-03-31 | Comments | 8 | Yes | Rev #1
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Revised (Digital) DR | 2022-03-23 | 2022-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-31 | 2022-03-31 | Comments | 8 | Yes | Rev #1
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Revised (Digital) EE | 2022-03-23 | 2022-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-31 | 2022-03-31 | Comments | 8 | Yes | Rev #1
Academy Preserve Ph 2 | KCS | FP22-05 | Academy Preserve Ph 2, Blk 1 3&4 40 Lts | Fenikes Holdings LLC | RME Engineering | Revised (Digital) CP | 2022-03-24 | 2022-03-24 | N/A | N/A | N/A | N/A | N/A | 2022-03-31 | 2022-03-31 | N/A | 2022-04-04 | 2022-04-04 | Comments | 11 | Yes | Rev #1; KN 3/28/22, JEB 3/31/22 comments (ccp)
Corporate Center Office | REG | SP22-04 | Park Hudson Ph 6, Blk 3 Lt 5 | Builder 10 Construction | McClure & Browne | Revised (Digital) DL | 2022-03-24 | 2022-03-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-05 | 2022-04-05 | Approved | 12 | Yes | Rev #1; review delayed due to vacation & heavy workload (reg)
3850 Sagebriar Dr | REG | SP22-14 | Park Hudson Ph 6, Blk 3 Lt 4 | Key Pride Development | McClure & Browne | Digital DR | 2022-03-24 | 2022-03-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-05 | 2022-04-05 | Approved | 12 | Yes | N/A
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2022-03-31 | 2022-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-06 | N/A | 2022-04-06 | 2022-04-06 | Comments | 6 | Yes | Rev #2; JEB comments 4/1/22; KN comments 4/6/22 (ccp)
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2022-03-31 | 2022-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-06 | 2022-04-06 | Comments | 6 | Yes | Rev #2
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | 1 CP | 2022-04-04 | 2022-04-04 | 2022-04-12 | N/A | N/A | N/A | N/A | 2022-04-14 | 2022-04-11 | N/A | 2022-04-18 | 2022-04-18 | Comments | 13 | Yes | Digital Copy Recv'd 3/31/22; Hard Copy recv'd 4/04/22 (ccp); JEB comments 4/7/22; KN comments 4/11/22
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Digital DR | 2022-04-04 | 2022-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | 2022-04-18 | Approved | 13 | Yes | Digital Copy Recv'd 3/31/22 (ccp)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Digital EE | 2022-04-04 | 2022-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | N/A | 2022-04-18 | 2022-04-18 | Comments | 13 | Yes | Digital Copy Recv'd 3/31/22 (ccp); some quanitites include total development & not just within ROW (reg)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Digital SR | 2022-04-04 | 2022-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | N/A | 2022-04-18 | 2022-04-18 | Approved | 13 | Yes | Digital Copy Recv'd 3/31/22 (ccp)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Digital WR | 2022-04-04 | 2022-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | 2022-04-18 | Approved | 13 | Yes | Digital Copy Recv'd 3/31/22 (ccp)
Rudder Pointe Ph 6 | KCS | FP22-04 | Rudder Pointe Ph 6, Blk 1-4 40 Lts | Bord Development | McClure & Browne | Revised (Digital) CP | 2022-04-05 | 2022-04-05 | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | 2022-04-11 | N/A | 2022-04-14 | 2022-04-14 | Comments | 9 | Yes | Rev #1; KN comments 4/11/22; JEB comments 4/11/22
Rudder Pointe Ph 6 | KCS | FP22-04 | Rudder Pointe Ph 6, Blk 1-4 40 Lts | Bord Development | McClure & Browne | Revised (Digital) DR | 2022-04-05 | 2022-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-14 | 2022-04-14 | Comments | 9 | Yes | Rev #1
Rudder Pointe Ph 6 | KCS | FP22-04 | Rudder Pointe Ph 6, Blk 1-4 40 Lts | Bord Development | McClure & Browne | Revised (Digital) EE | 2022-04-05 | 2022-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-14 | 2022-04-14 | Comments | 9 | Yes | Rev #1
Academy Preserve Ph 2 | KCS | FP22-05 | Academy Preserve Ph 2, Blk 1 3&4 40 Lts | Fenikes Holdings LLC | RME Engineering | Revised (Digital) CP | 2022-04-05 | 2022-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | N/A | 2022-04-11 | 2022-04-11 | Approved | 6 | Yes | Rev #3; JEB comments 4/7/22; KN comments 4/11/22
Take 5 Oil Change | KCS | SP22-03 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Altar Group | 1 CP | 2022-04-06 | 2022-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-11 | N/A | 2022-04-12 | 2022-04-12 | Comments | 6 | Yes | Digital Copy Recv'd on 1/25/22; Waited on Hard Copy (dms)
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Revised (Digital) CP | 2022-04-06 | 2022-04-06 | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | 2022-04-11 | N/A | 2022-04-12 | 2022-04-12 | Comments | 6 | Yes | Rev #2 (Take 5); JEB comments 4/7/22; KN comments 4/11/22
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2022-04-08 | 2022-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-12 | N/A | 2022-04-12 | 2022-04-12 | Approved | 4 | Yes | Rev #3
Austin's Colony Ph 21B & 21C | KCS | FP21-34 | Austin's Colony Ph 21B & 21C | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2022-04-08 | 2022-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-12 | 2022-04-12 | Approved | 4 | Yes | Rev #3
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | 1 CP | 2022-04-12 | 2022-04-13 | 2022-04-26 | N/A | N/A | N/A | N/A | 2022-04-25 | 2022-04-14 | N/A | 2022-04-26 | 2022-04-26 | Comments | 13 | Yes | Digital Copy recv'd 4/7/22; Waited on Hard Copy (ccp); JEB comments 4/13/22; KN comments 4/14/22
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Digital EE | 2022-04-12 | 2022-04-13 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-13 | N/A | 2022-04-26 | 2022-04-26 | Comments | 13 | Yes | Digital Copy recv'd 4/7/22
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Digital DR | 2022-04-12 | 2022-04-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | 2022-04-26 | Comments | 13 | Yes | Digital Copy recv'd 4/7/22. DR received a cursory review as it was not completed in accordance w/ B/CS Guidelines (pse)
Rudder Pointe Ph 6 | KCS | FP22-04 | Rudder Pointe Ph 6, Blk 1-4 40 Lts | Bord Development | McClure & Browne | Revised (Digital) CP | 2022-04-18 | 2022-04-18 | N/A | N/A | N/A | N/A | N/A | 2022-04-19 | 2022-04-26 | N/A | 2022-04-26 | 2022-04-26 | Comments | 8 | Yes | Rev #2; JEB comments 4/20/22; KN comments 4/26/22
Rudder Pointe Ph 6 | KCS | FP22-04 | Rudder Pointe Ph 6, Blk 1-4 40 Lts | Bord Development | McClure & Browne | Revised (Digital) EE | 2022-04-18 | 2022-04-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | 2022-04-26 | Comments | 8 | Yes | Rev #2
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) CP | 2022-04-18 | 2022-04-19 | N/A | N/A | N/A | N/A | N/A | 2022-04-25 | 2022-04-25 | N/A | 2022-04-27 | 2022-04-27 | Comments | 9 | Yes | Rev #1; recv'd 4/18/22 @ 4:59 p.m, distributed until 4/19/22 (ccp); JEB comments 4/20/22; KN comments 4/25/22 (ccp)
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) EE | 2022-04-18 | 2022-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-20 | N/A | 2022-04-27 | 2022-04-27 | Approved | 9 | Yes | Rev #1 (ccp)
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) WR | 2022-04-18 | 2022-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-20 | N/A | 2022-04-24 | 2022-04-27 | Approved | 9 | Yes | Rev #1 (ccp)
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) SR | 2022-04-18 | 2022-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-20 | N/A | 2022-04-27 | 2022-04-27 | Approved | 9 | Yes | Rev #1 (ccp)
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-04-19 | 2022-04-19 | N/A | N/A | N/A | N/A | N/A | 2022-04-25 | 2022-04-25 | N/A | 2022-04-29 | 2022-04-29 | Comments | 10 | Yes | Rev #1; JEB comments 4/19/22; KN comments 4/25/22
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Digital DR | 2022-04-19 | 2022-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-29 | 2022-04-29 | Comments | 10 | Yes | N/A
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) CP | 2022-04-20 | 2022-04-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | Comments | 7 | Yes | Originally recv'd 4/18/22 @ clients' request held until 4/20/22 (ccp); need to know what has changed from previsously approved documents
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) DR | 2022-04-20 | 2022-04-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | Comments | 7 | Yes | Rev #4; Originally recv'd 4/18/22 @ clients' request held until 4/20/22 (ccp); need to know what has changed from previsously approved documents
Merrill Green Prkg Add'n | PSE | SP22-26 | BISD Subd (Richard Carter Survey) | BISD-Paul Buckner | Trace Cryer-PBK | Digital DR | 2022-04-20 | 2022-04-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-04 | 2022-05-04 | Comments | 14 | Yes | Incomplete copy recv'd on 4/4/22 routing held per PSE; Add'l docs recv'd on 4/18/22; Site Plan submitted to SDRC on 4/20/22 (ccp)
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | 1 CP | 2022-04-25 | 2022-04-25 | 2022-04-29 | N/A | N/A | N/A | N/A | 2022-05-04 | 2022-05-05 | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Digital Recv'd on 4/22/22; Waited on Hard Copy; JEB comments 5/3/20; KN comments 5/5/22
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Digital DR | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-11 | 2022-05-11 | Comments | 16 | No | Comments are late due to delayed review for multiple cases w/ same deadline & sole amount of time needed to review DR in depth (reg)
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Digital WR | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Rev #1
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Digital SR | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Rev #1
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Digital EE | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Rev #1
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | 1 CP | 2022-04-25 | 2022-04-25 | 2022-05-03 | N/A | N/A | N/A | N/A | 2022-05-04 | 2022-05-05 | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Digital Recv'd on 4/25/22 (ccp); JEB comments 4/25/22; KN comments 5/5/22
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Digital EE | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-25 | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Need to add public storm sewer to EE (reg)
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Digital DR | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-09 | 2022-05-09 | Comments | 14 | Yes | Need more explanation about detention (reg)
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | 1 CP | 2022-04-25 | 2022-04-25 | 2022-05-03 | N/A | N/A | N/A | N/A | 2022-05-03 | 2022-05-05 | N/A | 2022-05-06 | 2022-05-06 | Comments | 11 | Yes | Digital Recv'd on 4/22/22; Waited on Hard Copy (ccp); JEB comments 4/26/22; KN comments 5/5/22
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Digital EE | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | N/A | 2022-05-06 | 2022-05-06 | Comments | 11 | Yes | Showing required & requested unit pricing, asking for clarificaition (reg)
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Digital DR | 2022-04-25 | 2022-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-06 | 2022-05-06 | Comments | 11 | Yes | Concern with steep grading to adjacent property (reg)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Digital CP | 2022-04-26 | 2022-04-26 | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-02 | N/A | 2022-05-04 | 2022-05-04 | Comments | 8 | Yes | Rev #1; JEB comments 4/26/22; KN comments 5/2/22 (dms); 5 repeat comments (reg)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Digital EE | 2022-04-26 | 2022-04-26 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-26 | N/A | 2022-05-04 | 2022-05-04 | Comments | 8 | Yes | Rev #1; approval dependent upon approval of CP (reg)
1520 N Texas Avenue | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Kimley Horn & Assoc | Revised (Digital) CP | 2022-04-26 | 2022-04-26 | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-02 | N/A | 2022-05-03 | 2022-05-03 | Comments | 7 | Yes | Rev #3; JEB comments 4/27/22; KN comments 5/2/22 (ccp)
Take 5 Oil Change | KCS | SP22-03 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnaker Texas Ave LLC | Altar Group | Digital CP | 2022-04-27 | 2022-04-27 | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | 2022-05-02 | N/A | 2022-05-03 | 2022-05-03 | Comments | 6 | Yes | Rev #2; JEB comments 4/28/22; KN comments 5/2/22 (dms)
American Lumber Pavement Expansion East & West Side | REG | SP22-21 | Bryan Ind'l Park Ph 2, Blk 5 Lt 2 | 4H Texas Properties LLC | Schultz Engineering | Digital DR | 2022-04-27 | 2022-04-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | Approved | 0 | Yes | Digital recv'd 4/27/22; No COB Public Infrastructure or detention pond (ccp)
Ph 4 Commercial Bldg 500 | KCS | SP22-28 | PVD Development Blk 1 Lt 3 | PVD Development Co LLC | Mitchell & Morgan | Digital DL | 2022-04-27 | 2022-04-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | Approved | 15 | No | N/A
Creekside Oaks Ph 1 | KCS | SQ22-03 | Creekside Oaks Ph 1, Blk 2 3&5 44 Lts | BORD Development | McClure & Browne | SQ Permit | 2022-04-27 | 2022-04-28 | N/A | N/A | 2022-04-29 | N/A | 2022-05-03 | N/A | 2022-05-03 | UKN | 2022-05-04 | 2022-05-04 | Comments | 7 | Yes | N/A
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) CP | 2022-04-28 | 2022-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | N/A | 2022-05-04 | 2022-05-04 | Comments | 6 | Yes | Rev #2; JEB comments 4/28/22; KN comments 5/2/22 (dms)
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) CP | 2022-04-29 | 2022-04-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | Comments | 13 | Yes | Rev #1 - Waiting on TxDOT Approval
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) DR | 2022-04-29 | 2022-04-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | Comments | 13 | Yes | Rev #5
New Heights Church/HSC Pkwy Sewer Extn | KCS | SP20-45 | John H Jones (ICL), Tract 57.1 | New Heights Church | J4 Engineering | Revised (Digital) CP | 2022-05-02 | 2022-05-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | N/A | 2022-05-03 | 2022-05-03 | Approved | 1 | Yes | Rev #1; Digital Copy Recv'd on 4/29/22; JEB comments 5/2/22; KN comments 5/3/22 (dms)
Piccino | REG | SP22-23 | Hunter's Revised, Lts 13&14 | NN Out Properties Ltd | J4 Engineering | Digital EE | 2022-05-02 | 2022-05-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | 2022-05-13 | Approved | 11 | Yes | public infrastructure removed. No need to review further(reg)
Piccino | REG | SP22-23 | Hunter's Revised, Lts 13&14 | NN Out Properties Ltd | J4 Engineering | 1 CP | 2022-05-02 | 2022-05-02 | 2022-05-03 | N/A | N/A | N/A | N/A | 2022-05-11 | 2022-05-03 | N/A | 2022-05-13 | 2022-05-13 | Approved | 11 | Yes | Digital Copy Recv'd on 4/28/22; JEB comments 5/2/22; KN comments 5/3/22 (dms) public infrastructure removed. No need to review further (reg)
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | 1 EE | 2022-05-04 | 2022-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-04 | N/A | 2022-05-18 | 2022-05-18 | Comments | 14 | Yes | Digital Copy Recv'd on Same Day (dms)
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | 3 CP | 2022-05-04 | 2022-05-04 | 2022-05-17 | N/A | N/A | N/A | N/A | 2022-05-13 | 2022-05-12 | N/A | 2022-05-18 | 2022-05-18 | Comments | 14 | Yes | Only 2 Routed; Digital Copy Recv'd on Same Day; JEB comments 5/4/22; KN comments 5/12/22 (dms)
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Digital SR | 2022-05-04 | 2022-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-10 | N/A | 2022-05-13 | 2022-05-13 | Comments | 9 | Yes | Emailed to CoCS (bmg)
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Digital EE | 2022-05-04 | 2022-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-10 | N/A | 2022-05-13 | 2022-05-13 | Comments | 9 | Yes | Emailed to CoCS (bmg)
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | 1 CP | 2022-05-04 | 2022-05-06 | 2022-05-11 | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | N/A | 2022-05-13 | 2022-05-13 | Comments | 9 | Yes | JEB comments 5/10/22 (dms); Emailed to CoCS (bmg)
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) CP | 2022-05-05 | 2022-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-10 | N/A | 2022-05-12 | 2022-05-12 | Comments | 7 | Yes | Rev #3
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) EE | 2022-05-09 | 2022-05-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | Approved | 3 | Yes | Rev #2
Sundown Subd C-Store | REG | SP21-48 | Sundown Subd., Blk 1 Lt 1 | Ruby Cunningham Support Trust | J4 Engineering | Revised (Digital) CP | 2022-05-09 | 2022-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-16 | 2022-05-16 | Approved | 7 | Yes | Rev #1; delayed due to needed conversation with LH
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | Digital DL | 2022-05-10 | 2022-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | Approved | 2 | Yes | No Comments - City of College Station Drainage
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | Digital TIA | 2022-05-10 | 2022-05-10 | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | N/A | N/A | 2022-05-12 | 2022-05-12 | Comments | 2 | Yes | Further Discussion due to BioCorridor Zoning
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | Digital WR | 2022-05-10 | 2022-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-12 | 2022-05-12 | Approved | 2 | Yes | No Comments - City of College Station Water Lines
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | 1 EE | 2022-05-10 | 2022-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-11 | N/A | 2022-05-12 | 2022-05-12 | Approved | 2 | Yes | Digital Copy Recv'd on 5/3/22 (dms)
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | 1 CP | 2022-05-10 | 2022-05-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | N/A | 2022-05-12 | 2022-05-12 | Comments | 2 | Yes | Digital Copy Recv'd on 5/3/22; Waited on Hard Copy; JEB comments 5/11/22; KN comments 5/13/22 (dms)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Revised (Digital) CP | 2022-05-11 | 2022-05-11 | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | 2022-05-16 | N/A | 2022-05-23 | 2022-05-23 | Comments | 12 | Yes | Rev #2; KN comments 5/13/22; JEB comments 5/16/22; delayed due to illness; approved pending BTU line design approval (reg)
Foxwood Crossing Ph 3 | PSE | FP22-06 | Foxwood Crossing Ph 3, Blk 4-6 27 Lts | BK Homes Development Inc | JBS Engineering | Revised (Digital) CP | 2022-05-12 | 2022-05-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | 2022-05-13 | Approved | 1 | Yes | Rev #4 (Sheet C4.0 only)
First Baptist Church | KCS | SP22-19 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | 1 CP | 2022-05-12 | 2022-05-12 | 2022-05-31 | N/A | N/A | N/A | N/A | 2022-05-24 | 2022-05-13 | N/A | 2022-05-24 | 2022-05-24 | Comments | 12 | Yes | Digital copy recv'd 5/11/2022; Waited on Hard Copy; JEB comments 5/12/22; KN comments 5/13/22 (ccp)
First Baptist Church | KCS | SP22-19 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | Digital DR | 2022-05-12 | 2022-05-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | 2022-05-24 | Approved | 12 | Yes | N/A
First Baptist Church | KCS | SP22-19 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | Digital EE | 2022-05-12 | 2022-05-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | 2022-05-24 | Comments | 12 | Yes | N/A
LaPerla Meat Market | KCS | SP20-16 | Bryan Original Townsite, Blk 194 Lts 1R & 6R | Alexandria Hernandez-Aguilar | McClure & Browne | TxDOT Permit | 2022-05-13 | 2022-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | 2022-05-13 | Emailed to TxDOT | 0 | Yes | N/A
Mechanic Shop | KCS | SP22-07 | Winter Add'n, Blk 1 Lts 3&4 | Javier Saldanae | The Brown Group | TxDOT Permit | 2022-05-13 | 2022-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-13 | 2022-05-13 | Emailed to TxDOT | 0 | Yes | N/A
LaPerla Meat Market | KCS | SP20-16 | Bryan Original Townsite, Blk 194 Lts 1R & 6R | Alexandria Hernandez-Aguilar | McClure & Browne | 1 CP | 2022-05-19 | 2022-05-19 | 2022-05-20 | N/A | N/A | N/A | N/A | 2022-05-24 | N/A | N/A | 2022-05-24 | 2022-05-24 | Comments | 6 | Yes | Digital Recv'd 5/17/22 (ccp)
LaPerla Meat Market | KCS | SP20-16 | Bryan Original Townsite, Blk 194 Lts 1R & 6R | Alexandria Hernandez-Aguilar | McClure & Browne | Digital EE | 2022-05-19 | 2022-05-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | 2022-05-24 | Comments | 6 | Yes | N/A
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | Revised (Digital) CP | 2022-05-26 | 2022-05-26 | N/A | N/A | N/A | N/A | N/A | 2022-06-03 | 2022-05-31 | N/A | 2022-06-08 | 2022-06-08 | Comments | 14 | Yes | Rev #1; JEB comments 5/27/22; KN comments 5/31/22
First Baptist Church | KCS | SP22-19 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | Revised (Digital) CP | 2022-05-31 | 2022-05-31 | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | N/A | 2022-06-10 | 2022-06-10 | Approved | 10 | Yes | Rev #1; JEB comments 5/31/22;KN comments 6/8/22
First Baptist Church | KCS | SP22-19 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | Revised (Digital) EE | 2022-05-31 | 2022-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-10 | 2022-06-10 | Approved | 10 | Yes | Rev #1
First Baptist Church | KCS | SP22-19 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | Revised (Digital) DR | 2022-05-31 | 2022-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-10 | 2022-06-10 | Approved | 10 | Yes | Rev #1
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Revised (Digital) CP | 2022-05-31 | 2022-05-31 | N/A | N/A | N/A | N/A | N/A | 2022-06-07 | 2022-06-08 | N/A | 2022-06-08 | 2022-06-08 | Comments | 8 | Yes | Rev #1; JEB & KN comments 6/8/22
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Revised (Digital) EE | 2022-05-31 | 2022-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | Comments | 8 | Yes | Rev #1; need to add sidewalk since not in 380 agreement
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Digital DR | 2022-05-31 | 2022-05-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | Approved | 8 | Yes | RTC address comments & original DL needs revision
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) CP | 2022-06-01 | 2022-06-01 | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | N/A | 2022-06-08 | 2022-06-08 | Comments | 7 | Yes | Rev #1; JEB comments 6/2/22;KN comments 6/8/22
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) DR | 2022-06-01 | 2022-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | Approved | 7 | Yes | Rev #1
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) EE | 2022-06-01 | 2022-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-08 | Comments | 7 | Yes | Rev #1
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2022-06-06 | 2022-06-07 | N/A | N/A | N/A | N/A | N/A | 2022-06-13 | 2022-06-14 | N/A | 2022-06-14 | 2022-06-14 | Comments | 8 | Yes | Rev #1; JEB comments 6/10/22; KN comments 6/14/22
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) EE | 2022-06-06 | 2022-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-10 | N/A | 2022-06-14 | 2022-06-14 | Approved | 8 | Yes | Rev #1
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) DR | 2022-06-06 | 2022-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-14 | 2022-06-14 | Comments | 8 | Yes | Rev #1
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) CP | 2022-06-08 | 2022-06-08 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-14 | N/A | 2022-06-15 | 2022-06-15 | Comments | 7 | Yes | Rev #2; JEB comments 6/8/22; KN comments 6/14/22
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) DR | 2022-06-08 | 2022-06-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-15 | 2022-06-15 | Comments | 7 | Yes | Rev #2
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2022-06-09 | 2022-06-09 | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | 2022-06-16 | N/A | 2022-06-17 | 2022-06-17 | Comments | 8 | Yes | Rev #1; JEB comments 6/14/22; KN comments 6/16/22; multiple repeat comments (reg)
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) EE | 2022-06-09 | 2022-06-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-14 | N/A | 2022-06-17 | 2022-06-17 | Comments | 8 | Yes | Rev #1; approval dependent upon approval of CP (reg)
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2022-06-09 | 2022-06-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-17 | 2022-06-17 | Approved | 8 | Yes | Rev #1
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Revised (Digital) CP | 2022-06-10 | 2022-06-10 | N/A | 2022-06-13 | N/A | N/A | N/A | N/A | 2022-06-16 | N/A | 2022-06-14 | 2022-06-16 | Comments | 6 | Yes | Rev #3; BTU line design approved. Minor sheet error/correction needed (reg)
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Revised (Digital) DR | 2022-06-10 | 2022-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-14 | 2022-06-16 | Comments | 6 | Yes | Rev #3; Minor sheet error/correction needed (reg)
Creekside Oaks Ph 1 | KCS | FP22-15 | Creekside Oaks Ph 1, Blk 2 3&5 44 Lts | BORD Development | McClure & Browne | 3 CP | 2022-06-14 | 2022-06-15 | 2022-06-28 | 2022-06-28 | N/A | N/A | N/A | 2022-06-27 | 2022-06-28 | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Only 2 Routed (dms); Digital recv'd on same day (ccp); JEB & KN comments 6/28/22 (dms); late - out unexpectedly 6/27/22 through 7/1/22 (kcs)
Creekside Oaks Ph 1 | KCS | FP22-15 | Creekside Oaks Ph 1, Blk 2 3&5 44 Lts | BORD Development | McClure & Browne | 1 EE | 2022-06-14 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Digital Recv'd on same day (ccp); late - out unexpectedly 6/27/22 through 7/1/2022 (kcs)
Creekside Oaks Ph 1 | KCS | FP22-15 | Creekside Oaks Ph 1, Blk 2 3&5 44 Lts | BORD Development | McClure & Browne | Digital DR | 2022-06-14 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Late - out unexpectedly 6/27/22 through 7/1/22 (kcs)
Creekside Oaks Ph 1 | KCS | FP22-15 | Creekside Oaks Ph 1, Blk 2 3&5 44 Lts | BORD Development | McClure & Browne | Digital SR | 2022-06-14 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Late - out unexpectedly 6/27/22 through 7/1/22 (kcs)
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Digital CP | 2022-06-14 | 2022-06-14 | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-16 | N/A | 2022-06-27 | 2022-07-05 | Comments | 21 | No | JEB comments 6/15/22; KN no comment 6/16/22
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Digital DR | 2022-06-14 | 2022-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | N/A
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | 3 CP | 2022-06-14 | 2022-06-15 | 2022-06-27 | 2022-06-28 | N/A | N/A | 2022-06-28 | 2022-06-27 | 2022-06-28 | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Only 2 Routed; Digital recv'd on 6/14/22; JEB comments 6/21/22; KN comments 6/28/22 (dms)
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | 1 EE | 2022-06-14 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Digital recv'd on same day (ccp)
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | 1 DL | 2022-06-14 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-05 | 2022-07-05 | Comments | 21 | No | Digital recv'd on same day (ccp)
S Beauty Supply Store | REG | SP22-32 | Cavitts Woodland Heights Ph 1, Blk A Lts 6 & 7 | K Han & S Lee | Galindo Engineers | Digital DR | 2022-06-14 | 2022-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-20 | 2022-06-20 | Comments | 6 | Yes | N/A
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | 1 CP | 2022-06-15 | 2022-06-15 | 2022-06-27 | N/A | N/A | N/A | N/A | 2022-06-27 | 2022-06-28 | N/A | 2022-06-29 | 2022-06-29 | Comments | 14 | Yes | Digital recv'd on 6/14/22; Waited on Hard Copy Recv'd 6/15/22 (ccp); JEB & KN comments 6/28/22 (dms)
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Digital DR | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-29 | 2022-06-29 | Comments | 14 | Yes | N/A
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Digital EE | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | N/A | 2022-06-29 | 2022-06-29 | Comments | 14 | Yes | N/A
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Digital UL | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | N/A | 2022-06-29 | 2022-06-29 | Comments | 14 | Yes | N/A
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) DR | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-16 | 2022-06-16 | Comments | 1 | Yes | Rev #6 - Requested TxDOT Reaponse to Revisions
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | N/A | 2022-06-20 | 2022-06-20 | Approved | 5 | Yes | Rev #2; JEB comments 6/15/22; KN comments 6/21/22
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) DR | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-20 | 2022-06-20 | Comments | 5 | Yes | Rev #2
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) EE | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-15 | N/A | 2022-06-20 | 2022-06-20 | Approved | 5 | Yes | Rev #2
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Digital DR | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | 2022-06-28 | Comments | 13 | Yes | N/A
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Digital TIA | 2022-06-15 | 2022-06-15 | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | N/A | N/A | 2022-06-28 | 2022-06-28 | Comments | 13 | Yes | N/A
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Revised (Digital) CP | 2022-06-20 | 2022-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-20 | 2022-06-20 | Approved | 0 | Yes | Rev #4
Traditions Ph 38 | REG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Revised (Digital) DR | 2022-06-20 | 2022-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Approved | 2 | Yes | Rev #4
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) DR | 2022-06-20 | 2022-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-05 | 2022-07-05 | Comments | 15 | No | Rev #7
S College Restaurant | BMG | SP22-33 | Palestine Subd., Blk 1 Lt 1 | Deeb Nader & Insherah Asadi | Schultz Engineering | TxDOT Permit | 2022-06-20 | 2022-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-20 | 2022-06-20 | Comments | 0 | Yes | Comments from COB engineering to be resolved prior to TxDOT submission
Marco Polo Ph 1 | REG | SP22-20 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) DR | 2022-06-21 | 2022-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Approved | 1 | Yes | Rev #3
Highland Oaks Ph 1 | REG | SQ22-04 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | SQ Permit | 2022-06-21 | 2022-06-21 | N/A | N/A | 2022-06-21 | N/A | 2022-06-27 | 2022-06-21 | 2022-06-27 | 2022-06-22 | 2022-06-27 | 2022-06-27 | Comments | 6 | Yes | N/A
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | TxDOT Permit | 2022-06-22 | 2022-06-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | 2022-06-27 | Emailed to TxDOT | 5 | Yes | N/A
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Revised (Digital) SR | 2022-06-28 | 2022-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-07 | N/A | 2022-07-07 | 2022-07-07 | Comments | 8 | Yes | Rev #1; JEB & KN comments 7/7/22
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Revised (Digital) EE | 2022-06-28 | 2022-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-07 | 2022-07-07 | Comments | 8 | Yes | Rev #1; Hard Copy Recv'd 6/29/22 (not req)
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Revised (Digital) CP | 2022-06-28 | 2022-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-07 | N/A | 2022-07-07 | 2022-07-07 | Comments | 8 | Yes | Rev #1; Hard Copy Recv'd 6/29/22 (not req); KN comments 6/29/22 (dms); JEB comments 7/7/22
LaPerla Meat Market | KCS | SP20-16 | Bryan Original Townsite, Blk 194 Lts 1R & 6R | Alexandria Hernandez-Aguilar | McClure & Browne | Revised (Digital) CP | 2022-06-28 | 2022-06-29 | 2022-07-07 | N/A | N/A | N/A | N/A | 2022-07-07 | 2022-07-03 | N/A | 2022-07-08 | 2022-07-08 | Comments | 9 | Yes | Rev #1
La Vita Centro II | REG | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Revised (Digital) CP | 2022-06-28 | 2022-06-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-01 | 2022-07-01 | Approved | 3 | Yes | Rev #2
Highland Oaks Ph 1 | REG | SQ22-04 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Revised SQ Permit | 2022-06-28 | 2022-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-01 | 2022-07-07 | Approved | 9 | Yes | Rev #1
La Vita Centro II | REG ZFK | SP22-24 | Bryan Original Townsite, Blk 144 Lts 3-5 | La Vita Centro LLC | J4 Engineering | Revised (Digital) EE | 2022-06-29 | 2022-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-01 | 2022-07-01 | Approved | 2 | Yes | Rev #2
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-06-30 | 2022-06-30 | N/A | N/A | N/A | N/A | N/A | 2022-07-06 | 2022-07-06 | N/A | 2022-07-12 | 2022-07-12 | Comments | 11 | Yes | Rev #2; KN comments 7/3/22; JEB comment recv'd 7/6/22
S Beauty Supply Store | REG | SP22-32 | Cavitts Woodland Heights Ph 1, Blk A Lts 6 & 7 | K Han & S Lee | Galindo Engineers | Digital DR | 2022-06-30 | 2022-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-01 | 2022-07-01 | Approved | 1 | Yes | Rev #1
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Revised (Digital) CP | 2022-07-01 | 2022-07-01 | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-13 | N/A | 2022-07-14 | 2022-07-14 | Comments | 12 | Yes | Rev #1; JEB comments 7/13/22
Highland Oaks Ph 1 | REG | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Revised (Digital) DR | 2022-07-01 | 2022-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-14 | 2022-07-14 | Comments | 12 | Yes | Rev #1
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) CP | 2022-07-07 | 2022-07-07 | N/A | N/A | N/A | N/A | N/A | 2022-07-14 | 2022-07-14 | N/A | 2022-07-15 | 2022-07-15 | Comments | 8 | Yes | Rev #1; JEB comments 7/14/22
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) DR | 2022-07-07 | 2022-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-15 | 2022-07-15 | Comments | 8 | Yes | Rev #1
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) SR | 2022-07-07 | 2022-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-14 | N/A | 2022-07-15 | 2022-07-15 | Comments | 8 | Yes | Rev #1
LaPerla Meat Market | KCS | SP20-16 | Bryan Original Townsite, Blk 194 Lts 1R & 6R | Alexandria Hernandez-Aguilar | McClure & Browne | Revised (Digital) CP | 2022-07-11 | 2022-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-11 | Approved | 0 | Yes | Rev #2
Shops @ Hudson Oaks | REG | SP22-39 | Park Hudson Ph 4, Blk 4 Lt 4R | BTX Retail | Walker Partners | Digital DR | 2022-07-12 | 2022-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-22 | 2022-07-22 | Comments | 10 | Yes | Pending TXDOT drainage design & TXDOT approval
Poco Loco Grocery Store Prkg Lt/Take 5 Oil Change | KCS | SP22-05 | Stephen F Austin #10, Blk 2 Lt 2.1 | Spinnake Texas Ave LLC | Kimley Horn & Assoc | TxDOT Permit | 2022-07-14 | 2022-07-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-20 | 2022-07-21 | Emailed to TxDOT | 7 | Yes | N/A
Majestic Pointe Ph 1 | PSE | FP21-15 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) CP | 2022-07-15 | 2022-07-15 | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-16 | N/A | 2022-07-22 | 2022-07-22 | Comments | 7 | Yes | Rev #4; JEB comments 7/16/22; KN comments 7/16/22; Submittal Rejected by PM - Previous Comments not Addressed
Majestic Pointe Ph 1 | PSE | FP21-15 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) DR | 2022-07-15 | 2022-07-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-22 | 2022-07-22 | Comments | 7 | Yes | Rev #4; Submittal Rejected by PM - Previous Comments not Addressed
Majestic Pointe Ph 1 | PSE | FP21-15 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) EE | 2022-07-15 | 2022-07-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-16 | N/A | 2022-07-22 | 2022-07-22 | Comments | 7 | Yes | Rev #4; Submittal Rejected by PM - Previous Comments not Addressed
Majestic Pointe Ph 1 | PSE | FP21-15 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) SR | 2022-07-15 | 2022-07-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-16 | N/A | 2022-07-22 | 2022-07-22 | Comments | 7 | Yes | Rev #4; Submittal Rejected by PM - Previous Comments not Addressed
FujiFilm Biotech Vic Warehouse | PSE | SP22-31 | Traditions Ph 25, Blk 1 Lt 3 | Fujifilm Diosynth Biotechnologies | Gessner Engineering | Revised (Digital) CP | 2022-07-15 | 2022-07-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-16 | N/A | 2022-07-19 | 2022-07-19 | Approved | 4 | Yes | Rev #2; JEB comments 7/15/22; KN comments 7/16/22
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-07-18 | 2022-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | N/A | 2022-07-25 | 2022-07-26 | Comments | 8 | Yes | Rev #3; JEB comments 7/20/22; KN comments 7/27/22
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) DR | 2022-07-18 | 2022-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-29 | 2022-08-29 | Comments | 42 | No | Rev #1
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) CP | 2022-07-18 | 2022-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | 2022-07-19 | Approved | 1 | Yes | Recv'd Verifiction of TxDOT Approval
Sterling "KIA" Subaru | PSE | SP21-32 | Mid Towne Center Subd., Blk 1 Lt1 | Terolyn Realty LP | Schultz Engineering | Revised (Digital) DR | 2022-07-18 | 2022-07-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-19 | 2022-07-19 | Approved | 1 | Yes | Recv'd Verifiction of TxDOT Approval
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) CP | 2022-07-20 | 2022-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | N/A | 2022-07-27 | 2022-08-18 | Approved | 29 | No | Rev #2; JEB comments 7/25/22; KN comments 7/27/22 [Approved pending FP Development Permit & execution of Trust Agreement per Legal - BMG]
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) EE | 2022-07-20 | 2022-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | 2022-08-15 | Approved | 26 | No | Rev #2 [Approved pending FP Development Permit & execution of Trust Agreement per Legal - BMG]
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) DR | 2022-07-20 | 2022-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | 2022-08-12 | Approved | 23 | No | Rev #2 [Approved pending FP Development Permit & execution of Trust Agreement per Legal - BMG]
Hudson at University Ph 2 | BMG | RP22-19 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | RME Engineering | Revised (Digital) UR | 2022-07-20 | 2022-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-27 | 2022-08-02 | Approved | 13 | Yes | Rev #2 [Approved pending FP Development Permit & execution of Trust Agreement per Legal - BMG]
Chick Lane Water Tower | KCS | SP22-36 | Edgewater Ph 3, Blk 21 Lt 50 | COB-Jayson Barfknecht | GLS | Digital DR | 2022-07-25 | 2022-07-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2022-08-02 | Approved | 8 | Yes | Rev #1
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | 1 CP | 2022-07-27 | 2022-07-28 | 2022-08-08 | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-08-02 | N/A | 2022-08-09 | 2022-08-09 | Comments | 13 | Yes | Digital recv'd on 7/25/22, waited on hard copy; KN comments 7/31/22; JEB comments 8/2/22 (ccp)
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Digital UR | 2022-07-27 | 2022-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | N/A | 2022-08-09 | 2022-08-09 | Comments | 13 | Yes | Digital copy recv'd 7/25/22, Waited on Hard Copy (ccp)
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | 1 EE | 2022-07-27 | 2022-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | N/A | 2022-08-09 | 2022-08-09 | Comments | 13 | Yes | N/A
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | 1 CP | 2022-07-27 | 2022-07-28 | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | N/A | N/A | 2022-08-09 | 2022-08-09 | Emailed to TxDOT | 13 | Yes | Digital copy recv'd 7/25/22; Waited on hard copy (ccp); Turn Lanes; TXDOT comments 8/12/22 & sent to applicant (reg)
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) DR | 2022-07-27 | 2022-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-08-09 | Comments | 13 | Yes | Rev #1
BISD Maintenance & Transportation Facility | REG | SP22-44 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) TIA | 2022-07-27 | 2022-07-28 | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | N/A | N/A | 2022-08-09 | 2022-08-09 | Approved | 13 | Yes | Rev #1
Wholesale/Fabrication Bldg | BMG | SP22-35 | Carrabba Ind'l Park Ph 11, Blk 1 Lt 8 | GRT Interests LLC | J4 Engineering | Digital DR | 2022-08-01 | 2022-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2022-08-02 | Comments | 1 | Yes | N/A
1411 E WJB Pkwy | BMG | SP22-46 | John F Ettle Add'n No 2, Blk 1 Lts 17&18 | Mike Ramirez | N/A | TxDOT Permit | 2022-08-01 | 2022-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-01 | 2022-08-02 | Emailed to TxDOT | 1 | Yes | N/A
Aqua Tots | KCS | SP22-48 | Bryan Towne Center, Blk 3 Lt 2 | Carson Sheen Trustee | J4 Engineering | Digital DL | 2022-08-03 | 2022-08-03 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | 2022-08-11 | 2022-08-16 | Approved | 13 | Yes | Comments sent on 16th same as in 2nd SDRC notification (KCS)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | 3 CP | 2022-08-04 | 2022-08-04 | 2022-08-16 | 2022-08-16 | N/A | N/A | N/A | 2022-08-16 | 2022-08-12 | N/A | 2022-08-17 | 2022-08-17 | Comments | 13 | Yes | Recv'd Digital 8/4/22 (ccp); Only 1 Routed for Rev (dms); KN comments 8/10/22; JEB comments 8/12/22
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Digital WR | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | N/A | 2022-08-16 | 2022-08-17 | Comments | 13 | Yes | N/A
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Digital SR | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | N/A | 2022-08-16 | 2022-08-17 | Comments | 13 | Yes | N/A
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Digital EE | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | N/A | 2022-08-16 | 2022-08-17 | Comments | 13 | Yes | N/A
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Digital DL | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-16 | 2022-08-17 | Comments | 13 | Yes | N/A
Oak Creek Ranch | KCS | PP22-23 | Oak Creek Ranch | E & F Development Inc | Mitchell & Morgan | Digital TIA | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | 2022-08-16 | N/A | N/A | 2022-08-22 | 2022-08-22 | Comments | 18 | No | N/A
Marco Polo Ph 1 | REG | SP22-41 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | 1 CP | 2022-08-04 | 2022-08-04 | 2022-08-05 | 2022-08-09 | N/A | N/A | N/A | 2022-08-08 | 2022-08-10 | N/A | 2022-08-10 | 2022-08-10 | Comments | 6 | Yes | Digital copy recv'd 7/27/22; Waited on hard copy; 2nd request sent 8/3/22; JEB comments 8/8/22; KN comments 8/10/22 (ccp)
Marco Polo Ph 1 | REG | SP22-41 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Digital DR | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-10 | 2022-08-10 | Comments | 6 | Yes | N/A
Marco Polo Ph 1 | REG | SP22-41 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Digital EE | 2022-08-04 | 2022-08-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-10 | 2022-08-10 | Comments | 6 | Yes | N/A
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Digital UR | 2022-08-08 | 2022-08-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | N/A | 2022-08-15 | 2022-08-15 | Approved | 7 | Yes | N/A
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2022-08-08 | 2022-08-09 | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | N/A | 2022-08-15 | 2022-08-15 | Comments | 7 | Yes | Rev #2; JEB no comments 8/11/22; KN no comments 8/12/22; BTU line design & easement needed
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) EE | 2022-08-08 | 2022-08-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | 2022-08-15 | Approved | 7 | Yes | Rev #2
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2022-08-08 | 2022-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-22 | 2022-08-22 | Comments | 14 | Yes | Rev #1
Wholesale/Fabrication | BMG | SP22-35 | Carrabba Ind'l Park Ph 11, Blk 1 Lt 8 | GRT Interests LLC | J4 Engineering | Digital DL | 2022-08-08 | 2022-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2022-08-11 | Comments | 3 | Yes | N/A
Wholesale/Fabrication | BMG | SP22-35 | Carrabba Ind'l Park Ph 11, Blk 1 Lt 8 | GRT Interests LLC | J4 Engineering | Suppl DL | 2022-08-08 | 2022-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-11 | 2022-08-11 | Comments | 3 | Yes | N/A
University TXB C-Store/Gas station | BMG | SP22-30 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | Cool Breeze Consultants | Digital DR | 2022-08-09 | 2022-08-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-15 | 2022-08-15 | Comments | 6 | Yes | N/A
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) CP | 2022-08-10 | 2022-08-10 | N/A | N/A | N/A | N/A | 2022-08-17 | 2022-08-17 | 2022-08-12 | N/A | 2022-08-24 | 2022-08-24 | Comments | 14 | Yes | Rev #1; JEB & KN comments 8/12/22
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) EE | 2022-08-10 | 2022-08-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | Comments | 14 | Yes | Rev #1
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) DR | 2022-08-10 | 2022-08-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | Comments | 14 | Yes | Rev #1
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | 1 CP | 2022-08-15 | 2022-08-15 | 2022-08-24 | N/A | N/A | N/A | N/A | 2022-08-25 | 2022-08-23 | N/A | 2022-08-29 | 2022-08-29 | Comments | 14 | Yes | Digital Copy Recv'd 8/12/22; Waited on Hard Copy (dms); JEB & KN comments 8/23/22
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | Digital EE | 2022-08-15 | 2022-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-23 | N/A | 2022-08-29 | 2022-08-29 | Comments | 14 | Yes | N/A
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | Digital DR | 2022-08-15 | 2022-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-29 | 2022-08-29 | Approved | 14 | Yes | N/A
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Digital WR | 2022-08-18 | 2022-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2022-09-02 | Approved | 15 | No | N/A
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2022-08-19 | 2022-08-22 | N/A | UKN | N/A | N/A | N/A | N/A | 2022-08-23 | N/A | 2022-09-01 | 2022-09-01 | Comments | 13 | Yes | Rev #3; JEB comments recv'd 8/22/22; KN comments recv'd 8/23/22; BTU comments never recv'd, needed for final approval (reg)
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-08-19 | 2022-08-22 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-23 | N/A | 2022-08-29 | 2022-08-29 | Comments | 10 | Yes | Rev #4; JEB comments recv'd 8/22/22; KN comments recv'd 8/23/22
Bank of Brenham | CRB | SP22-51 | Penner Place, Blk 2, Lt 5R | Jim E Kruse | Kimley Horn & Assoc | Digital DL | 2022-08-24 | 2022-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | Comments | 7 | Yes | N/A
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Revised (Digital) SR | 2022-08-30 | 2022-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | N/A | 2022-09-07 | 2022-09-07 | Comments | 7 | Yes | Rev #2; plans are conditionally approved but cannot be released at this time per JEB
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Revised (Digital) EE | 2022-08-30 | 2022-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-07 | 2022-09-07 | Comments | 7 | Yes | Rev #2; plans are conditionally approved but cannot be released at this time per JEB
Turkey Creek Sewer Extn | BMG | FP22-17 | Turkey Creek Subd., Blk 1 Lts 1&2 | BCS Turkey Creek LP | Mitchell & Morgan | Revised (Digital) CP | 2022-08-30 | 2022-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | N/A | 2022-09-07 | 2022-09-07 | Comments | 7 | Yes | Rev #2; plans are conditionally approved but cannot be released at this time per JEB
Traditions Ph 38 | REG BMG | FP22-09 | Traditions Ph 38, Blk 1-3 35 Lts | Bryan Traditions LP | Schultz Engineering | Revised (Digital) DR | 2022-08-31 | 2022-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | 2022-09-06 | Approved | 5 | Yes | Rev #5
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) CP | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | N/A | 2022-09-13 | 2022-09-13 | Comments | 11 | Yes | Rev #1; KP comments 9/12/22 & JEB comments 9/13/22 (dms)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) EE | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | Comments | 11 | Yes | Rev #1
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) SR | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | Comments | 11 | Yes | Rev #1
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) WR | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | Comments | 11 | Yes | Rev #1
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) DR | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | 2022-09-13 | Comments | 11 | Yes | Rev #1
Marco Polo Ph 1 | REG | SP22-41 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) DR | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | 2022-09-07 | Approved | 5 | Yes | Rev #1
Marco Polo Ph 1 | REG | SP22-41 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) EE | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | 2022-09-07 | Approved | 5 | Yes | Rev #1
Marco Polo Ph 1 | REG ZFK | SP22-41 | Bryan Original Townsite, Blk 96 Lts 2R&3R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2022-09-02 | 2022-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | N/A | 2022-09-06 | 2022-09-07 | Approved | 5 | Yes | Rev #1; JEB no comments 9/2/22 (reg)
University TXB C-Store/Gas Station | BMG | SP22-30 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | Cool Breeze Consultants | Revised (Digital) DR | 2022-09-06 | 2022-09-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2022-09-15 | Comments | 9 | Yes | Rev #1
Miramont Sec 19 | REG | FP22-16 | Miramont Sec 19, Lts 1-14 | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2022-09-07 | 2022-09-07 | N/A | 2022-09-07 | N/A | N/A | N/A | N/A | 2022-09-08 | N/A | 2022-09-12 | 2022-09-12 | Approved | 5 | Yes | Rev #4
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) CP | 2022-09-08 | 2022-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-13 | N/A | 2022-09-21 | 2022-09-21 | Comments | 13 | Yes | Rev #2; JEB comment 9/13/22 (dms)
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) EE | 2022-09-08 | 2022-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | Comments | 13 | Yes | Rev #2
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) DR | 2022-09-08 | 2022-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | Comments | 13 | Yes | Rev #2
C C Creations | PSE | SQ22-05 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | SQ Permit | 2022-09-09 | 2022-09-13 | N/A | N/A | 2022-09-13 | N/A | UKN | N/A | 2022-09-13 | 2022-09-16 | 2022-09-20 | 2022-09-20 | Approved | 11 | Yes | Existing trees to be saved must be protected
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | Revised (Digital) EE | 2022-09-09 | 2022-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | Comments | 12 | Yes | Rev #1
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | Revised (Digital) CP | 2022-09-09 | 2022-09-13 | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | 2022-09-21 | N/A | 2022-09-21 | 2022-09-21 | Comments | 12 | Yes | Rev #1; JEB comment 9/14/22 (dms); KN comment 9/21/22
Traditions Ph 20D | REG | FP22-24 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | TxDOT Permit | 2022-09-13 | 2022-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-16 | 2022-09-16 | Comments | 3 | Yes | On hold until TXDOT approves DR & culvert design
Bank of Brenham | CRB | SP22-51 | Penner Place, Blk 2, Lt 5R | Jim E Kruse | Kimley Horn & Assoc | 1 Drainage CP | 2022-09-15 | 2022-09-16 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-29 | Comments | 14 | Yes | N/A
Bank of Brenham | CRB | SP22-51 | Penner Place, Blk 2, Lt 5R | Jim E Kruse | Kimley Horn & Assoc | Digital DR | 2022-09-15 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-27 | 2022-09-29 | Comments | 14 | Yes | N/A
Traditions Ph 20D | REG | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | 1 CP | 2022-09-16 | 2022-09-16 | 2022-09-26 | 2022-09-28 | N/A | N/A | N/A | 2022-09-27 | 2022-09-28 | N/A | 2022-10-04 | 2022-10-04 | Comments | 18 | No | Digital Drawing Recv'd on 9/13/22; Waited on Hard-Copy; JEB comments 9/20/22; KN comments 9/28/22 (dms)
Traditions Ph 20D | REG | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Digital EE | 2022-09-16 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | N/A | 2022-10-04 | 2022-10-04 | Comments | 18 | No | REG delayed review due to drainage report concerns
Traditions Ph 20D | REG | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Digital UR | 2022-09-16 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | N/A | 2022-10-04 | 2022-10-04 | Approved | 18 | No | N/A
Traditions Ph 20D | REG | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Digital DR | 2022-09-16 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2022-10-04 | Comments | 18 | No | REG delayed review due to drainage report concerns
Traditions Ph 20E | REG | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Digital UR | 2022-09-16 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | N/A | 2022-10-04 | 2022-10-04 | Approved | 18 | No | N/A
Traditions Ph 20E | REG | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Digital DR | 2022-09-16 | 2022-09-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2022-10-04 | Comments | 18 | No | REG delayed review due to drainage report concerns
University TXB C-Store/Gas Station | BMG | SP22-30 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | Cool Breeze Consultants | Revised (Digital) DR | 2022-09-20 | 2022-09-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | 2022-09-20 | Approved | 0 | Yes | Rev #2
Saint Gobain Bldg Expansion | CRB | SP22-50 | Brazos County Ind'l Park Ph 3, Blk 3 Lt 1 | Saint Gobain | Kevin McCreary | Digital DR | 2022-09-20 | 2022-09-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2022-10-04 | Comments | 14 | Yes | N/A
Randolph Townhomes | CRB | SP22-57 | Bryan Original Townsite, Blk 209, Lts 6R-10R | NN Out Properties Ltd | J4 Engineering | Digital DL | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-05 | 2022-10-06 | Approved | 14 | Yes | N/A
Randolph Townhomes | CRB | SP22-57 | Bryan Original Townsite, Blk 209, Lts 6R-10R | NN Out Properties Ltd | J4 Engineering | Digital EE | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | N/A | 2022-10-05 | 2022-10-06 | Approved | 14 | Yes | N/A
Wholesale/Fabrication | BMG | SP22-35 | Carrabba Ind'l Park Ph 11, Blk 1 Lt 8 | GRT Interests LLC | J4 Engineering | Revised (Digital) Suppl DL | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-26 | 2022-09-26 | Approved | 4 | Yes | Rev #1; Approved by PSE
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | Revised (Digital) EE | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | 2022-10-03 | Approved | 11 | Yes | Rev #2
Drew's Car Wash | KCS | SP22-37 | Chatham Northview, Blk 14 Lt R-1 | Drew Congleton | Schultz Engineering | Revised (Digital) CP | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | N/A | 2022-10-03 | 2022-10-03 | Approved | 11 | Yes | Rev #2; JEB comments 9/26/22; KN no comments 10/3/22 (dms)
Regional Detention Pond | BMG | SQ22-06 | Windmill Park Subd | 2819 Nguyen LLC | J4 Engineering | SQ Permit | 2022-09-22 | 2022-09-26 | N/A | N/A | 2022-09-29 | N/A | UKN | N/A | 2022-09-26 | 2022-10-03 | 2022-09-29 | 2022-09-30 | Comments | 8 | Yes | N/A
Regional Detention Pond | BMG | SQ22-06 | Windmill Park Subd | 2820 Nguyen LLC | J4 Engineering | Digital DR | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2022-09-30 | Comments | 8 | Yes | N/A
Randolph Townhomes | CRB | SP22-57 | Bryan Original Townsite, Blk 209, Lts 6R-10R | NN Out Properties Ltd | J4 Engineering | Digital CP | 2022-09-22 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | 2022-10-05 | N/A | 2022-10-05 | 2022-10-06 | Comments | 14 | Yes | JEB comments 9/26/22; KN no comments 10/5/22 (dms)
Oak Creek Ranch | KCS | PP22-23 | Oak Creek Ranch | E & F Development Inc | Mitchell & Morgan | Revised (Digital) TIA | 2022-09-23 | 2022-09-26 | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | N/A | N/A | 2022-10-03 | 2022-10-03 | Comments | 10 | Yes | Rev #1
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Digital DR | 2022-09-28 | 2022-09-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-13 | 2022-10-13 | Comments | 15 | No | N/A
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Digital SL | 2022-09-28 | 2022-09-29 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | N/A | 2022-10-13 | 2022-10-13 | Comments | 15 | No | N/A
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Digital WL | 2022-09-28 | 2022-09-29 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | N/A | 2022-10-13 | 2022-10-13 | Comments | 15 | No | N/A
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Digital EE | 2022-09-28 | 2022-09-29 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | N/A | 2022-10-13 | 2022-10-13 | Comments | 15 | No | N/A
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | 1 CP | 2022-09-28 | 2022-09-29 | 2022-10-10 | N/A | N/A | N/A | N/A | 2022-10-10 | 2022-10-10 | N/A | 2022-10-13 | 2022-10-13 | Comments | 15 | No | Digital Copy Recv'd on 9/22/22; Waited on SDRC Submittal; JEB & KN comments 10/10/22 (dms)
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU - David Werley | Schultz Engineering | Digital SR | 2022-09-28 | 2022-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-05 | N/A | 2022-10-10 | 2022-10-10 | Comments | 12 | Yes | N/A
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU - David Werley | Schultz Engineering | Digital EE | 2022-09-28 | 2022-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-05 | N/A | 2022-10-10 | 2022-10-10 | Comments | 12 | Yes | N/A
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU - David Werley | Schultz Engineering | 1 CP | 2022-09-28 | 2022-09-28 | 2022-09-30 | N/A | N/A | N/A | N/A | N/A | 2022-10-05 | N/A | 2022-10-10 | 2022-10-10 | Comments | 12 | Yes | Digital Copy Recv'd Same Day; CP missing detail sheets-made request; JEB & KN comments 10/5/22 (dms)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) DR | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | Comments | 8 | Yes | Rev #2
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) EE | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-11 | Comments | 8 | Yes | Rev #2
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) CP | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | 2022-10-06 | 2022-10-10 | N/A | 2022-10-11 | 2022-10-11 | Comments | 8 | Yes | Rev #2; JEB comments 10/4/22; KN no comments 10/10/22 (dms)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | TxDOT Permit | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | 2022-10-14 | Emailed to TxDOT | 11 | Yes | N/A
Miramont Sec 18 | REG KCS | FP22-32 | Miramont Sec 18, Blk 1&2 13 Lts | Adam Development Properties LP | McClure & Browne | Digital DR | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | Comments | 15 | No | N/A
Miramont Sec 18 | REG KCS | FP22-32 | Miramont Sec 18, Blk 1&2 13 Lts | Adam Development Properties LP | McClure & Browne | Digital UR | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | N/A | 2022-10-18 | 2022-10-18 | Comments | 15 | No | N/A
Miramont Sec 18 | REG KCS | FP22-32 | Miramont Sec 18, Blk 1&2 13 Lts | Adam Development Properties LP | McClure & Browne | Digital EE | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | N/A | 2022-10-18 | 2022-10-18 | Approved | 15 | No | N/A
Miramont Sec 18 | REG KCS | FP22-32 | Miramont Sec 18, Blk 1&2 13 Lts | Adam Development Properties LP | McClure & Browne | 1 CP | 2022-10-03 | 2022-10-03 | 2022-10-17 | 2022-10-13 | N/A | N/A | N/A | 2022-10-14 | 2022-10-05 | N/A | 2022-10-18 | 2022-10-18 | Comments | 15 | No | JEB comments 10/4/22; KN comments 10/5/22 (dms)
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | Revised (Digital) DL | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-13 | 2022-10-13 | Comments | 10 | Yes | Rev #1
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | Revised (Digital) EE | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-13 | 2022-10-13 | Comments | 10 | Yes | Rev #1
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | Revised (Digital) CP | 2022-10-03 | 2022-10-03 | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | 2022-10-12 | N/A | 2022-10-13 | 2022-10-13 | Comments | 10 | Yes | Rev #1; JEB comments 10/4/22; KN comments 10/10/22 (dms)
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Digital DR | 2022-10-04 | 2022-10-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | 2022-10-18 | Comments | 14 | Yes | N/A
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Digital EE | 2022-10-04 | 2022-10-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-05 | N/A | 2022-10-18 | 2022-10-18 | Comments | 14 | Yes | N/A
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | 1 CP | 2022-10-04 | 2022-10-04 | 2022-10-13 | 2022-10-17 | N/A | N/A | N/A | 2022-10-14 | 2022-10-14 | N/A | 2022-10-18 | 2022-10-18 | Comments | 14 | Yes | Digital Copy Recv'd 10/3/22; Waited on Hard-Copy; JEB comments 10/5/22; KN comments 10/14/22 (dms)
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Digital EE | 2022-10-05 | 2022-10-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-10-25 | 2022-10-25 | Approved | 20 | No | N/A
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | 1 CP | 2022-10-05 | 2022-10-07 | 2022-10-13 | 2022-10-18 | N/A | N/A | N/A | 2022-10-17 | 2022-10-20 | N/A | 2022-10-25 | 2022-10-25 | Comments | 20 | No | Digital Copy Recv'd 10/5/22; Waited on Hard- Copy; JEB comments 10/18/22; KN comments 10/20/22 (dms)
Bank of Brenham | CRB BMG | SP22-51 | Penner Place, Blk 2, Lt 5R | Jim E Kruse | Kimley Horn & Assoc | Revised (Digital) CP | 2022-10-05 | 2022-10-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-10 | 2022-10-12 | Comments | 7 | Yes | Rev #1
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Digital SR | 2022-10-10 | 2022-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-10-24 | 2022-10-24 | Comments | 14 | Yes | N/A
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Digital WR | 2022-10-10 | 2022-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-10-24 | 2022-10-24 | Comments | 14 | Yes | N/A
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | 1 EE | 2022-10-10 | 2022-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-18 | N/A | 2022-10-24 | 2022-10-24 | Comments | 14 | Yes | N/A
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | 1 CP | 2022-10-10 | 2022-10-10 | 2022-10-24 | UKN | N/A | N/A | N/A | UKN | 2022-10-21 | N/A | 2022-10-24 | 2022-10-24 | Comments | 14 | Yes | Digital Copy Recv'd 10/7/22; Waited on Hard-Copy; JEB comments 10/18/22; KN comments 10/21/22 (dms)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Digital DR | 2022-10-11 | 2022-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-24 | 2022-10-24 | Comments | 13 | Yes | N/A
The Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Digital DR | 2022-10-11 | 2022-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | 2022-10-25 | Comments | 14 | Yes | Note this was added to the tracking sheet under a different engineer so review will be starting 11/1/2022. (KCS)
Margaret Wallace | REG BMG | RP21-21 | Margaret Wallace, Blk 5 Lts 1R & 2R | Syed Hyder | J4 Engineering | Revised (Digital) DL | 2022-10-13 | 2022-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-19 | Approved | 6 | Yes | Reviewed/approved by REG, stamped by BMG
Shops @ Hudson Oaks | REG ZFK | SP22-39 | Park Hudson Ph 4, Blk 4 Lt 4R | BTX Retail | Walker Partners | TxDOT Permit | 2022-10-17 | 2022-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-26 | Emailed to TxDOT | 9 | Yes | N/A
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Revised (Digital) EE | 2022-10-18 | 2022-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | 2022-10-25 | Approved | 7 | Yes | Rev #1
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2022-10-18 | 2022-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | Comments | 13 | Yes | Rev #2
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) CP | 2022-10-18 | 2022-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | N/A | 2022-10-31 | 2022-10-31 | Comments | 13 | Yes | Rev #1; JEB comments 10/24/22; KN comments 10/26/22 (dms)
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Revised (Digital) CP | 2022-10-18 | 2022-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | N/A | 2022-10-25 | 2022-10-25 | Comments | 7 | Yes | Rev #1; JEB comments 10/20/22; KN comments 10/21/22 (dms)
Randolph Townhomes | CRB ZFK | SP22-57 | Bryan Original Townsite, Blk 209, Lts 6R-10R | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2022-10-19 | 2022-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | N/A | 2022-10-31 | 2022-10-31 | Comments | 12 | Yes | Rev #1; JEB comments 10/24/22; KN comments 10/27/22 (dms)
BTU Admin Bldg | CRB | SP22-55 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Digital DR | 2022-10-20 | 2022-10-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-09 | Approved | 20 | No | N/A
BTU Admin Bldg | CRB | SP22-55 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Digital EE | 2022-10-20 | 2022-10-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-20 | N/A | 2022-11-07 | 2022-11-09 | Approved | 20 | No | N/A
Miramont Sec 18 | REG KCS | FP22-32 | Miramont Sec 18, Blk 1&2 13 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2022-10-20 | 2022-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | Approved | 11 | Yes | Rev #1
Miramont Sec 18 | REG KCS | FP22-32 | Miramont Sec 18, Blk 1&2 13 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2022-10-20 | 2022-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | N/A | 2022-10-31 | 2022-10-31 | Approved | 11 | Yes | Rev #1; JEB comments 10/25/22; KN comments 10/27/22 (dms)
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | Revised (Digital) CP | 2022-10-20 | 2022-10-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | N/A | 2022-10-31 | 2022-10-31 | Comments | 11 | Yes | Rev #2; JEB comments 10/24/22; KN comments 10/26/22 (dms)
BTU Admin Bldg | CRB | SP22-55 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | 1 CP | 2022-10-20 | 2022-10-20 | 2022-11-02 | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-21 | N/A | 2022-11-07 | 2022-11-09 | Comments | 20 | No | Digital Copy Recv'd 10/14/22; Waited on EE; JEB comments 10/20/22; KN comments 10/21/22 (dms)
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Digital EE | 2022-10-24 | 2022-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | N/A | 2022-10-31 | 2022-10-31 | Comments | 7 | Yes | N/A
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-10-24 | 2022-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | N/A | 2022-10-31 | 2022-10-31 | Comments | 7 | Yes | Rev #5; JEB comments 10/25/22; KN comments 10/27/22 (dms)
Villages @ Traditions Ph 5B | CRB BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Digital DL | 2022-10-26 | 2022-10-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | Comments | 19 | No | N/A
Pagosa Springs Ph 1-5 | KCS | MP22-07 | Pagosa Springs Ph 1-5 | S E Investments | McClure & Browne | Digital TIA | 2022-10-31 | 2022-10-31 | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | N/A | 2022-11-14 | 2022-11-14 | Comments | 14 | Yes | Design Eng initial sent it to SDRC on 10/26, however, it was not forwarded to our dept until 10/31 (dms)
Progress Park | CRB ZFK | SP22-61 | Progress Park Ph 2, Blk 2 Lt 5 | Crossway Farms Inc | Alvarado Group LLC | Digital CP | 2022-10-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-07 | Comments | 7 | Yes | Digital Copy Recv'd 10/31/22; Waiting on EE & Hard Copy; Email sent out on 10/31/22 to Miguel Alvarado; After SDRC comments, CP not Req (dms)
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) CP | 2022-11-01 | 2022-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | N/A | 2022-11-03 | 2022-11-03 | Comments | 2 | Yes | Rev #3; JEB & KN comments 11/2/22 (jls)
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) EE | 2022-11-01 | 2022-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-03 | 2022-11-03 | Comments | 2 | Yes | Rev #3
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) DR | 2022-11-01 | 2022-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-03 | 2022-11-03 | Comments | 2 | Yes | Rev #3
The Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) DR | 2022-11-01 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-11 | 2022-11-11 | Comments | 10 | Yes | Rev #1
Pop Shelf | KCS | SP22-63 | Bryan Town Center Blk 3, Lt R-B | Bryan Retail, LLC/PS Bryan | J4 Engineering | Digital DL | 2022-11-02 | 2022-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | Approved | 9 | Yes | N/A
Texas Communications | BMG | SP22-65 | Brazos County Ind'l Park Ph 3, Blk 7 Lt 10 | Broadband Towers/ The Sendero Group | J4 Engineering | Digital DR | 2022-11-02 | 2022-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-16 | Comments | 14 | Yes | N/A
The Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Digital EE | 2022-11-03 | 2022-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-03 | N/A | 2022-11-17 | 2022-11-17 | Comments | 14 | Yes | N/A
The Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | 1 CP | 2022-11-03 | 2022-11-03 | 2022-11-04 | 2022-11-16 | N/A | N/A | 2022-11-03 | 2022-11-15 | 2022-11-03 | N/A | 2022-11-17 | 2022-11-17 | Comments | 14 | Yes | Incomplete Digital Copy Recv'd 10/11/22; Waited on EE, Hard-Copy & Resubmittal of Digital (dms)
BISD Maintenance & Transportation Facility | KCS ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | 1 CP | 2022-11-03 | 2022-11-03 | 2022-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2022-11-08 | Comments | 5 | Yes | Digital Copy Recv'd 11/2/22; Waited on Hard Copy; EE not yet recv'd; JEB comments 11/8/22, KN comments 11/15/22 (jls); Request to delay review until Site Plan is further developed
Traditions Ph 20D | REG CRB | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-11-04 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | N/A | 2022-11-21 | 2022-11-21 | Comments | 17 | No | Rev #1; JEB comments 11/8/22, KN comments 11/15/22 (jls)
Traditions Ph 20D | REG CRB | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) DR | 2022-11-04 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-10 | 2022-11-10 | Comments | 6 | Yes | Rev #1
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-11-04 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | N/A | 2022-11-21 | 2022-11-21 | Comments | 17 | No | Rev #1; JEB comments 11/8/22, KN comments 11/15/22 (jls)
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) DR | 2022-11-04 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-10 | 2022-11-10 | Comments | 6 | Yes | Rev #1
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Revised (Digital) SR | 2022-11-07 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-07 | 2022-11-07 | Approved | 0 | Yes | Rev #1
BTU Admin Bldg-Offsite Sewer | CRB | FP22-27 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Revised (Digital) CP | 2022-11-07 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-07 | 2022-11-07 | Approved | 0 | Yes | Rev #2 - JEB no comments 11/7/22; KN no comments 11/11/22 (jls)
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) CP | 2022-11-07 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | N/A | 2022-11-09 | 2022-11-09 | Comments | 2 | Yes | Rev #4 - Partial Approval - Storm Sewer System ST-2 & ST-3 to be reviewed by DE (off-site detention to be evaluated); KN comments 11/11/22 (jls)
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) EE | 2022-11-07 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-09 | 2022-11-09 | Comments | 2 | Yes | Rev #4 - Estimate could change based on the off-site detention analysis
C C Creations | PSE | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) DR | 2022-11-07 | 2022-11-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-09 | 2022-11-09 | Comments | 2 | Yes | Rev #4 - Off site Detention to be evaluated
Saint Gobain Bldg Expansion | CRB ZFK | SP22-50 | Brazos County Ind'l Park Ph 3, Blk 3 Lt 1 | Saint Gobain | Kevin McCreary | 1 CP | 2022-11-10 | 2022-11-10 | 2022-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | Approved | 4 | Yes | Digital Copy Recv'd on Same Day (jls)
Traditions Ph 20F | CRB | FP22-35 | Traditions Ph 20F | TAP-Lard Development LLC | McClure & Browne | Digital EE | 2022-11-10 | 2022-11-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-30 | Comments | 16 | No | N/A
Traditions Ph 20F | CRB | FP22-35 | Traditions Ph 20F | TAP-Lard Development LLC | McClure & Browne | 1 CP | 2022-11-10 | 2022-11-10 | 2022-11-14 | 2022-11-30 | N/A | N/A | N/A | 2022-11-29 | 2022-11-28 | N/A | 2022-11-28 | 2022-11-30 | Comments | 16 | No | Digital Copy Recv'd on Same Day; JEB comments 11/15/22; KN comments 11/28/22 (jls)
3405 Tabor Rd | CRB KCS | RP22-28 | Woodville Acres Ph 3, Blk 1 Lts1 2-4&6R | Aria 2011 Family LLC | MP&D Strategies | Digital DR | 2022-11-10 | 2022-11-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | UKN | 2022-11-21 | 2022-11-21 | Comments | 11 | Yes | Submittal was overlooked by staff in getting this out for review (dms)
BISD Maintenance & Transportation Facility | KCS ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Digital DR | 2022-11-14 | 2022-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | Comments | 13 | Yes | N/A
Villages @ Traditions Ph 5B | CRB BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Revised (Digital) DL | 2022-11-17 | 2022-11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-21 | Approved | 4 | Yes | Rev #1
Villages @ Traditions Ph 5A | CRB BMG | SP22-60 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Revised (Digital) DL | 2022-11-17 | 2022-11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-21 | Approved | 4 | Yes | Rev #2
Traditions Ph 20D | REG CRB | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) DR | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | 2022-11-21 | Comments | 3 | Yes | Rev #2
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) DR | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | 2022-11-21 | Comments | 3 | Yes | Rev #2
Traditions Ph 20F | CRB | FP22-35 | Traditions Ph 20F | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) DR | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2022-11-30 | Comments | 8 | Yes | Rev #2
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Digital UL | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | N/A | 2022-12-13 | 2022-12-13 | Comments | 21 | No | JEB comments 11/18/22, KN comments 11/28/22 (jls), delayed return due to change in project engineer
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Digital EE | 2022-11-18 | 2022-11-18 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | N/A | 2022-12-13 | 2022-12-13 | Comments | 21 | No | JEB comments 11/18/22, KN comments 11/28/22 (jls), delayed return due to change in project engineer
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | 1 CP | 2022-11-18 | 2022-11-18 | 2022-12-06 | 2022-12-06 | N/A | N/A | N/A | 2022-12-05 | 2022-11-28 | N/A | 2022-12-13 | 2022-12-13 | Comments | 21 | No | Digital Copy Recv'd 11/16/22; Waited on Hard Copy; JEB comments 11/18/22, KN comments 11/28/22; delayed return due to change in project engineer (jls)
Traditions Ph 20D | REG CRB | SQ22-07 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | SQ Permit | 2022-11-21 | 2022-11-22 | N/A | N/A | 2022-11-22 | N/A | 2022-11-22 | 2022-11-28 | 2022-11-30 | 2022-12-02 | 2022-12-05 | 2022-12-06 | Approved | 11 | Yes | N/A
Traditions Ph 20E | REG CRB | SQ22-08 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | SQ Permit | 2022-11-21 | 2022-11-22 | N/A | N/A | 2022-11-22 | N/A | 2022-11-22 | 2022-11-28 | 2022-11-30 | 2022-12-02 | 2022-12-05 | 2022-12-06 | Approved | 11 | Yes | N/A
Traditions Ph 20F | CRB BMG | SQ22-09 | Traditions Ph 20F | TAP-Lard Development LLC | McClure & Browne | SQ Permit | 2022-11-21 | 2022-11-22 | N/A | N/A | 2022-11-22 | N/A | 2022-11-22 | 2022-11-28 | 2022-11-30 | 2022-12-02 | 2022-12-05 | 2022-12-06 | Approved | 11 | Yes | N/A
Aggieland RV Park & Storage | KCS | SP22-18 | 6 at 21 Crossing Subd, Blk 1 Lt 4 | Aggieland RV Park & Storage | McClure & Browne | Revised (Digital) CP | 2022-11-21 | 2022-11-21 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-12-02 | 2022-12-02 | Comments | 7 | Yes | Rev #3, JEB no comments 11/29/22 (jls)
Bonham Trace Ph 2 | BMG | SQ22-10 | Bonham Trace Ph 2, 42 Lts | Bonham Trace LLC | McClure & Browne | SQ Permit | 2022-11-21 | 2022-11-22 | N/A | N/A | 2022-11-22 | N/A | 2022-11-22 | 2022-11-28 | 2022-11-30 | 2022-12-02 | 2022-12-05 | 2022-12-05 | Approved | 10 | Yes | Delayed return due to being out-of-office with illness (BMG)
Traditions Ph 20D | REG CRB | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-11-22 | 2022-11-22 | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | N/A | 2022-12-05 | 2022-12-05 | Comments | 9 | Yes | Rev #2; KN comments 11/28/22, JEB comments 11/29/22 (jls)
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-11-22 | 2022-11-22 | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2022-11-29 | N/A | 2022-12-05 | 2022-12-05 | Comments | 9 | Yes | Rev #2; KN comments 11/28/22, JEB comments 11/29/22 (jls)
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) EE | 2022-11-22 | 2022-11-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2022-11-30 | Comments | 4 | Yes | Rev #1
Pagosa Springs Ph 1-5 | ZFK | MP22-07 | Pagosa Springs Ph 1-5 | S E Investments | McClure & Browne | Revised (Digital) TIA | 2022-11-22 | 2022-11-22 | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | N/A | N/A | 2022-12-01 | 2022-12-01 | Approved | 5 | Yes | Rev #1; B&B submitted a response to first submittal & it was reviewed & filed (KCS)
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-11-23 | 2022-11-23 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | N/A | 2022-12-19 | 2022-12-19 | Comments | 22 | No | Rev #5; KN no comments & JEB comments 11/28/22 (jls)
Whataburger | KCS | SP22-68 | Smythe Add'n Ph 1, Blk C Lt 4R | Whataburger | Greenberg Farrow | 1 CP | 2022-11-30 | 2022-11-30 | 2022-12-01 | 2022-12-01 | N/A | N/A | N/A | 2022-12-12 | 2022-12-05 | N/A | 2022-12-13 | 2022-12-13 | Comments | 13 | Yes | Digital Copy Recv'd 11/22/22; Waited on Hard Copy & EE; JEB & KN comments 12/5/22 (jls); Not moving forward at this time due to Developer's legal issues (dms)
Whataburger | KCS | SP22-68 | Smythe Add'n Ph 1, Blk C Lt 4R | Whataburger | Greenberg Farrow | Digital EE | 2022-11-30 | 2022-11-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-05 | N/A | 2022-12-13 | 2022-12-13 | Comments | 13 | Yes | JEB & KN comments 12/5/22 (jls); Not moving forward at this time due to Developer's legal issues (dms)
Whataburger | KCS | SP22-68 | Smythe Add'n Ph 1, Blk C Lt 4R | Whataburger | Greenberg Farrow | Digital DR | 2022-11-30 | 2022-11-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-05 | N/A | 2022-12-13 | 2022-12-13 | Comments | 13 | Yes | JEB & KN Comments 12/5/22; Not moving forward at this time due to Developer's legal issues (dms)
Rudder Pointe Ph 7 | KCS | SQ22-06 | Rudder Pointe Ph 7, Blk 1-6 52 Lts | BORD Development | McClure & Browne | SQ Permit | 2022-11-30 | 2022-11-30 | N/A | N/A | 2022-12-05 | N/A | 2022-12-01 | 2022-12-05 | 2022-12-01 | 2022-12-06 | 2022-12-06 | 2022-12-06 | Approved | 6 | Yes | Digital Copy Recv'd 11/10/22; Waited on FP Submittal to SDRC (dms)
BISD Maintenance & Transportation Facility | KCS ZFK | SQ22-11 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | SQ Permit | 2022-12-01 | 2022-12-01 | N/A | N/A | 2022-12-01 | N/A | 2022-12-06 | UKN | 2022-12-01 | 2022-12-06 | 2022-12-06 | 2022-12-06 | Comments | 5 | Yes | ECP & SWPPP Recv'd 11/30/22; Waited on G.A. (dms), Received TxDOT Drainage Report Review 12/27/2022
Watson Ln Townhomes | KCS | SP21-42 | Hanzen-Zak, Lts 1R-1 to 1R-5 | TM5 Properties | McClure & Browne | 1 CP | 2022-12-02 | 2022-12-02 | 2022-12-02 | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A | 2022-12-20 | 2022-12-20 | Comments | 18 | No | Digital Copy Recv'd 11/28/22; Waited on Hard Copy; JEB comments 12/5/22; KN comments 12/6/22 (jls)
Watson Ln Townhomes | KCS | SP21-42 | Hanzen-Zak, Lts 1R-1 to 1R-5 | TM5 Properties | McClure & Browne | Digital EE | 2022-12-02 | 2022-12-02 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-06 | N/A | 2022-12-20 | 2022-12-20 | Comments | 18 | No | JEB comments 12/5/22; KN comments 12/6/22 (jls)
BTU Admin Bldg | CRB WPK | SP22-55 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Revised (Digital) CP | 2022-12-06 | 2023-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-13 | N/A | 2023-01-24 | 2023-01-24 | Comments | 14 | Yes | Rev #1; Plans came in on 12/6/22, however they didn't get routed in a timely manner (dms) Due on 1/20/23, returned 1/24/23
Traditions Ph 20D | CRB BMG | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-12-07 | 2022-12-07 | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-13 | N/A | 2022-12-16 | 2022-12-16 | Comments | 9 | Yes | Rev #3; JEB no comments 12/12/22; KN no comments 12/13/22 (jls); Approved pending TxDOT permits (bmg)
Traditions Ph 20E | REG CRB | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-12-07 | 2022-12-07 | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-13 | N/A | 2022-12-16 | 2022-12-16 | Comments | 9 | Yes | Rev #3; JEB no comments 12/12/22; KN no comments 12/13/22 (jls); Approved pending TxDOT permits (bmg)
Traditions Ph 20F | CRB BMG | FP22-35 | Traditions Ph 20F, Blk 8 Lts 1-15 | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-12-07 | 2022-12-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | N/A | 2022-12-16 | 2022-12-16 | Comments | 9 | Yes | Rev #1; JEB comments 12/7/22; KN no comments 12/16/22 (jls) Approved pending TxDOT permits (bmg)
Traditions Ph 20F | CRB BMG | FP22-35 | Traditions Ph 20F, Blk 8 Lts 1-15 | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) EE | 2022-12-07 | 2022-12-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | 2022-12-16 | Comments | 9 | Yes | Rev #1; Approved pending TxDOT permits (bmg)
Texas Communications | BMG | SP22-65 | Brazos County Ind'l Park Ph 3, Blk 7 Lt 10 | Broadband Towers/ The Sendero Group | J4 Engineering | Digital WL | 2022-12-07 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | Comments | 5 | Yes | N/A
Texas Communications | BMG | SP22-65 | Brazos County Ind'l Park Ph 3, Blk 7 Lt 10 | Broadband Towers/ The Sendero Group | J4 Engineering | Digital SL | 2022-12-07 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | Comments | 5 | Yes | N/A
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A Subd., Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | 1 CP | 2022-12-08 | 2022-12-09 | 2023-01-03 | UKN | N/A | N/A | N/A | 2022-12-20 | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 28 | No | Digital Copy Recv'd on Same Day; JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A Subd., Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Digital EE | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 28 | No | JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A Subd., Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Digital DR | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-10 | Comments | 28 | No | N/A
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A Subd., Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Digital SL | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 28 | No | JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A Subd., Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Digital WL | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 28 | No | JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B Subd., Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | 1 CP | 2022-12-08 | 2022-12-09 | 2023-01-03 | UKN | N/A | N/A | N/A | 2022-12-20 | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 27 | No | Digital Copy Recv'd on Same Day; JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B Subd., Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Digital EE | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 27 | No | JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B Subd., Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Digital DR | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-10 | Comments | 27 | No | N/A
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B Subd., Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Digital SL | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 27 | No | JEB comments 12/28/22; KN comments 1/5/23 (jls)
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B Subd., Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Digital WL | 2022-12-08 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | N/A | 2023-01-10 | 2023-01-10 | Comments | 27 | No | JEB comments 12/28/22; KN comments 1/5/23 (jls)
Physicians Center | REG BMG | RP22-07 | Park Hudson Ph 1, Blk 1 Lt 2-R1 & 3R | BV Physicians Org | Strong Surveying | Digital DR | 2022-12-08 | 2022-12-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-15 | 2022-12-15 | Comments | 7 | Yes | N/A
University TXB C-Store/Gas Station | BMG | SP22-30 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | Cool Breeze Consultants | Revised (Digital) DR | 2022-12-08 | 2022-12-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2022-12-08 | Comments | 0 | Yes | Rev #3
Rudder Pointe Ph 7 | KCS | SQ22-06 | Rudder Pointe Ph 7, Blk 1-6 52 Lts | BORD Development | McClure & Browne | Revised SQ Permit | 2022-12-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2022-12-08 | Approved | 0 | Yes | Rev #1
University TXB C-Store/Gas Station | BMG | SP22-30 | Hudson at University Ph 2, Blk 1 Lt 8R | Alina Hospitality LP | Cool Breeze Consultants | Digital UL | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | Comments | 0 | Yes | Rev #2; No revised utility reports needed/provided (bmg)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 | 5 J land & Development LLC | Schultz Engineering | 1 DR | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | Digital Copy Recv'd on Same Day
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 | 5 J land & Development LLC | Schultz Engineering | Digital SL | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Approved | 15 | No | JEB comments 12/27/22; KN comments 12/29/22 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 | 5 J land & Development LLC | Schultz Engineering | Digital WR | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | JEB comments 12/27/22; KN comments 12/29/22 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 | 5 J land & Development LLC | Schultz Engineering | 1 EE | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | Digital Copy Recv'd on Same Day; JEB comments 12/27/22; KN comments 12/29/22 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 | 5 J land & Development LLC | Schultz Engineering | 1 CP | 2022-12-09 | 2022-12-09 | 2022-12-15 | UKN | N/A | N/A | N/A | 2022-12-29 | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | Digital Copy Recv'd on Same Day; JEB comments 12/27/22; KN comments 12/29/22 (jls)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) WR | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-19 | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | Rev #1; JEB comments 12/12/22; KN comments 12/19/22 (jls); Awaiting clarification from JEB & SJV (bmg on 21-Dec)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) SR | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-19 | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | Rev #1; JEB comments 12/12/22; KN comments 12/19/22 (jls); Awaiting clarification from JEB & SJV (bmg on 21-Dec)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) EE | 2022-12-09 | 2022-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2022-12-29 | Comments | 15 | No | Rev #1; Awaiting clarification from JEB & SJV (bmg on 21-Dec)
Oakmont Ph 4A | KCS | SQ22-41 | Oakmont Ph 4B Subd., Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | SQ Permit | 2022-12-12 | 2022-12-12 | N/A | N/A | 2022-12-13 | N/A | 2022-12-14 | 2022-12-14 | 2022-12-12 | 2022-12-12 | 2022-12-20 | 2022-12-20 | Comments | 8 | Yes | N/A
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) DR | 2022-12-12 | 2022-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2022-12-29 | Comments | 12 | Yes | Rev #1; Awaiting clarification from JEB & SJV (bmg on 21-Dec)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) CP | 2022-12-12 | 2022-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Comments | 12 | Yes | Rev #1; JEB comments 12/12/22 (jls); Awaiting clarification from JEB & SJV (bmg on 21-Dec); KN no comments 12/29/22 (jls)
BISD Maintenance & Transportation Facility | KCS ZFK | SQ22-11 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised SQ Permit | 2022-12-13 | 2022-12-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-20 | 2022-12-20 | Approved | 7 | Yes | Rev #1
Oakmont Ph 4B | KCS | SQ22-12 | Oakmont Ph 4A Subd., Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | SQ Permit | 2022-12-13 | 2022-12-13 | N/A | N/A | 2022-12-13 | N/A | 2022-12-13 | 2022-12-14 | 2022-12-16 | 2022-12-16 | 2022-12-20 | 2022-12-20 | Approved | 7 | Yes | Initially Recv'd on 12/9/22; Waited on ECP (dms)
Villages @ Traditions Ph 5B | BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Digital WR | 2022-12-14 | 2022-12-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Approved | 8 | Yes | JEB comments 12/19/22 (jls)
Villages @ Traditions Ph 5B | BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Digital SR | 2022-12-14 | 2022-12-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Approved | 8 | Yes | JEB comments 12/19/22 (jls)
Villages @ Traditions Ph 5B | BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | 1 EE | 2022-12-14 | 2022-12-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Approved | 8 | Yes | Digital Copy Recv'd on Same Day (dms); JEB comments 12/19/22 (jls)
Villages @ Traditions Ph 5B | BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | 1 CP | 2022-12-14 | 2022-12-15 | 2022-12-19 | 2022-12-15 | N/A | N/A | N/A | 2022-12-28 | 2022-12-29 | N/A | 2022-12-29 | 2022-12-29 | Comments | 8 | Yes | Digital Copy Recv'd on Same Day (jls); JEB comments 12/19/22 (jls)
Carrabba Ind'l Park Ph 11 | ZFK | SP22-69 | Carrabba Ind'l Park Ph 11, Blk 1 Lt 3 | GRT Interests LLC | J4 Engineering | Digital DL | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | Approved | 14 | Yes | N/A
First Baptist Church | BMG | SP22-70 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley Horn & Assoc | DL | 2022-12-14 | 2022-12-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-19 | 2022-12-19 | Comments | 5 | Yes | N/A
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2022-12-15 | 2022-12-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-30 | 2022-12-30 | Comments | 10 | Yes | Rev #3
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised (Digital) CP | 2022-12-19 | 2022-12-19 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | N/A | 2023-01-11 | 2023-01-11 | Comments | 17 | No | Rev #2; JEB & KN comments 1/3/23 (jls)
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised (Digital) EE | 2022-12-19 | 2022-12-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-01-11 | Comments | 17 | No | Rev #2
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised (Digital) DR | 2022-12-19 | 2022-12-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-01-11 | Comments | 17 | No | Rev #2
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) CP | 2022-12-20 | 2022-12-21 | 2023-01-06 | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | N/A | 2023-01-03 | 2023-01-03 | Comments | 8 | Yes | Rev #1; JEB & KN comments 1/3/23 (jls)
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) EE | 2022-12-20 | 2022-12-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | Comments | 8 | Yes | Rev #1
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) DR | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | Comments | 8 | Yes | Rev #1
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Digital WR | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | N/A | 2023-01-03 | 2023-01-03 | Approved | 8 | Yes | JEB & KN comments 1/3/23 (jls)
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Digital SR | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | N/A | 2023-01-03 | 2023-01-03 | Approved | 8 | Yes | JEB & KN comments 1/3/23 (jls)
Traditions Ph 20D | CRB BMG | FP22-25 | Traditions Ph 20D, Blk 1 6&7 20 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) EE | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2022-12-29 | Comments | 1 | Yes | Rev #1; Pending drainage report and TxDOT UIR permit
Traditions Ph 20E | CRB BMG | FP22-26 | Traditions Ph 20E, Blk 2-4 13 Lts | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) EE | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2022-12-29 | Comments | 4 | Yes | Rev #2; Pending drainage report and TxDOT UIR permit
Traditions Ph 20F | CRB BMG | FP22-35 | Traditions Ph 20F, Blk 8 Lts 1-15 | TAP-Lard Development LLC | McClure & Browne | Digital UR | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | N/A | 2022-12-29 | 2022-12-28 | Comments | 3 | Yes | Rev #2; JEB no comments 1/3/23 (jls)
Traditions Ph 20F | CRB BMG | FP22-35 | Traditions Ph 20F, Blk 8 Lts 1-15 | TAP-Lard Development LLC | McClure & Browne | Revised (Digital) CP | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-28 | N/A | 2022-12-29 | 2022-12-29 | Comments | 4 | Yes | Rev #2; JEB no comments 1/3/23 (jls)
Physicians Center | REG BMG | RP22-07 | Park Hudson Ph 1, Blk 1 Lt 2-R1 & 3R | BV Physicians Org | Strong Surveying | Revised (Digital) DR | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-21 | 2022-12-21 | Approved | 1 | Yes | Rev #1
Woodson Development | KCS | SP21-08 | College Oaks, Blk 1 Lts 13-18 | CzechMex Properties LLC | M3 Engineering | Revised (Digital) CP | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-27 | N/A | 2022-12-28 | 2022-12-28 | Approved | 3 | Yes | Rev #7; JEB comments 12/27/22 (jls)
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) CP | 2022-12-20 | 2022-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | N/A | 2022-12-30 | 2022-12-30 | Comments | 5 | Yes | Rev #2; DE sent incorrect version of CP on 12/15/22; DE Mistake corrected 12/20/22 & docs distributed same day; JEB comments 12/27/22; KN no comments 12/29/22 (jls)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) DR | 2022-12-22 | 2022-12-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-10 | Approved | 9 | Yes | N/A
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Digital EE | 2022-12-22 | 2022-12-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-10 | Approved | 13 | Yes | N/A
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2022-12-22 | 2022-12-28 | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | 2022-12-29 | N/A | 2023-01-04 | 2023-01-10 | Approved | 14 | Yes | Rev #2: a 3rd revision was sent in during review of 2nd revision, JEB stated that 2nd and 3rd revisions were the same, comments received from JEB and KN on 12/29/25
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Revised (Digital) UL | 2022-12-27 | 2022-12-27 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | N/A | 2023-01-04 | 2023-01-04 | Approved | 3 | Yes | N/A
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Digital DL | 2022-12-27 | 2022-12-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | Approved | 3 | Yes | N/A
10.5361

## 2023
Project Name | Project Eng | Case # | Subdivision | Applicant | Engineer | Infrastructure Submitted | Date Submittal Received | Date Distr. | Inspector Comments Received | BTU Comments Received | Dev Srvcs Comments Received | Fire Comments Recv'd | Traffic Comments Recv'd | Water Comments Received | FP Coord Comments Received | Date Comments Prepared | Comments Sent to Applicant / Engineer | Status | Gross Review Days | Met Deadline? | Add'l Comments
First Baptist Church | BMG | SP22-70 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley-Horn & Assoc | Revised (Digital) DL | 2023-01-04 | 2023-01-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | Approved | 0 | Yes | Rev #1
Villages @ Traditions Ph 5B | BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Revised (Digital) CP | 2023-01-05 | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-10 | Approved | 5 | Yes | Rev #1
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) WR | 2023-01-06 | 2023-01-06 | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | N/A | 2023-01-12 | 2023-01-12 | Comments | 6 | Yes | Rev #2; JEB no comments 1/6/23 (jls)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) SR | 2023-01-06 | 2023-01-06 | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | N/A | 2023-01-12 | 2023-01-12 | Approved | 6 | Yes | Rev #2; JEB no comments 1/6/23; KN no comments 1/11/23 (jls)
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) EE | 2023-01-06 | 2023-01-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | Approved | 6 | Yes | Rev #2
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) DR | 2023-01-06 | 2023-01-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | Comments | 6 | Yes | Rev #2
Woodville Estates | BMG | FP22-30 | Woodville Estates, Blk 1&2 30 Lts | Blue Burro Management LLC | JBS Engineering | Revised (Digital) CP | 2023-01-06 | 2023-01-06 | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | N/A | 2023-01-12 | 2023-01-12 | Approved | 6 | Yes | Rev #2; JEB no comments 1/6/23; KN no comments 1/11/23 (jls)
BTU Admin Bldg | WPK | SQ23-01 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | SQ Permit | 2023-01-06 | 2023-01-10 | N/A | N/A | 2023-01-11 | 2023-01-11 | 2023-01-18 | 2023-01-10 | 2023-01-18 | 2023-01-12 | 2023-01-12 | Approved | 6 | Yes | Clearing of site authorized under the SQ permit.
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) DR | 2023-01-09 | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-01-11 | Comments | 2 | Yes | Rev #2
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) EE | 2023-01-09 | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-01-11 | Approved | 2 | Yes | Rev #2
Sage Meadow Ph 2 | BMG | FP22-19 | Sage Meadow Ph 2, Blk 3-6 41 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) CP | 2023-01-09 | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | N/A | 2023-01-11 | 2023-01-11 | Comments | 2 | Yes | Rev #2
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2023-01-09 | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | Comments | 3 | Yes | Rev #4
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) CP | 2023-01-09 | 2023-01-09 | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | N/A | 2023-01-12 | 2023-01-12 | Comments | 3 | Yes | Rev #3; JEB comments 1/10/23; KN no comments 1/12/23 (KCS)
Oakmont Ph 2C | KCS | SQ23-02 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | SQ Permit | 2023-01-10 | 2023-01-10 | N/A | N/A | 2023-01-11 | 2023-01-10 | 2023-01-13 | 2023-01-10 | 2023-01-18 | 2023-01-19 | 2023-01-19 | Comments | 8 | Yes | N/A
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) DR | 2023-01-10 | 2023-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | 2023-01-25 | Comments | 14 | Yes | Rev #2
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Digital UR | 2023-01-10 | 2023-01-10 | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | N/A | 2023-01-25 | 2023-01-25 | Comments | 14 | Yes | JEB comments 1/16/23; KN comments 1/18/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) EE | 2023-01-10 | 2023-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | Comments | 14 | Yes | Rev #1
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) CP | 2023-01-10 | 2023-01-10 | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-01-18 | N/A | 2023-01-25 | 2023-01-25 | Comments | 14 | Yes | Rev #1; JEB comments 1/16/23; KN comments 1/18/23 (jls)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Digital UR | 2023-01-11 | 2023-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-15 | 2023-01-18 | Approved | 6 | Yes | Rev #3; JEB comments 1/11/23; KN comments 1/18/23 (jls)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) DR | 2023-01-11 | 2023-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | Comments | 6 | Yes | Rev #3
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) EE | 2023-01-11 | 2023-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-18 | Comments | 6 | Yes | Rev #3
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-01-11 | 2023-01-11 | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | N/A | 2023-01-18 | 2023-01-18 | Comments | 6 | Yes | Rev #3; JEB comments 1/11/23; KN comments 1/18/23 (jls)
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Revised (Digital) CP | 2023-01-13 | 2023-01-13 | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | N/A | 2023-01-24 | 2023-01-24 | Comments | 10 | Yes | Rev #2; JEB comments 1/16/23; KN no comments 1/24/233 (jls)
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Revised (Digital) CP | 2023-01-13 | 2023-01-13 | N/A | N/A | N/A | N/A | N/A | 2023-01-16 | N/A | 2023-01-23 | 2023-01-23 | Comments | 9 | Yes | Rev #3; JEB comments 1/16/23
Oakmont Ph 2C | KCS | FP23-05 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | 1 CP | 2023-01-17 | 2023-01-17 | 2023-01-27 | 2023-01-20 | N/A | N/A | 2023-01-27 | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | Comments | 14 | Yes | Digital Copy Recv'd on Same Day; JEB comments 1/20/23; KN comments 1/27/23 (jls)
Oakmont Ph 2C | KCS | FP23-05 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | Digital EE | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | Approved | 14 | Yes | JEB comments 1/20/23; KN comments 1/27/23 (jls)
Oakmont Ph 2C | KCS | FP23-05 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | Digital DR | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Approved | 14 | Yes | N/A
Oakmont Ph 2C | KCS | FP23-05 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | Digital WL | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | Approved | 14 | Yes | JEB comments 1/20/23; KN comments 1/27/23 (jls)
Oakmont Ph 2C | KCS | FP23-05 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | Digital SL | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | N/A | 2023-01-31 | 2023-01-31 | Approved | 14 | Yes | JEB comments 1/20/23; KN comments 1/27/23 (jls)
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) CP | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | N/A | 2023-01-23 | 2023-01-23 | Comments | 6 | Yes | Rev #4; only sent to JEB for comments 1/17/23
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Digital EE | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | Comments | 6 | Yes | N/A
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2023-01-17 | 2023-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | Comments | 6 | Yes | Rev #5
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) CP | 2023-01-23 | 2023-01-23 | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-27 | N/A | 2023-02-10 | 2023-02-10 | Comments | 18 | No | Rev #3; JEB no comments 1/23/23; KN comments 1/27/23 (jls)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) WR | 2023-01-23 | 2023-01-23 | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | N/A | 2023-02-10 | 2023-02-10 | Comments | 18 | No | Rev #2; JEB no comments 1/23/23; KN comments 1/27/23 (jls)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) DR | 2023-01-23 | 2023-01-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | Comments | 18 | No | Rev #3
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) EE | 2023-01-23 | 2023-01-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | Comments | 18 | No | Rev #3
Dutch Brothers | CRB ZFK | SP22-62 | Villa Maria Wal-Mart Add'n, Blk B Pt of Lt 11 | David Foor & Sam Moore | Tectonics Design Group | Revised (Digital) CP | 2023-01-23 | 2023-01-23 | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | N/A | 2023-01-27 | 2023-01-27 | Approved | 4 | Yes | Rev #3; JEB no comments 1/23/23; KN no comments 1/24/23 (jls)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-01-25 | 2023-01-25 | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | N/A | 2023-02-01 | 2023-02-02 | Comments | 8 | Yes | Rev #4; JEB no comments 2/8/23; KN Comments 2/13/23 (jls)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) EE | 2023-01-25 | 2023-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-02 | Comments | 8 | Yes | Rev #4
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) UR | 2023-01-25 | 2023-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-02 | Comments | 8 | Yes | Rev #4
Garoppolo | BMG | SP23-06 | Bryan Original Townsite, Blk 135 Lts 3A-3C&4A-4C | NN Out Properties Ltd | J4 Engineering | 1 CP | 2023-01-25 | 2023-01-25 | 2023-01-26 | 2023-01-25 | N/A | N/A | 2023-01-30 | 2023-02-03 | N/A | 2023-02-09 | 2023-02-09 | Comments | 15 | No | Digital Copy Recv'd on Same Day; JEB no comments 1/25/23; KN comments 2/3/23 (jls)
Garoppolo | BMG | SP23-06 | Bryan Original Townsite, Blk 135 Lts 3A-3C&4A-4C | NN Out Properties Ltd | J4 Engineering | 1 EE | 2023-01-25 | 2023-01-25 | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | N/A | 2023-02-09 | 2023-02-09 | Comments | 15 | No | JEB no comments 1/25/23; KN comments 2/3/23 (jls)
Garoppolo | BMG | SP23-06 | Bryan Original Townsite, Blk 135 Lts 3A-3C&4A-4C | NN Out Properties Ltd | J4 Engineering | Digital DL | 2023-01-25 | 2023-01-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Comments | 15 | No | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Digital TIA | 2023-01-26 | 2023-01-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Comments | 8 | Yes | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Digital DL | 2023-01-26 | 2023-01-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Comments | 8 | Yes | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | 1 EE | 2023-01-26 | 2023-01-26 | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | N/A | 2023-02-03 | 2023-02-03 | Comments | 8 | Yes | KN comments 2/3/23; JEB comments 2/8/23 (jls)
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | 1 CP | 2023-01-26 | 2023-01-26 | 2023-01-27 | 2023-02-08 | N/A | N/A | N/A | 2023-02-08 | N/A | 2023-02-03 | 2023-02-03 | Comments | 8 | Yes | Digital Copy Recv'd 1/3/23; Waited on Hard Copy; KN comments 2/3/23; JEB comments 2/8/23 (jls); JEB comments sent 2/13
BTU Admin Bldg | WPK | SP22-55 | BTU Subd., Blk 1 Lts 1&2 | BTU-David Werley | Schultz Engineering | Revised (Digital) CP | 2023-01-26 | 2023-01-26 | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-01-27 | N/A | 2023-02-02 | 2023-02-02 | Approved | 7 | Yes | Rev #2; JEB no comments 1/27/23 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 6 Lts | 5 J land & Development LLC | Schultz Engineering | Revised (Digital) CP | 2023-01-27 | 2023-01-27 | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-03 | N/A | 2023-02-09 | 2023-02-09 | Comments | 13 | Yes | Rev #1; JEB comments 2/2/23; KN comments 2/3/23 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 6 Lts | 5 J land & Development LLC | Schultz Engineering | Revised (Digital) EE | 2023-01-27 | 2023-01-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Comments | 13 | Yes | Rev #1;
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 6 Lts | 5 J land & Development LLC | Schultz Engineering | Revised (Digital) WR | 2023-01-27 | 2023-01-27 | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | N/A | 2023-02-09 | 2023-02-09 | Approved | 13 | Yes | Rev #1; JEB comments 2/2/23; KN comments 2/3/23 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 6 Lts | 5 J land & Development LLC | Schultz Engineering | Revised (Digital) DR | 2023-01-27 | 2023-01-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Approved | 13 | Yes | Rev #1
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) DR | 2023-02-02 | 2023-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | Comments | 11 | Yes | Rev #5
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-02-02 | 2023-02-02 | UKN | N/A | N/A | N/A | N/A | 2023-02-12 | N/A | 2023-02-03 | 2023-02-03 | Comments | 1 | Yes | Rev #5; JEB no comments 2/8/23; KN Comments 2/12/23 (jls)
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2023-02-02 | 2023-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-02-20 | Comments | 18 | No | Rev #1
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2023-02-02 | 2023-02-02 | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | N/A | 2023-02-20 | 2023-02-20 | Comments | 18 | No | Rev #1; JEB comments 2/2/23 (jls)
Rudder Pointe Ph 5 | KCS | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised (Digital) CP | 2023-02-02 | 2023-02-02 | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | N/A | 2023-02-09 | 2023-02-09 | Comments | 7 | Yes | Rev #2; JEB no comments 2/2/23 (jls); KN no comments 2/9/23 (KCS)
Oakmont Ph 2C | KCS | FP23-05 | Oakmont Ph 2C, Blk 1-3 32 Lts | Adam Development Properties LP | McClure & Browne | 1 CP | 2023-02-03 | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | N/A | 2023-02-10 | 2023-02-10 | Approved | 7 | Yes | Rev #1; JEB no comments 2/3/23; KN no comments 2/6/23 (jls)
Mods Apt Complex | KCS | SQ23-03 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | SQ Permit | 2023-02-06 | 2023-02-06 | N/A | N/A | 2023-02-06 | 2023-02-10 | N/A | 2023-02-06 | N/A | 2023-02-10 | 2023-02-10 | Comments | 4 | Yes | Incomplete Digital Copies Recv'd 2/3/23; Waited on Site Plan (dms)
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | 1 CP | 2023-02-07 | 2023-02-08 | UKN | N/A | N/A | N/A | 2023-02-20 | 2023-02-17 | N/A | 2023-02-23 | 2023-02-23 | Comments | 16 | No | Digital copy recv'd same day; Waited on EE; JEB & KN comments 2/17/23 (jls)
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Digital EE | 2023-02-07 | 2023-02-08 | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-23 | 2023-02-23 | Comments | 16 | No | JEB & KN comments 2/17/23 (jls)
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Digital UL | 2023-02-07 | 2023-02-08 | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-23 | 2023-02-23 | Comments | 16 | No | JEB & KN comments 2/17/23 (jls)
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Digital DR | 2023-02-07 | 2023-02-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Comments | 16 | No | N/A
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | 1 CP | 2023-02-10 | 2023-02-10 | 2023-02-14 | UKN | N/A | N/A | 2023-02-22 | 2023-02-20 | N/A | 2023-02-27 | 2023-02-27 | Comments | 17 | No | Digital copy recv'd on 2/8/23; Waited on hard copy (dms); KN no comments; JEB comments 2/20/23 (jls)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Digital EE | 2023-02-10 | 2023-02-10 | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-02-27 | 2023-02-27 | Comments | 17 | No | JEB comments 2/20/23 (jls)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) CP | 2023-02-14 | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-02-20 | Approved | 6 | Yes | Rev #4; JEB no comments 2/15/23 (jls)
Bonham Trace Ph 2 | BMG | FP22-23 | Bonham Trace Ph 2, 42 Lts | Bonham LLC | McClure & Browne | Revised (Digital) EE | 2023-02-14 | 2023-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-02-20 | Approved | 6 | Yes | Rev #4
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-02-16 | 2023-02-16 | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-17 | 2023-02-20 | Comments | 4 | Yes | Rev #6; KN no comments 2/17/23
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) EE | 2023-02-22 | 2023-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Approved | 7 | Yes | Rev #5
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-02-22 | 2023-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Re | 2023-03-01 | Approved | 7 | Yes | Rev #7
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-02-28 | 2023-02-28 | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-03-08 | 2023-03-08 | Comments | 8 | Yes | Rev #1; JEB comments 3/9/23 (jls)
Oak Creek Ranch | KCS | PP22-23 | Oak Creek Ranch, Blk 1 Lt 1 | E & F Development Inc | Mitchell & Morgan | Revised (Digital) TIA | 2023-03-01 | 2023-03-01 | N/A | N/A | N/A | N/A | 2023-03-06 | N/A | N/A | 2023-03-06 | 2023-03-07 | Approved | 6 | Yes | Rev #3; ZFK no comments 3/6/23 (jls); comments sent with SDRC notification (KCS)
Quicker Sticker | SJS | SP23-17 | Briarcrest-Hughes Ph 2, Blk 1 Lts 2R&3R | A Gotner & M Tomchesson | RME Engineering | Digital DL | 2023-03-01 | 2023-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Approved | 14 | Yes | N/A
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) CP | 2023-03-01 | 2023-03-01 | 2023-03-09 | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-03-09 | 2023-03-09 | Comments | 8 | Yes | Rev#2; JEB & KN comments 3/8/23; AM no comments 3/9/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Digital SL | 2023-03-01 | 2023-03-01 | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-13 | 2023-03-13 | Comments | 12 | Yes | N/A
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Digital WL | 2023-03-01 | 2023-03-01 | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-13 | 2023-03-13 | Comments | 12 | Yes | N/A
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | TxDOT Permit | 2023-03-02 | 2023-03-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-21 | Emailed to TxDOT | 19 | No | N/A
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2023-03-02 | 2023-03-02 | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-03-08 | 2023-03-08 | Comments | 6 | Yes | Rev #2; JEB no comments 3/6/23 (jls); KN comment 3/8/23 (KCS)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Digital DR | 2023-03-03 | 2023-03-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 21 | No | Waited on requested meeting with developer to discuss prior to sending to engineers (KCS)
Garoppolo | BMG | SP23-06 | Bryan Original Townsite, Blk 135 Lts 3A-3C&4A-4C | NN Out Properties Ltd | J4 Engineering | Revised (Digital) CP | 2023-03-07 | 2023-03-07 | 2023-03-09 | N/A | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-03-13 | 2023-03-13 | Approved | 6 | Yes | Rev #1; JEB no comments 3/7/23; KN comments 3/14/23; AM no comments 3/9/23 (jls)
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | 1 CP | 2023-03-08 | 2023-03-08 | 2023-03-15 | 2023-03-14 | N/A | N/A | 2023-03-20 | 2023-03-14 | N/A | 2023-03-21 | 2023-03-21 | Comments | 13 | Yes | Digital copy recv'd on 2/8/23; Waited on Hard Copy and EE; JEB comments 3/9/23; KN comments 3/14/23; KF no comments 3/15/23, ZFK comments 3/20/23 (jls)
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Digital DL | 2023-03-08 | 2023-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Comments | 13 | Yes | N/A
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Digital EE | 2023-03-08 | 2023-03-08 | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-03-21 | 2023-03-21 | Comments | 13 | Yes | JEB comments 3/9/23; KN comments 3/14/23 (jls)
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2023-03-08 | 2023-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Denied | 16 | No | Rev #6
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) CP | 2023-03-08 | 2023-03-08 | 2023-03-09 | N/A | N/A | N/A | N/A | 2023-03-14 | N/A | 2023-03-24 | 2023-03-24 | Denied | 16 | No | Rev #5; JEB no comments 3/9/23; KF no comments 3/9/23; KN comments 3/14/23 (jls); waited for developer to hear back from HOA in regards to detention pond access. Developer got denied access & will redesigning entire site. Plan set is now outdated
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | TxDOT Permit | 2023-03-08 | 2023-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-21 | Emailed to TxDOT | 13 | Yes | N/A
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2023-03-09 | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Comments | 14 | Yes | Rev #1
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2023-03-09 | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Comments | 14 | Yes | Rev #3
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) EE | 2023-03-09 | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Comments | 14 | Yes | Rev #2
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-03-10 | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | N/A | 2023-03-24 | 2023-03-24 | Comments | 14 | Yes | Rev #1; JEB comments 3/24/23 (KCS)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) DR | 2023-03-10 | 2023-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 14 | Yes | Rev #1
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 6 Lts | 5 J land & Development LLC | Schultz Engineering | Revised (Digital) CP | 2023-03-13 | 2023-03-20 | UKN | N/A | N/A | N/A | N/A | 2023-03-22 | N/A | 2023-03-22 | 2023-03-22 | Approved | 9 | Yes | Rev #2; Distribution delayed - staff error; JEB no comments 3/20/23; KN no comments 3/22/23 (jls)
Windmill Park | BMG | FP22-36 | Windmill Park Subd., Blk 1&2 6 Lts | 5 J land & Development LLC | Schultz Engineering | Revised (Digital) EE | 2023-03-13 | 2023-03-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Approved | 9 | Yes | Rev #2; Distribution delayed - staff error (jls)
Crossway Auto Center | ZFK | SP22-61 | Progress Park Ph 2, Blk 2 Lt 5 | Michael Kelly | Miguel Alvarado | 1 DR | 2023-03-14 | 2023-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Comments | 16 | No | Draft version of drainage report, missing crucial information
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) CP | 2023-03-14 | 2023-03-14 | UKN | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | N/A | 2023-03-22 | 2023-03-22 | Comments | 8 | Yes | Rev #1; JEB no comments 3/14/23; KN no comments 3/22/23; ZFK no comments 3/22/23 (jls)
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) EE | 2023-03-14 | 2023-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Comments | 8 | Yes | Rev #1
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) UL | 2023-03-14 | 2023-03-14 | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | N/A | 2023-03-22 | 2023-03-22 | Comments | 8 | Yes | Rev #1; JEB comments 3/14/23; KN no comments 3/22/23 (jls)
Hush & Whisper | BMG | FP23-02 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) DR | 2023-03-14 | 2023-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Comments | 8 | Yes | Rev #1
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) CP | 2023-03-15 | 2023-03-15 | 2023-03-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 9 | Yes | Rev #3; AM no comments 3/15/23; KN comments 3/22/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) EE | 2023-03-15 | 2023-03-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 9 | Yes | Rev #2
Texas Communications | BMG | SP22-65 | Brazos County Ind'l Park Ph 3, Blk 7 Lt 10 | Broadband Towers/ The Sendero Group | J4 Engineering | Revised (Digital) DR | 2023-03-17 | 2023-03-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Approved | 10 | Yes | Rev #2
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Digital CP | 2023-03-17 | 2023-03-17 | UKN | UKN | N/A | N/A | 2023-03-29 | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | Comments | 14 | Yes | Submitted 3/15/23; Waited on EE; KN comments 3/22/23; JEB comments 3/27/23 (jls)
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Digital SR | 2023-03-17 | 2023-03-17 | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | Comments | 14 | Yes | KN comments 3/22/23; JEB comments 3/27/23 (jls)
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Digital WR | 2023-03-17 | 2023-03-17 | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | N/A | 2023-03-31 | 2023-03-31 | Comments | 14 | Yes | KN comments 3/22/23; JEB comments 3/27/23 (jls)
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Digital EE | 2023-03-17 | 2023-03-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Comments | 14 | Yes | N/A
Santa Teresa | SJS | SP23-26 | Opersteny, Blk 3 Lt 1R | Santa Teresa Catholic Church | J4 Engineering | Digital DL | 2023-03-22 | 2023-03-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Approved | 12 | Yes | N/A
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) UR | 2023-03-22 | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | N/A | 2023-03-24 | 2023-03-24 | Comments | 2 | Yes | Rev #2
Post Office Bldg Expn | ENB | SQ23-04 | Briar Meadows Creek Ph 3, Lt 4 | U S Postal Service | GPD Group | SQ Permit | 2023-03-22 | 2023-03-28 | N/A | N/A | 2023-04-03 | 2023-04-03 | 2023-04-03 | 2023-04-03 | UKN | 2023-04-03 | 2023-04-03 | Comments | 12 | Yes | Waited on Site Plan to be submitted to SDRC; SP submitted on 3/22/23 (dms)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-03-23 | 2023-03-23 | UKN | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 1 | Yes | Rev #8
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2023-03-23 | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 1 | Yes | Rev #3
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) WL | 2023-03-23 | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 1 | Yes | Rev #1
Oakmont Ph 4B | KCS | FP22-42 | Oakmont Ph 4B, Blk 30-34 50 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) SL | 2023-03-23 | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Comments | 1 | Yes | Rev #1
Salad and Go | ZFK | SP23-24 | Midway Place, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Digital DL | 2023-03-23 | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | Comments | 13 | Yes | TxDOT comment requires full redesign of site
Salad and Go | ZFK | SP23-24 | Midway Place, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Digital EE | 2023-03-23 | 2023-03-23 | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | N/A | 2023-04-05 | 2023-04-05 | Comments | 13 | Yes | TxDOT comment requires full redesign of site
Salad and Go | ZFK | SP23-24 | Midway Place, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Digital CP | 2023-03-23 | 2023-03-23 | UKN | UKN | N/A | N/A | N/A | 2023-03-23 | N/A | 2023-04-05 | 2023-04-05 | Comments | 13 | Yes | Digital copy recv'd on 3/22/23; Waited on EE; KN comments 3/23/23; JEB no comments 3/23/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Digital DR | 2023-03-24 | 2023-03-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Comments | 18 | No | Late due to Easter weekend and Urban Drainage Seminar
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Digital EE | 2023-03-24 | 2023-03-24 | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | N/A | 2023-04-11 | 2023-04-11 | Comments | 17 | No | JEB comments 3/27/23; KN comments 4/6/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | 1 CP | 2023-03-24 | 2023-03-24 | UKN | UKN | N/A | N/A | N/A | 2023-04-06 | N/A | 2023-04-11 | 2023-04-11 | Comments | 17 | No | JEB comments 3/27/23; KN comments 4/6/23 (jls)
Regional Detention Pond | BMG | SQ22-06 | Windmill Park Subd | 2820 Nguyen LLC | J4 Engineering | Revised (Digital) DR | 2023-03-24 | 2023-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Comments | 17 | No | Rev #1
1824 Cimino Dr | SJS | SP23-31 | Carrabba Ind'l Park Ph 11, Blk 1 Lt 9 | GRT Interests | J4 Engineering | Digital DL | 2023-03-29 | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Approved | 13 | Yes | N/A
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Revised (Digital) DL | 2023-03-29 | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | Comments | 11 | Yes | Rev #1; SJS comments
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Revised (Digital) CP | 2023-03-29 | 2023-03-29 | 2023-03-29 | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | N/A | 2023-04-10 | 2023-04-10 | Comments | 12 | Yes | Rev #1; KF no comments 3/29/23; JEB comments 3/31/23; KN no comments 4/6/23; SJS comments (jls)
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2023-03-29 | 2023-03-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Comments | 13 | Yes | Rev #6
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) CP | 2023-03-29 | 2023-03-29 | UKN | N/A | N/A | N/A | N/A | 2023-04-06 | N/A | 2023-04-11 | 2023-04-11 | Comments | 13 | Yes | Rev #7; JEB no comments 3/31/23; KN no comments 4/6/23 (jls)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) DR | 2023-03-31 | 2023-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Comments | 4 | Yes | Rev #2
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) EE | 2023-03-31 | 2023-03-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Comments | 4 | Yes | Rev #2
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-03-31 | 2023-03-31 | UKN | N/A | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-04 | 2023-04-04 | Comments | 4 | Yes | Rev #2; JEB comments 4/4/23; KN no comments 4/6/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) UR | 2023-04-04 | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | N/A | 2023-04-12 | 2023-04-12 | Comments | 7 | Yes | Rev #3; JEB no comments 4/12/23 (KCS)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) EE | 2023-04-04 | 2023-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Comments | 7 | Yes | Rev #3
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) CP | 2023-04-04 | 2023-04-04 | 2023-04-06 | N/A | N/A | N/A | N/A | 2023-04-12 | N/A | 2023-04-12 | 2023-04-12 | Comments | 7 | Yes | Rev #4; AM comments 4/6/23; KN comments 4/6/23 (jls); JEB no comments 4/12/23 (KCS)
4251 Boonville Dr | KCS | RZ23-08 | J W Scott Survey | Adam Development Properties LP | Kimley-Horn & Assoc | Digital TIA | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | 2023-04-18 | N/A | N/A | 2023-04-20 | 2023-04-20 | Comments | 14 | Yes | N/A
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-04-05 | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Comments | 6 | Yes | Rev #9, KF comments 4/5/23
Brazos Christian School | BMG | SP23-19 | Brazos Christian School , Blk 1 Lt 1R | Brazos Christian School | McClure & Browne | Digital DL | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | Comments | 1 | Yes | N/A
Salad and Go | ZFK | SP23-24 | Midway Place, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Digital UR | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | N/A | 2023-04-14 | 2023-04-14 | Comments | 8 | Yes | JEB no comments & KN comments 4/6/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) SL | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Approved | 15 | No | Rev #2
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Digital EE | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Comments | 15 | No | Rev #1
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Digital DR | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Comments | 15 | No | Rev #1
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | TxDOT Permit | 2023-04-05 | 2023-04-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | Comments | 0 | Yes | Permit Submitted on 4/5/23; Waited on Signature & Traffic Control Plan (dms)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-04-06 | 2023-04-06 | UKN | N/A | N/A | N/A | N/A | 2023-04-14 | N/A | 2023-04-17 | 2023-04-17 | Comments | 10 | Yes | Rev #3; JEB no comments 4/14/23 (dms)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) EE | 2023-04-06 | 2023-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | Comments | 10 | Yes | Rev #3
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) DR | 2023-04-06 | 2023-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | Comments | 11 | Yes | Rev #3
Brazos Christian School | BMG | SP23-19 | Brazos Christian School , Blk 1 Lt 1R | Brazos Christian School | McClure & Browne | Digital DR | 2023-04-12 | 2023-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | Comments | 0 | Yes | N/A
Carrabba Terrabon Research Park | SJS | SP23-20 | Carrabba Terrabon Research Park, Lt 1 | Amence Development | Altar Group | Digital DL | 2023-04-12 | 2023-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Approved | 9 | Yes | N/A
Coffee Shop w/ Drive Thru | KCS | SP23-13 | Smythe Add'n, Blk C Lt 7R | Asher Development | Kimley-Horn & Assoc | TxDOT Permit | 2023-04-12 | 2023-04-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-26 | Emailed to TxDOT | 14 | Yes | N/A
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | TxDOT Permit | 2023-04-14 | 2023-04-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-26 | Emailed to TxDOT | 12 | Yes | N/A
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-04-18 | 2023-04-18 | UKN | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Comments | 0 | Yes | Rev #4; pending approval contingent on sewer/lift station report, 4/18/23, (KCS)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) EE | 2023-04-18 | 2023-04-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Comments | 0 | Yes | Rev #4; pending approval contingent on sewer/lift station report, 4/18/23, (KCS)
Reveille Estates Ph 1 | KCS | FP23-10 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) DR | 2023-04-18 | 2023-04-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Comments | 0 | Yes | Rev #4; pending approval contingent on sewer/lift station report, 4/18/23, (KCS)
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-04-19 | 2023-04-19 | 2023-04-20 | N/A | N/A | N/A | N/A | 2023-04-28 | N/A | 2023-04-28 | 2023-04-28 | Comments | 9 | Yes | Rev #10; KF no comments 4/20/23 (jls); Not initially forwarded to water for review
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Revised (Digital) DL | 2023-04-19 | 2023-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Approved | 7 | Yes | Rev #3
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Revised (Digital) CP | 2023-04-19 | 2023-04-19 | 2023-04-20 | N/A | N/A | N/A | 2023-04-25 | 2023-04-20 | N/A | 2023-04-23 | 2023-04-23 | Comments | 4 | Yes | Rev #2; KF no comments 4/20/23; KN comments 4/20/23; JEB no comments 4/20/23; ZFK comments 4/25/23 (jls)
Saint Gobain Bldg Expansion | ZFK | SP22-50 | Brazos County Ind'l Park Ph 3, Blk 3 Lt 1 | Saint Gobain | Kevin McCreary | Revised (Digital) CP | 2023-04-19 | 2023-04-19 | 2023-04-20 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Comments | 9 | Yes | Rev #2; KF no comments 4/20/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) CP | 2023-04-19 | 2023-04-19 | UKN | N/A | N/A | N/A | N/A | 2023-04-20 | N/A | 2023-04-26 | 2023-04-26 | Comments | 7 | Yes | Rev #5; JEB comments 4/20/23; KN no comments 4/20/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) DR | 2023-04-19 | 2023-04-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Comments | 7 | Yes | Rev #5
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2023-04-20 | 2023-04-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Comments | 6 | Yes | Rev #8
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised (Digital) CP | 2023-04-21 | 2023-04-21 | 2023-04-26 | 2023-04-21 | N/A | N/A | N/A | 2023-04-28 | N/A | 2023-04-28 | 2023-04-28 | Comments | 7 | Yes | Rev #1; JEB comments 4/24/23; KF no comments 4/26/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised (Digital) EE | 2023-04-21 | 2023-04-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | Comments | 7 | Yes | Rev #1
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Digital SR | 2023-04-21 | 2023-04-21 | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-04-28 | 2023-04-28 | Comments | 7 | Yes | JEB comments 4/24/23; KN comments 4/28/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Digital WR | 2023-04-21 | 2023-04-21 | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | N/A | 2023-04-28 | 2023-04-28 | Comments | 7 | Yes | JEB comments 4/24/23; KN comments 4/28/23 (jls)
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Digital DR | 2023-04-25 | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Comments | 13 | Yes | N/A
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Digital CP | 2023-04-25 | 2023-04-25 | 2023-05-04 | 2023-04-26 | N/A | N/A | N/A | 2023-05-08 | N/A | 2023-05-08 | 2023-05-08 | Comments | 13 | Yes | Digital copy recv'd on 3/21/23; Waited on EE (jls); JEB comments 4/26/23; MO comments 5/4/23; KN comments 5/8/23 (jls)
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Digital EE | 2023-04-25 | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Comments | 13 | Yes | N/A
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Digital CP | 2023-04-25 | 2023-04-25 | UKN | UKN | N/A | N/A | 2023-05-05 | 2023-04-28 | N/A | 2023-05-09 | 2023-05-09 | Comments | 14 | Yes | ZFK no comments 5/5/23 (jls)
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Digital EE | 2023-04-25 | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | Comments | 14 | Yes | N/A
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Digital DR | 2023-04-25 | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | Comments | 14 | Yes | N/A
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Digital SR | 2023-04-25 | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | N/A | 2023-05-09 | 2023-05-09 | Comments | 14 | Yes | N/A
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Digital WR | 2023-04-25 | 2023-04-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | Comments | 14 | Yes | N/A
Hush & Whisper | BMG | SP23-28 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) UL | 2023-04-26 | 2023-04-23 | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | N/A | 2023-05-01 | 2023-05-01 | Comments | 5 | Yes | Rev #2; KN Comments 5/4/23 (jls)
Hush & Whisper | BMG | SP23-28 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) DR | 2023-04-26 | 2023-04-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Comments | 5 | Yes | Rev #2
Hush & Whisper | BMG | SP23-28 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Fibertown | Revised (Digital) CP | 2023-04-26 | 2023-04-26 | UKN | N/A | N/A | N/A | N/A | 2023-05-01 | N/A | 2023-05-01 | 2023-05-01 | Comments | 5 | Yes | Rev #2; KN Comments 5/4/23 (jls)
Hush & Whisper | BMG | SP23-28 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Arkitex Studio Inc | TxDOT Permit | 2023-04-27 | 2023-04-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Emailed to TxDOT | 4 | Yes | Permit Submitted on 3/21/23; Waited on Traffic Control Plan (dms)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised (Digital) CP | 2023-05-02 | 2023-05-02 | 2023-05-03 | N/A | N/A | N/A | N/A | 2023-05-08 | N/A | 2023-05-09 | 2023-05-09 | Comments | 7 | Yes | Rev #2; KF no comments 5/3/23; JEB comments 5/8/23; KN comments 5/8/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised (Digital) WR | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | N/A | 2023-05-09 | 2023-05-09 | Comments | 7 | Yes | Rev #1; JEB comments 5/8/23; KN comments 5/8/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised (Digital) SR | 2023-05-02 | 2023-05-02 | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | N/A | 2023-05-09 | 2023-05-09 | Comments | 7 | Yes | Rev #1; JEB comments 5/8/23; KN comments 5/8/23 (jls)
Hush & Whisper | BMG | SQ23-05 | Hush & Whisper Barrel Storage Subd., Blk 1 Lt 1 | Tabor Road Ventures | Arkitex Studio Inc | SQ Permit | 2023-05-02 | 2023-05-08 | N/A | N/A | 2023-05-09 | UKN | UKN | 2023-05-08 | UKN | 2023-05-08 | 2023-05-08 | Approved | 6 | Yes | Approval to proceed from LAH via email 2023-03-27 (prior to SQ submittal)
4251 Boonville Dr | KCS | RZ23-08 | J W Scott Survey | Adam Development Properties LP | Kimley-Horn & Assoc | Revised (Digital) TIA | 2023-05-03 | 2023-05-03 | N/A | N/A | N/A | N/A | 2023-05-10 | N/A | N/A | 2023-05-10 | 2023-05-18 | Comments | 15 | No | Rev #1
Brazos Christian School | BMG | SP23-19 | Brazos Christian School , Blk 1 Lt 1R | Brazos Christian School | McClure & Browne | Revised (Digital) DL | 2023-05-03 | 2023-05-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Comments | 5 | Yes | N/A
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Revised (Digital) CP | 2023-05-03 | 2023-05-03 | 2023-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Comments | 7 | Yes | Rev #3; KF no comments; JEB no comments; KN comments 5/4/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) CP | 2023-05-03 | 2023-05-03 | 2023-05-04 | N/A | N/A | N/A | N/A | 2023-05-05 | N/A | 2023-05-05 | 2023-05-05 | Approved | 2 | Yes | Rev #6; AM no comments 5/4/23; JEB no comments 5/4/23; KF no comments 5/4/23 (jls)
Mods Apt Complex | KCS | SP22-58 | The Mods, Blk 1&2 2 Lts | JL2E Investments | L2 Engineering | Revised (Digital) EE | 2023-05-03 | 2023-05-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | Approved | 2 | Yes | N/A
4251 Boonville Dr | KCS | RZ23-08 | J W Scott Survey | Adam Development Properties LP | Kimley-Horn & Assoc | Digital DR | 2023-05-05 | 2023-05-05 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-21 | 2023-05-21 | Comments | 16 | No | Email sent to design engineer 5/18/23 to advise still under review and comments will be returned upon receipt (KCS). FP Coor. Comments sent 5/21/2023 (KCS).
BISD Maintenance & Transportation Facility | ZFK | SP22-64 | BISD Subd (Bryan ISD Operations District) | BISD-Paul Buckner | Quiddity Engineering | Revised (Digital) CP | 2023-05-08 | 2023-05-08 | UKN | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-16 | Approved | 8 | Yes | Rev #11; JEB no comments 5/8/23 (jls); Approved 5/16
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) TIA | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | Approved | 14 | Yes | Rev #3
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) EE | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | Approved | 14 | Yes | Rev #3
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Digital UR | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | N/A | 2023-05-22 | 2023-05-22 | Comments | 14 | Yes | Rev #3
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Digital DR | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | Comments | 14 | Yes | Awaiting comments from Sam Vernon
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) CP | 2023-05-08 | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-24 | 2023-05-24 | Comments | 16 | No | Rev #5; JEB no comments 5/8/23; MO no comments 5/8/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) EE | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | Comments | 16 | No | Rev #5
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) WR | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | N/A | 2023-05-24 | 2023-05-24 | Approved | 16 | No | Rev #5; JEB no comments 5/8/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) SR | 2023-05-08 | 2023-05-08 | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | N/A | 2023-05-24 | 2023-05-24 | Comments | 16 | No | Rev #5; JEB no comments 5/8/23 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised (Digital) CP | 2023-05-10 | 2023-05-10 | 2023-05-10 | N/A | N/A | N/A | N/A | 2023-05-10 | N/A | 2023-05-18 | 2023-05-18 | Comments | 8 | Yes | Rev #3; KF no comments 5/10/23 (jls)
Dollar Tree | SJS | SP23-11 | Villa Maria Wal-Mart Addn, Blk B Lt 11 | Crossfulton Investments | Gessner Engineering | Revised (Digital) CP | 2023-05-11 | 2023-05-11 | 2023-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Approved | 7 | Yes | Rev #4; KF no comments 5/15/23 (jls)
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | Revised (Digital) DR | 2023-05-11 | 2023-05-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Approved | 7 | Yes | N/A
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) SR | 2023-05-15 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | 2023-05-25 | Comments | 10 | Yes | Rev #1; JEB comments 5/19/23 (jls)
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) WR | 2023-05-15 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | 2023-05-25 | Comments | 10 | Yes | Rev #1; JEB comments 5/19/23 (jls)
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) EE | 2023-05-15 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | Comments | 10 | Yes | Rev #1
Timber Oaks | SJS | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) CP | 2023-05-15 | 2023-05-16 | UKN | N/A | N/A | N/A | 2023-05-24 | 2023-05-19 | N/A | 2023-05-25 | 2023-05-25 | Comments | 10 | Yes | Rev #1; JEB comments 5/19/23; ZFK no comments 5/24/23 (jls)
7 Brew Coffee | ZFK | SP23-21 | Texas-Villa Maria Retail, Lt 2 | Texas-Villa Maria Retail LP | Kirkman Engineering | Digital EE | 2023-05-16 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-30 | 2023-05-30 | Comments | 13 | Yes | JEB comments 5/16/23 (dms); KN comments 5/25/23 (jls)
7 Brew Coffee | ZFK | SP23-21 | Texas-Villa Maria Retail, Lt 2 | Texas-Villa Maria Retail LP | Kirkman Engineering | Digital CP | 2023-05-16 | 2023-05-16 | UKN | 2023-05-26 | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-30 | 2023-05-30 | Comments | 13 | Yes | Submitted 5/12/23; Waited on EE (jls); JEB comments 5/16/23 (dms); KN comments 5/25/23 (jls)
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | 1 EE | 2023-05-16 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-31 | 2023-05-31 | Comments | 14 | Yes | JEB comments 5/17/23 (jls)
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Digital DR | 2023-05-16 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Comments | 14 | Yes | N/A
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) EE | 2023-05-16 | 2023-05-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | Comments | 9 | Yes | Rev #1
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) CP | 2023-05-16 | 2023-05-16 | 2023-05-17 | N/A | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-25 | 2023-05-25 | Comments | 9 | Yes | Rev #1
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | 3 CP | 2023-05-17 | 2023-05-17 | 2023-05-18 | UKN | N/A | N/A | N/A | 2023-05-30 | N/A | 2023-05-31 | 2023-05-31 | Comments | 13 | Yes | Digital recv'd on same day; Only routed 1; Submittal contained missing pages/errors; JEB comments on incomplete set 5/17/23; PK no comments 5/18/23; KN comments 5/30/23; JEB comments 5/30/23 (jls)
Crossway Auto Center | ZFK | SP22-61 | Progress Park Ph 2, Blk 2 Lt 5 | Michael Kelly | Miguel Alvarado | Revised (Digital) DR | 2023-05-22 | 2023-05-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Comments | 8 | Yes | Sent to TxDOT for approval; TxDOT comments received back on 6/13 and forwarded to developer for revisions
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | 3 CP | 2023-05-22 | 2023-05-22 | 2023-05-26 | UKN | N/A | N/A | N/A | 2023-05-30 | N/A | 2023-06-08 | 2023-06-08 | Comments | 16 | No | Digital copy submitted on 5/22/23 & hard copy submitted on 5/23/23; only 1 routed for review; KF no comments 5/25/23 (dms); JEB comments 5/23/23; KN comments 5/30/23 (jls)
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | 2 EE | 2023-05-22 | 2023-05-22 | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | N/A | 2023-06-08 | 2023-06-08 | Comments | 16 | No | Digital copy submitted on 5/22/23 & hard copy submitted on 5/23/23; JEB comments 5/23/23; KN comments 5/30/23 (jls)
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Digital DR | 2023-05-22 | 2023-05-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | Comments | 16 | No | Comments sent 6/8
Hope Subd Ph 1 | BMG | FP21-17 | Hope Subd Ph 1, Blk 1 Lts 1-12 & Blk 2 Lts 1-10 | B/CS Habitat for Humanity | CEC | Revised (Digital) DR | 2023-05-24 | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | Comments | 20 | No | Rev #2; need to review as a new submittal since it's been over 2 yrs (dms)
Hope Subd Ph 1 | BMG | FP21-17 | Hope Subd Ph 1, Blk 1 Lts 1-12 & Blk 2 Lts 1-10 | B/CS Habitat for Humanity | CEC | Revised (Digital) SR | 2023-05-24 | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | N/A | 2023-06-14 | 2023-06-14 | Comments | 20 | No | Rev #2; need to review as a new submittal since it's been over 2 yrs (dms); KN comments 6/6/23 (jls)
Hope Subd Ph 1 | BMG | FP21-17 | Hope Subd Ph 1, Blk 1 Lts 1-12 & Blk 2 Lts 1-10 | B/CS Habitat for Humanity | CEC | Revised (Digital) EE | 2023-05-24 | 2023-05-24 | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | N/A | 2023-06-14 | 2023-06-14 | Comments | 20 | No | Rev #2; need to review as a new submittal since it's been over 2 yrs (dms); KN comments 6/6/23 (jls)
Hope Subd Ph 1 | BMG | FP21-17 | Hope Subd Ph 1, Blk 1 Lts 1-12 & Blk 2 Lts 1-10 | B/CS Habitat for Humanity | CEC | Revised (Digital) CP | 2023-05-24 | 2023-05-24 | 2023-05-26 | 2023-05-24 | N/A | N/A | 2023-06-05 | 2023-06-06 | N/A | 2023-06-14 | 2023-06-14 | Comments | 20 | No | Rev #2; need to review as a new submittal since it's been over 2 yrs; KF no comments 5/26/23 (dms); KN comments 6/6/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) EE | 2023-05-24 | 2023-05-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-08 | Comments | 14 | Yes | Rev #2
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) DR | 2023-05-24 | 2023-05-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-08 | Comments | 14 | Yes | Rev #2
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) CP | 2023-05-24 | 2023-05-25 | UKN | N/A | N/A | N/A | N/A | 2023-06-01 | N/A | 2023-06-01 | 2023-06-08 | Comments | 14 | Yes | Rev #2; JEB no comments 5/25/23 (jls)
Finfeather Storage | BMG | SP23-15 | Cedar Ridge Ph 1, Blk 1 Lt 1 | Dallas Beck | RTR Design | Digital DL | 2023-05-25 | 2023-05-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | Comments | 0 | Yes | N/A
Villages @ Traditions Ph 5B | BMG | SP22-59 | Traditions Ph 19, Blk 1 Lt 1R | Tradition Acq Partnership LP | Schultz Engineering | Revised (Digital) CP | 2023-05-25 | 2023-05-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Approved | 1 | Yes | Plans submitted to reflect revised BTU routing per discussions in the Pre-Con (jls)
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) EE | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | Comments | 10 | Yes | Rev #1
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) SR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | N/A | 2023-06-06 | 2023-06-06 | Comments | 10 | Yes | Rev #1; JEB comments 6/5/23; KN comments 6/6/23 (jls)
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) CP | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | N/A | 2023-06-06 | 2023-06-06 | Comments | 10 | Yes | Rev #1; JEB comments 6/5/23; KN comments 6/6/23 (jls)
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | 1 CP | 2023-05-26 | 2023-05-26 | 2023-06-09 | UKN | N/A | N/A | 2023-06-07 | 2023-06-06 | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | KN comments 6/6/23 (kcs); JEB NO comments 6/6/23 (kcs); PK comments 6/9/23 (JLS)
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Digital EE | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Digital DR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Digital SR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Digital WR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | 1 CP | 2023-05-26 | 2023-05-26 | 2023-06-09 | UKN | N/A | N/A | 2023-06-07 | 2023-06-06 | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | KN comments 6/6/23 (kcs); JEB comments 6/6/23 (kcs); ZFK comments 6/7/23; PK comments 6/9/23 (jls)
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Digital EE | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Digital DR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Digital SR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Digital WR | 2023-05-26 | 2023-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Comments | 11 | Yes | N/A
LEC Exterior Amenities | BMG | SP23-14 | Country Club Lake Add'n, Blk 1 Lt 1 | COB-Parks & Rec | PBK Sports | Digital DR | 2023-05-26 | 2023-06-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | Comments | 19 | No | Email missed by staff member causing delay in routing (jls)
4251 Boonville Dr | KCS | RZ23-08 | J W Scott Survey | Adam Development Properties LP | Kimley-Horn & Assoc | Revised (Digital) TIA | 2023-05-31 | 2023-05-31 | N/A | N/A | N/A | N/A | 2023-05-31 | N/A | N/A | 2023-05-31 | 2023-05-31 | Approved | 0 | Yes | Rev #2
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Digital DL | 2023-05-31 | 2023-06-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | Comments | 18 | No | Email missed by staff member causing delay in routing (jls)
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Digital EE | 2023-05-31 | 2023-06-05 | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | N/A | 2023-06-23 | 2023-06-23 | Comments | 18 | No | JEB comments 6/14/23; KN comments 6/15/23 (jls)
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Digital UL | 2023-05-31 | 2023-06-05 | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | N/A | 2023-06-23 | 2023-06-23 | Comments | 18 | No | JEB comments 6/14/23; KN comments 6/15/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Digital CP | 2023-06-01 | 2023-06-01 | UKN | UKN | N/A | N/A | 2023-06-13 | 2023-06-12 | N/A | 2023-06-19 | 2023-06-19 | Comments | 18 | No | KN comments 6/12/23; ZFK comments 6/13/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Digital EE | 2023-06-01 | 2023-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | Comments | 18 | No | KN comments 6/12/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Digital WL | 2023-06-01 | 2023-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | Comments | 18 | No | KN comments 6/12/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Digital SL | 2023-06-01 | 2023-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | Comments | 18 | No | KN comments 6/12/23 (jls)
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) DR | 2023-06-07 | 2023-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | Comments | 7 | Yes | Rev #1
Pena RV Parking Lot | SJS | SP23-45 | Get-n-Go, Blk 1 Pt of Lt 1 | Richard Pena | Galindo Engineers | Digital DR | 2023-06-07 | 2023-06-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | Approved | 7 | Yes | N/A
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) CP | 2023-06-07 | 2023-06-07 | 2023-06-08 | N/A | N/A | N/A | N/A | 2023-06-07 | N/A | 2013-06-12 | 2023-06-13 | Comments | 6 | Yes | Rev #2; JEB comments 6/7/23; MO comments 6/8/23; KN comments 6/13/23 (jls)
Finfeather Storage | BMG | SP23-15 | Cedar Ridge Ph 1, Blk 1 Lt 1 | Dallas Beck | RTR Design | Digital CP | 2023-06-12 | 2023-06-12 | UKN | N/A | N/A | N/A | N/A | 2023-06-15 | N/A | 2023-06-23 | 2023-06-26 | Comments | 14 | Yes | KN comments 6/15/23 (jls)
Finfeather Storage | BMG | SP23-15 | Cedar Ridge Ph 1, Blk 1 Lt 1 | Dallas Beck | RTR Design | Digital EE | 2023-06-12 | 2023-06-12 | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | N/A | 2023-06-23 | 2023-06-26 | Comments | 14 | Yes | KN comments 6/15/23 (jls)
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Revised (Digital) EE | 2023-06-13 | 2023-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | Comments | 10 | Yes | Rev #1
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Digital CP | 2023-06-13 | 2023-06-13 | 2023-06-23 | N/A | N/A | N/A | N/A | 2023-06-15 | N/A | 2023-06-23 | 2023-06-23 | Comments | 10 | Yes | JEB comments 6/14/23; KN comments 6/15/23; MO no comments 6/23/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-06-20 | 2023-06-20 | 2023-06-29 | N/A | N/A | N/A | 2023-06-27 | 2023-06-29 | N/A | 2023-07-10 | 2023-07-10 | Comments | 20 | No | Rev #1; ZFK comments 6/27/23; KN no comments 6/29/23; PK no comments 6/29/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Digital DL | 2023-06-20 | 2023-06-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Comments | 20 | No | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) DR | 2023-06-21 | 2023-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | Comments | 12 | Yes | Rev #2; Scheduling meeting to go over form and content for drainage report 7/3
First Baptist Church | BMG | SP22-70 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley-Horn & Assoc | Revised (Digital) DL | 2023-06-21 | 2023-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-27 | Comments | 6 | Yes | Rev #2
Twin City Mission Parking Lot | BMG | SP23-12 | Lawler Place Ph 1, Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Digital DL | 2023-06-21 | 2023-06-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Approved | 0 | Yes | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Digital CP | 2023-06-22 | 2023-06-22 | 2023-07-05 | UKN | N/A | N/A | UKN | 2023-07-03 | N/A | 2023-07-14 | 2023-07-14 | Comments | 21 | No | Digital copy recv'd on 6/15/23; Waited on EE (jls); KN comments 7/3/23 (dms); AM no comments 7/5/23 (jls)
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Digital SL | 2023-06-22 | 2023-06-22 | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-14 | 2023-07-14 | Comments | 21 | No | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Digital WL | 2023-06-22 | 2023-06-22 | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-14 | 2023-07-14 | Comments | 21 | No | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Digital DL | 2023-06-22 | 2023-06-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Comments | 21 | No | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Digital EE | 2023-06-22 | 2023-06-22 | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-14 | 2023-07-14 | Comments | 21 | No | N/A
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Revised (Digital) EE | 2023-06-27 | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | Comments | 2 | Yes | Rev #2
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Revised (Digital) CP | 2023-06-27 | 2023-06-27 | 2023-06-28 | N/A | N/A | N/A | N/A | 2023-06-29 | N/A | 2023-06-30 | 2023-06-30 | Comments | 2 | Yes | Rev #2; JEB comments 6/27/23; MO no comments 6/28/23; KN no comments (jls)
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | 1 (Revised) CP | 2023-06-27 | 2023-06-27 | 2023-06-28 | N/A | N/A | N/A | N/A | 2023-07-05 | N/A | 2023-07-05 | 2023-07-05 | Comments | 7 | Yes | Rev #1; Digital copy submitted on 6/27/23 & hard copy submitted same day; JEB comments 6/27/23; KF comments 6/28/23; KN comments 7/5/23 (jls)
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | 1 (Revised) EE | 2023-06-27 | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Approved | 7 | Yes | Rev #2
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) DR | 2023-06-27 | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Comments | 7 | Yes | Rev #2
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Digital SR | 2023-06-27 | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | N/A | 2023-07-05 | 2023-07-05 | Comments | 7 | Yes | JEB comments 6/27/23; KN comments 7/5/23 (jls)
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Digital WR | 2023-06-27 | 2023-06-27 | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-05 | 2023-07-05 | Comments | 7 | Yes | JEB comments 6/27/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) CP | 2023-06-28 | 2023-06-28 | UKN | N/A | N/A | N/A | N/A | 2023-06-29 | N/A | 2023-06-29 | 2023-06-29 | Comments | 1 | Yes | Rev #6; JEB no comments 6/29/23; KN comments 7/5/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) SR | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | N/A | 2023-06-29 | 2023-06-29 | Approved | 1 | Yes | Rev #6; JEB no comments 6/29/23; KN comments 7/5/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) DR | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | Comments | 1 | Yes | Rev #6
Timber Oaks | SJS ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) SR | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | N/A | 2023-07-07 | 2023-07-07 | Comments | 8 | Yes | Rev #2; KN comments 7/5/23 (jls)
Timber Oaks | SJS ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) WR | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | N/A | 2023-07-07 | 2023-07-07 | Comments | 8 | Yes | Rev #2; KN comments 7/5/23 (jls)
Timber Oaks | SJS ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) EE | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-07 | Comments | 8 | Yes | Rev #2; KN comments 7/5/23 (jls)
Timber Oaks | SJS ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) CP | 2023-06-28 | 2023-06-28 | 2023-06-29 | N/A | N/A | N/A | N/A | 2023-07-05 | N/A | 2023-07-05 | 2023-07-07 | Comments | 8 | Yes | Rev #2; KF no comments 6/29/23; KN comments 7/5/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised TxDOT Permit | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-07-03 | Emailed to TxDOT | 5 | Yes | Rev #1
World Nail Spa | KCS | SP22-01 | Mitchell-Lawrence-Cavitt, Blk 15 Lts 3-4 | Tommy Nguyen | Patterson Architects | TxDOT Permit | 2023-06-28 | 2023-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-28 | Emailed to TxDOT | 0 | Yes | Original submission was recv'd on 6/13/23. It was incomplete & design engineer was notified on same day (dms)
Pleasant Hill Sec 3 | KCS | PP23-21 | Pleasant Hill Sec 3 Ph 1-9 | WBW Single Land Investment | Yalgo Engineering | Digital DR | 2023-06-29 | 2023-06-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Comments | 34 | No | N/A
7 Brew Coffee | ZFK | SP23-21 | Texas-Villa Maria Retail, Lt 2 | Texas-Villa Maria Retail LP | Kirkman Engineering | Revised (Digital) CP | 2023-06-30 | 2023-06-30 | UKN | N/A | N/A | N/A | N/A | 2023-07-06 | N/A | 2023-07-10 | 2023-07-10 | Comments | 9 | Yes | Rev #1; JEB comments 7/3/23 (dms); KN no comments 7/6/23 (jls)
7 Brew Coffee | ZFK | SP23-21 | Texas-Villa Maria Retail, Lt 2 | Texas-Villa Maria Retail LP | Kirkman Engineering | Revised (Digital) EE | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Approved | 9 | Yes | Rev #1
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2023-06-30 | 2023-06-30 | UKN | N/A | N/A | N/A | N/A | 2023-07-12 | N/A | 2023-07-17 | 2023-07-17 | Comments | 16 | No | KN no comments 7/6/23; JEB no comments 7/12/23 (jls)
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) EE | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Comments | 16 | No | Rev #1
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Comments | 16 | No | Rev #1
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Digital SR | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | N/A | 2023-07-17 | 2023-07-17 | Comments | 16 | No | KN no comments 7/6/23; JEB no comments 7/12/23 (jls)
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) CP | 2023-06-30 | 2023-06-30 | UKN | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #2; ZFK no comments 7/6/23; KN no comments 7/6/23 (jls)
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) DR | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #2
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) EE | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #2
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) SR | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #2
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Revised (Digital) CP | 2023-06-30 | 2023-06-30 | UKN | N/A | N/A | N/A | 2023-07-10 | 2023-07-06 | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #1; KN comments 7/6/23; ZFK no comments (jls)
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Revised (Digital) DR | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #1
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Revised (Digital) EE | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #1
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Revised (Digital) CP | 2023-06-30 | 2023-06-30 | UKN | N/A | N/A | N/A | 2023-07-10 | 2023-07-06 | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #1; KN comments 7/6/23; ZFK no comments (jls)
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Revised (Digital) DR | 2023-06-30 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | Comments | 11 | Yes | Rev #1
Highland Oaks | ZFK | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | 2 EE | 2023-07-03 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Approved | 7 | Yes | Rev #2; Digital copy submitted on 6/30/23
Highland Oaks | ZFK | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | 3 CP | 2023-07-03 | 2023-06-30 | UKN | N/A | N/A | N/A | N/A | 2023-07-06 | N/A | 2023-07-10 | 2023-07-10 | Comments | 7 | Yes | Rev #2; Only 1 routed for rev; JEB comments 7/3/23 (dms); KN comments 7/6/23 (jls)
Highland Oaks | ZFK | FP21-28 | Highland Oaks Ph 1, Blk 1-4 & 7 49 Lts | Hilton Road LLC | J4 Engineering | Digital DR | 2023-07-03 | 2023-06-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Approved | 7 | Yes | N/A
Finfeather Storage | BMG | SP23-15 | Cedar Ridge Ph 1, Blk 1 Lt 1 | Dallas Beck | RTR Design | Revised (Digital) CP | 2023-07-03 | 2023-07-05 | UKN | N/A | N/A | N/A | N/A | 2023-07-07 | N/A | 2023-07-13 | 2023-07-13 | Comments | 10 | Yes | Rev #1; JEB no comments 7/6/23; KN comments 7/7/23 (jls)
Finfeather Storage | BMG | SP23-15 | Cedar Ridge Ph 1, Blk 1 Lt 1 | Dallas Beck | RTR Design | Revised (Digital) EE | 2023-07-03 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | Approved | 10 | Yes | Rev #1; Submission files not labeled properly causing delay (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) DR | 2023-07-03 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | Comments | 10 | Yes | Rev #1
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Revised (Digital) EE | 2023-07-05 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Approved | 6 | Yes | Rev #3
1407 Conner Street | BMG | RP23-18 | Castle Heights Add'n, Blk 3 Lt 5 | Estate of Grant Herbert Wallace | Dawn Development | Revised (Digital) CP | 2023-07-05 | 2023-07-05 | 2023-07-06 | N/A | N/A | N/A | N/A | 2023-07-06 | N/A | 2023-07-11 | 2023-07-11 | Approved | 6 | Yes | Rev #3; MO no comments 7/6/23; JEB comments 7/6/23 (jls)
3100 Leonard Rd | BMG | SP23-54 | Zeno Phillips League, Blk 18 Lt 36 | Adhrit Properties | Adhrit Properties | Digital DL | 2023-07-05 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Approved | 5 | Yes | N/A
Chicken Oil Co | ENB | SP23-39 | J E Scott Survey, Blk 6 Lt 19 | Dixie Chicken | Schultz Engineering | Digital CP | 2023-07-05 | 2023-07-05 | UKN | N/A | N/A | N/A | 2023-07-17 | 2023-07-07 | N/A | 2023-07-17 | 2023-07-17 | Comments | 12 | Yes | JEB comments 7/6/23; KN comments 7/7/23; ZFK comments 7/17/23 (jls)
Chicken Oil Co | ENB | SP23-39 | J E Scott Survey, Blk 6 Lt 19 | Dixie Chicken | Schultz Engineering | Digital EE | 2023-07-05 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | N/A | 2023-07-17 | 2023-07-17 | Comments | 12 | Yes | JEB comments 7/6/23; KN comments 7/7/23 (jls)
First Baptist Church | BMG | SP23-51 | First Baptist Church of Bryan, Blk 1 Lt 1 | First Baptist Church | Kimley-Horn & Assoc | Revised (Digital) DL | 2023-07-05 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-11 | Approved | 6 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Digital CP | 2023-07-05 | 2023-07-05 | UKN | UKN | N/A | N/A | 2023-07-17 | 2024-07-24 | N/A | 2023-07-25 | 2023-07-25 | Comments | 20 | No | Received 6/13/23; Waited for project to be scheduled for SDRC; JEB comments 7/6/23; ZFK no comments 7/17/23; KN comments 7/24/23 (jls)
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Digital EE | 2023-07-05 | 2023-07-05 | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | N/A | 2023-07-25 | 2023-07-25 | Comments | 20 | No | Received 6/13/23; Waited for project to be scheduled for SDRC
Pleasant Hill Sec 3 | KCS | SQ23-06 | Pleasant Hill Sec 3 Ph 1-9 | WBW Single Land Investment | Yalgo Engineering | SQ Permit | 2023-07-05 | 2023-07-10 | N/A | N/A | 2023-07-13 | UKN | 2023-07-10 | 2023-07-10 | UKN | 2023-07-17 | 2023-07-17 | Approved | 12 | Yes | N/A
Park Heights Add'n | SJV | RP23-13 | Park Heights Add'n, Lts 6-8 | Joseph Vaughn, III | Kerr Surveying | Flood Study | 2023-07-07 | 2023-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Comments | 11 | Yes | N/A
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) DR | 2023-07-11 | 2023-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Comments | 0 | Yes | Rev #7
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) EE | 2023-07-11 | 2023-07-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Comments | 0 | Yes | Rev #7
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) CP | 2023-07-11 | 2023-07-11 | 2023-07-13 | N/A | N/A | N/A | N/A | 2023-07-24 | N/A | 2023-07-11 | 2023-07-11 | Comments | 0 | Yes | Rev #7; JEB no comments 7/12/23; MO no comments 7/13/23; KN no comments 7/24/23 (jls)
CC Creation Facility | WPK | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) DR | 2023-07-12 | 2023-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Comments | 6 | Yes | Rev #6
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) CP | 2023-07-12 | 2023-07-12 | UKN | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Approved | 6 | Yes | Rev #2
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) DR | 2023-07-12 | 2023-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Approved | 6 | Yes | Rev #2
Rock Pointe Ph 1 | ZFK | FP23-06 | Rock Pointe Ph 1, Blk 2-4 19 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) WR | 2023-07-12 | 2023-07-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Approved | 6 | Yes | Rev #1
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Digital CP | 2023-07-12 | 2023-07-13 | 2023-07-24 | UKN | N/A | N/A | N/A | 2023-07-24 | N/A | 2023-07-19 | 2023-07-19 | Comments | 7 | Yes | JEB comments 7/17/23 (jls); KN comments 7/24/23, MO no comments 7/24/23 (jls)
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Digital EE | 2023-07-12 | 2023-07-13 | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | N/A | 2023-07-19 | 2023-07-19 | Comments | 7 | Yes | JEB comments 7/17/23 (jls); KN comments 7/24/23 (jls)
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Digital DR | 2023-07-12 | 2023-07-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | Approved | 7 | Yes | N/A
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Digital SR | 2023-07-12 | 2023-07-13 | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | N/A | 2023-07-19 | 2023-07-19 | Approved | 7 | Yes | JEB comments 7/17/23 (jls)
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Digital WL | 2023-07-12 | 2023-07-13 | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | N/A | 2023-07-19 | 2023-07-19 | Approved | 7 | Yes | JEB comments 7/17/23 (jls)
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) DR | 2023-07-14 | 2023-07-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | Comments | 5 | Yes | Rev #3
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) DR | 2023-07-14 | 2023-07-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Comments | 19 | No | Rev #3
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) CP | 2023-07-14 | 2023-07-14 | UKN | N/A | N/A | N/A | N/A | 2023-07-17 | N/A | 2023-08-02 | 2023-08-02 | Comments | 19 | No | Rev #3; JEB no comments 7/17/23 (jls)
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Digital SL | 2023-07-19 | 2023-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Comments | 21 | No | Attachment missing from submission; contacted DE to resend; no response & doc not recv'd (jls)
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Digital DR | 2023-07-19 | 2023-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Comments | 21 | No | DR sent to TxDOT 7/26/2023 (KCS)
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Digital CP | 2023-07-19 | 2023-07-20 | UKN | UKN | N/A | UKN | N/A | 2023-07-26 | N/A | 2023-08-09 | 2023-08-09 | Comments | 21 | No | KN comments 7/24/23 (jls); Comments expected by EOB 8/10/23 (jls)
Shops @ Hudson Oaks | ZFK | SP23-57 | Park Hudson Ph 4, Blk 4 Lt 5R | BTX Retail | Walker Partners | Digital DL | 2023-07-19 | 2023-07-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Approved | 19 | No | Approval upon receipt of TxDOT drainage approval
Shops @ Hudson Oaks | ZFK | SP23-57 | Park Hudson Ph 4, Blk 4 Lt 5R | BTX Retail | Walker Partners | Digital SL | 2023-07-19 | 2023-07-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Comments | 19 | No | N/A
Shops @ Hudson Oaks | ZFK | SP23-57 | Park Hudson Ph 4, Blk 4 Lt 5R | BTX Retail | Walker Partners | Digital WL | 2023-07-19 | 2023-07-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Approved | 19 | No | N/A
Douglass Mitsubishi | BMG | SP23-18 | Garlyn Shelton Imports, Lt 1R | N Douglas Investments | JBS Engineering | Digital DL | 2023-07-20 | 2023-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Comments | 14 | Yes | N/A
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Digital CP | 2023-07-21 | 2023-07-21 | UKN | UKN | N/A | N/A | UKN | 2023-07-24 | N/A | 2023-08-08 | 2023-08-08 | Comments | 18 | No | KN comments 7/24/23, JEB no comments 7/24/23 (jls); Comments expected by EOB 8/10/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Digital EE | 2023-07-21 | 2023-07-21 | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | N/A | 2023-08-08 | 2023-08-08 | Comments | 18 | No | KN comments 7/24/23, JEB no comments 7/24/23 (jls)
Finfeather Storage | BMG | SP23-15 | Cedar Ridge Ph 1, Blk 1 Lt 1 | Dallas Beck | RTR Design | Revised (Digital) CP | 2023-07-21 | 2023-07-21 | 2023-07-26 | N/A | N/A | N/A | N/A | 2023-07-24 | N/A | 2023-07-25 | 2023-07-25 | Approved | 4 | Yes | Rev #2; KN comments 7/24/23; KF no comments 7/26/23 (jls)
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) SR | 2023-07-24 | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | N/A | 2023-07-28 | 2023-07-28 | Approved | 3 | Yes | Rev #3
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) WR | 2023-07-24 | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | N/A | 2023-07-28 | 2023-07-28 | Approved | 3 | Yes | Rev #3
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) EE | 2023-07-24 | 2023-07-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | Comments | 3 | Yes | Rev #3
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) CP | 2023-07-24 | 2023-07-24 | 2023-07-26 | N/A | N/A | N/A | 2023-07-28 | 2023-07-26 | N/A | 2023-07-28 | 2023-07-28 | Comments | 3 | Yes | Rev #3; KN no comments 7/25/23; KF no comments 7/26/23; JEB comments 7/26/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Digital DR | 2023-07-25 | 2023-07-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Comments | 14 | Yes | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) DR | 2023-07-26 | 2023-07-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | Approved | 8 | Yes | N/A
25th St Townhomes | BMG | CU23-03 | Travis Park, Blk 4 Lts 9-10 | Titan Premier Investments | Center Pole Engineering | Digital CP | 2023-07-28 | 2023-07-28 | 2023-08-07 | UKN | N/A | N/A | 2023-08-10 | 2023-08-11 | N/A | 2023-08-14 | 2023-08-14 | Comments | 17 | No | JEB comments 7/31/23; AM no comments 8/7/23; ZFK no comments 8/10/23; KN comments 8/11/23 (jls)
25th St Townhomes | BMG | CU23-03 | Travis Park, Blk 4 Lts 9-10 | Titan Premier Investments | Center Pole Engineering | Digital EE | 2023-07-28 | 2023-07-28 | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | N/A | 2023-08-14 | 2023-08-14 | Comments | 17 | No | N/A
CREI Storage | ENB | SP23-58 | Progress Park Ph 2, Blk 2 Lt 3 | CREI Storage 1820 Owner LP | J4 Engineering | Digital DR | 2023-07-28 | 2023-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | Comments | 18 | No | Waiting on TxDOT Review 8/15/23
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) CP | 2023-07-28 | 2023-07-28 | 2023-08-07 | N/A | N/A | N/A | N/A | 2023-08-07 | N/A | 2023-08-09 | 2023-08-09 | Comments | 12 | Yes | Rev #1; MO comments 8/7/23 (jls)
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) EE | 2023-07-28 | 2023-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Comments | 12 | Yes | Rev #1; JEB comments 7/31/23 (jls)
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Digital DR | 2023-07-28 | 2023-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Comments | 12 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Digital UR | 2023-07-28 | 2023-07-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | Comments | 12 | Yes | JEB comments 7/31/23 (jls)
CREI Storage | ENB | SP23-58 | Progress Park Ph 2, Blk 2 Lt 3 | CREI Storage 1820 Owner LP | J4 Engineering | Digital CP | 2023-07-28 | 2023-08-03 | 2023-08-07 | UKN | N/A | N/A | 2023-08-15 | 2023-08-08 | N/A | 2023-08-15 | 2023-08-15 | Comments | 18 | No | Original submission recv'd 7/28/23, waited for EE (jls); JEB comments 8/3/23; MO no comments 8/7/23; KN comments 8/8/23; ZFK comments 8/15/23 (jls)
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Revised (Digital) CP | 2023-08-01 | 2023-08-01 | 2023-08-07 | N/A | N/A | N/A | N/A | 2023-08-08 | N/A | 2023-08-08 | 2023-08-08 | Comments | 7 | Yes | Rev #1; MO no comments 8/7/23, JEB comments 8/8/23; KN no comments 8/11/23 (jls)
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Revised (Digital) EE | 2023-08-01 | 2023-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Comments | 7 | Yes | Rev #1
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised (Digital) CP | 2023-08-01 | 2023-08-01 | 2023-08-07 | N/A | N/A | N/A | N/A | 2023-08-10 | N/A | 2023-08-08 | 2023-08-08 | Comments | 7 | Yes | KN comments 8/11/23 (jls), Comments, changes may be needed due to SDRC review; Water comments sent on 8/11
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised (Digital) DL | 2023-08-01 | 2023-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Approved | 7 | Yes | N/A
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) CP | 2023-08-01 | 2023-08-01 | 2023-08-01 | N/A | N/A | N/A | N/A | 2023-08-11 | N/A | 2023-08-08 | 2023-08-14 | Comments | 13 | Yes | Rev #4; KF no comments 8/1/23 (jls),
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) EE | 2023-08-01 | 2023-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-14 | Approved | 13 | Yes | Rev #4
CREI Storage | ENB | SP23-58 | Progress Park Ph 2, Blk 2 Lt 3 | CREI Storage 1820 Owner LP | J4 Engineering | Digital EE | 2023-08-03 | 2023-08-03 | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | N/A | 2023-08-14 | 2023-08-15 | Comments | 12 | Yes | JEB comments 8/3/23; KN comments 8/8/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) CP | 2023-08-07 | 2023-08-07 | UKN | N/A | N/A | N/A | N/A | 2023-08-11 | N/A | 2023-08-14 | 2023-08-14 | Approved | 7 | Yes | Rev #8; KN no comments 8/11/23 (jls)
Majestic Pointe Ph 1 | BMG | FP23-26 | Majestic Pointe Ph 1, Blk 2-3 30 Lts | Contreras Construction Co | McClure & Browne | Revised (Digital) DR | 2023-08-07 | 2023-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | Approved | 7 | Yes | Rev #8
Villa Maria Gas Station | KCS | SP21-44 | Shirewood Ph 2, Blk 14 Lt 1 | VM Retail LLC | RSK Engineering | TxDOT Permit | 2023-08-07 | 2023-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Comments | 1 | Yes | Original submission was recv'd on 5/23/23. It was incomplete & design engineer was notified (dms)
TXB C-Store/Gas Station | BMG | SQ23-07 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | SQ Permit | 2023-08-07 | 2023-08-16 | N/A | N/A | 2023-08-17 | 2023-08-18 | 2023-08-18 | 2023-08-20 | 2023-08-18 | 2023-08-21 | 2023-08-21 | Approved | 14 | Yes | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-08-11 | 2023-08-11 | UKN | N/A | N/A | N/A | N/A | 2023-08-15 | N/A | 2023-08-16 | 2023-08-16 | Comments | 5 | Yes | JEB comments 8/15/23; KN comments 8/15/23 (jls)
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) DR | 2023-08-11 | 2023-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | Approved | 5 | Yes | Approved
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) EE | 2023-08-11 | 2023-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | Approved | 5 | Yes | Approved
CC Creation Facility | WPK | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) CP | 2023-08-11 | 2023-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Approved | 12 | Yes | Detention Pond/Storm Sewer
CC Creation Facility | WPK | SP22-08 | Bryan Ind'l Park Ph 2, Blk 6 Lt 1R | Lawson Properties V | Gessner Engineering | Revised (Digital) DR | 2023-08-11 | 2023-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Approved | 12 | Yes | N/A
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2023-08-14 | 2023-08-14 | 2023-08-23 | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | N/A | 2023-08-28 | 2023-08-28 | Comments | 14 | Yes | Rev #2; JEB comments 8/14/23; KN no comments 8/23/23; ZFK no comments 8/23/23; PK no comments 8/23/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) CP | 2023-08-14 | 2023-08-14 | 2023-08-23 | N/A | N/A | N/A | N/A | 2023-08-23 | N/A | 2023-08-24 | 2023-08-24 | Comments | 10 | Yes | Rev #1; JEB no comments 8/23/23; AM no comments 8/23/23; KN comments 8/23/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) DR | 2023-08-14 | 2023-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | Comments | 10 | Yes | Rev #1
Mystic Oak | ENB | RP23-20 | Mystic Oak Ph 1, Blk 1&2 7 Lts | Shabeer Jaffar | JBS Engineering | Revised (Digital) CP | 2023-08-14 | 2023-08-14 | 2023-08-17 | N/A | N/A | N/A | N/A | 2023-08-15 | N/A | 2023-08-21 | 2023-08-21 | Approved | 7 | Yes | Rev #2; JEB no comments 8/15/23; MO no comments 8/17/23 (jls)
Reveille Estates Ph 1 | KCS | SQ23-08 | Reveille Estates Ph 1, Blk 1-4 32 Lts | B/CS Leasing | McClure & Browne | SQ Permit | 2023-08-14 | 2023-08-16 | N/A | N/A | 2023-08-17 | 2023-08-18 | 2023-08-18 | 2023-08-20 | 2023-08-18 | 2023-08-18 | 2023-08-18 | Comments | 4 | Yes | N/A
Reveille Estates Ph 2 | KCS | SQ23-09 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | SQ Permit | 2023-08-14 | 2023-08-16 | N/A | N/A | 2023-08-17 | 2023-08-18 | 2023-08-18 | 2023-08-20 | 2023-08-18 | 2023-08-18 | 2023-08-18 | Comments | 4 | Yes | N/A
Timber Oaks | ENB | FP22-18 | Timber Oaks Subd., Blk 5&6 57 Lts | Wall Development | Colliers Engineering/KFW | Revised (Digital) CP | 2023-08-15 | 2023-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | Approved | 2 | Yes | Rev #5
Tee Dr Townhomes | ENB | CU23-07 | Country Club Estates Ph 1, Blk D Lts 1R-6R | Optimal Housing Five LLC | J4 Engineering | Digital DR | 2023-08-16 | 2023-08-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | Comments | 9 | Yes | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) CP | 2023-08-23 | 2023-08-23 | 2023-08-30 | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | 2023-08-28 | 2023-09-06 | Comments | 14 | Yes | Rev #1; AM no comments 8/30/23; KN no comments 8/31/23 (jls)
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) EE | 2023-08-23 | 2023-08-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-09-06 | Comments | 14 | Yes | Rev #1
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) WL | 2023-08-23 | 2023-08-23 | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | 2023-08-28 | 2023-08-28 | Comments | 5 | Yes | Rev #1; KN no comments 8/31/23 (jls)
7 Brew Coffee | ZFK | SP23-21 | Texas-Villa Maria Retail, Lt 2 | Texas-Villa Maria Retail LP | Kirkman Engineering | Digital UR | 2023-08-24 | 2023-08-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | Approved | 4 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) DR | 2023-08-24 | 2023-08-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | Comments | 7 | Yes | Rev #1
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2023-08-29 | 2023-08-29 | UKN | N/A | N/A | N/A | N/A | 2023-09-05 | N/A | 2023-09-11 | 2023-09-11 | Comments | 12 | Yes | Rev #3; JEB no comments 9/1/23; KN comments 9/5/23 (jls)
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2023-08-29 | 2023-08-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Comments | 12 | Yes | N/A
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-08-29 | 2023-08-29 | UKN | N/A | N/A | N/A | N/A | 2023-09-05 | N/A | 2023-09-07 | 2023-09-07 | Comments | 8 | Yes | JEB no comments 9/1/23; KN no comments 9/5/23 (jls)
Reveille Estates Ph 2 | KCS | FP23-25 | Reveille Estates Ph 2, Blk 14&15 20 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) DL | 2023-08-29 | 2023-08-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Comments | 8 | Yes | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-08-29 | 2023-08-30 | 2023-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | Comments | 7 | Yes | AM no comments 8/30/23 (jls)
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised (Digital) CP | 2023-08-30 | 2023-08-30 | UKN | N/A | N/A | N/A | N/A | 2023-08-31 | N/A | 2023-09-06 | 2023-09-06 | Comments | 6 | Yes | Rev #4
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised (Digital) DL | 2023-08-30 | 2023-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | Comments | 6 | Yes | N/A
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Digital DL | 2023-08-30 | 2023-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Approved | 20 | No | N/A
Tee Dr Townhomes | ENB | RP23-34 | Country Club Estates Ph 1, Blk D Lts 1R-6R | Optimal Housing Five LLC | J4 Engineering | Digital CP | 2023-08-30 | 2023-08-31 | 2023-09-15 | N/A | N/A | N/A | N/A | 2023-09-14 | N/A | 2023-09-14 | 2023-09-14 | Comments | 14 | Yes | JEB no comments 8/31/23; AM no comments 9/15/23; ZFK no comments 9/15/23; KN comments 9/15/23 (jls)
Tee Dr Townhomes | ENB | RP23-34 | Country Club Estates Ph 1, Blk D Lts 1R-6R | Optimal Housing Five LLC | J4 Engineering | Digital EE | 2023-08-30 | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | Approved | 14 | Yes | N/A
Tee Dr Townhomes | ENB | RP23-34 | Country Club Estates Ph 1, Blk D Lts 1R-6R | Optimal Housing Five LLC | J4 Engineering | Revised (Digital) DR | 2023-08-30 | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | Approved | 14 | Yes | N/A
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Digital CP | 2023-08-31 | 2023-08-31 | 2023-09-11 | UKN | N/A | N/A | 2023-09-14 | 2023-09-14 | N/A | 2023-09-19 | 2023-09-19 | Comments | 19 | No | KF no comments 9/11/23; JEB comments 9/14/23; KN comments 9/14/23; ZFK no comments 9/14/23 (jls)
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Digital EE | 2023-08-31 | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | N/A | 2023-09-19 | 2023-09-19 | Comments | 19 | No | N/A
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Digital DR | 2023-08-31 | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Comments | 19 | No | N/A
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Digital SR | 2023-08-31 | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | N/A | 2023-09-19 | 2023-09-19 | Comments | 19 | No | N/A
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Digital WR | 2023-08-31 | 2023-08-31 | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | N/A | 2023-09-19 | 2023-09-19 | Comments | 19 | No | N/A
Starbucks | BMG | SP23-52 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Digital UL | 2023-09-01 | 2023-09-01 | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | N/A | 2023-09-19 | 2023-09-20 | Approved | 19 | No | No comments from JEB (bmg)
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Digital CP | 2023-09-06 | 2023-09-06 | 2023-09-15 | N/A | N/A | N/A | N/A | 2023-09-22 | N/A | 2023-09-13 | 2023-09-13 | Comments | 7 | Yes | Rev #2; AM no comments 9/15/23; KN no comments 9/21/23; JEB no comments 9/22/23 (jls)
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | SQ Permit | 2023-09-06 | 2023-09-08 | N/A | N/A | 2023-09-08 | N/A | 2023-09-11 | N/A | N/A | 2023-09-13 | 2023-09-13 | Comments | 7 | Yes | No longer req per BMG
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) CP | 2023-09-08 | 2023-09-08 | UKN | N/A | N/A | N/A | N/A | 2023-09-08 | N/A | 2023-09-12 | 2023-09-12 | Comments | 4 | Yes | Rev #3; JEB comments 9/8/23 (jls)
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) EE | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Comments | 4 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) DR | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Comments | 4 | Yes | N/A
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) CP | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Approved | 7 | Yes | Rev #3
Yaupon Trails Ph 3A & 4A | KCS | FP23-17 | Yaupon Trails Ph 3A & 4A Blk 9&11 65 lts | 1983 Land Investments LLC | Schultz Engineering | Revised (Digital) EE | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Approved | 7 | Yes | Rev #3
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Revised (Digital) CP | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | N/A | 2023-09-15 | 2023-09-15 | Comments | 7 | Yes | Rev #2; JEB comments 9/14/23 (jls)
Yaupon Trails Ph 3B | KCS | FP23-23 | Yaupon Trails Ph 3B, Blk 7 Lts 7-31 | Ranier & Son Development | Schultz Engineering | Revised (Digital) EE | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Comments | 7 | Yes | Rev #2
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Revised (Digital) CP | 2023-09-08 | 2023-09-08 | UKN | N/A | N/A | N/A | N/A | 2023-09-22 | N/A | 2023-09-26 | 2023-09-26 | Approved | 18 | No | Rev #2; KN no comments 9/21/23; JEB no comments 9/22/23 (jls)
Yaupon Trails Ph 4B & 5A | KCS | FP23-24 | Yaupon Trails Ph 4B & 5A, Blk 9 Lts 89-127 | Ranier & Son Development | Schultz Engineering | Revised (Digital) EE | 2023-09-08 | 2023-09-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Approved | 18 | No | Rev #2
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) CP | 2023-09-11 | 2023-09-11 | UKN | N/A | N/A | N/A | N/A | 2023-09-21 | N/A | 2023-09-26 | 2023-09-26 | Comments | 15 | No | Rev #4; JEB no comments 9/13/23; KN no comments 9/21/23 (jls)
Austin's Colony Ph 22B & 23A | KCS | FP22-20 | Austin's Colony Ph 22B & 23A, Blk 5-11 78 Lts | Carrabba Family Ltd Partnership | J4 Engineering | Revised (Digital) DR | 2023-09-11 | 2023-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 15 | No | N/A
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Digital CP | 2023-09-12 | 2023-09-12 | 2023-09-14 | UKN | N/A | N/A | 2023-09-15 | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 14 | Yes | KF no comments 9/14/23; ZFK no comments 9/15/23; KN comments 9/26/23 (jls)
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Digital EE | 2023-09-12 | 2023-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 14 | Yes | N/A
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Digital WR | 2023-09-12 | 2023-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 14 | Yes | N/A
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Digital SR | 2023-09-12 | 2023-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 14 | Yes | N/A
Chicken Oil Co | ENB | SP23-39 | J E Scott Survey, Blk 6 Lt 19 | Dixie Chicken | Schultz Engineering | Revised (Digital) CP | 2023-09-13 | 2023-09-13 | 2023-09-15 | N/A | N/A | N/A | N/A | 2023-09-20 | N/A | 2023-09-20 | 2023-09-25 | Approved | 12 | Yes | Rev #1; JEB no comments 9/13/23; AM no comments 9/15/23; KN comments 9/20/23 (jls); KN comments addressed in newest CP (enb)
Chicken Oil Co | ENB | SP23-39 | J E Scott Survey, Blk 6 Lt 19 | Dixie Chicken | Schultz Engineering | Revised (Digital) EE | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-25 | Approved | 12 | Yes | Rev #1
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Digital CP | 2023-09-13 | 2023-09-13 | UKN | UKN | N/A | N/A | 2023-09-15 | 2023-09-13 | N/A | 2023-09-19 | 2023-09-26 | Comments | 13 | Yes | Original submission recv'd 9/5/23, waited for EE (jls); JEB comments 9/13/23; ZFK comments 9/15/23 (jls)
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Digital DR | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-26 | Comments | 13 | Yes | N/A
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Digital EE | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-26 | Comments | 13 | Yes | N/A
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A, Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | N/A | 2023-09-26 | 2023-09-26 | Comments | 13 | Yes | Rev #1; JEB comments 9/14/23; KN no comments 9/20/23(jls)
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A, Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 13 | Yes | Rev #1
Oakmont Ph 4C | KCS | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Digital CP | 2023-09-13 | 2023-09-13 | N/A | UKN | N/A | N/A | 2023-09-15 | 2023-09-26 | N/A | 2023-09-27 | 2023-09-27 | Comments | 14 | Yes | JEB comments 9/14/23; ZFK comments 9/15/23; KN comments 9/26/23 (jls)
Oakmont Ph 4C | KCS | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Digital EE | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-27 | 2023-09-27 | Comments | 14 | Yes | N/A
Oakmont Ph 4C | KCS | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Digital WL | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-27 | 2023-09-27 | Comments | 14 | Yes | N/A
Oakmont Ph 4C | KCS | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Digital SL | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-27 | 2023-09-27 | Comments | 14 | Yes | N/A
Oakmont Ph 4C | KCS | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Digital DR | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Comments | 14 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) CP | 2023-09-13 | 2023-09-13 | 2023-09-26 | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-26 | 2023-09-26 | Comments | 13 | Yes | Rev #4, JEB comments 9/13/23; KN & MO comments 9/26/23 (jls)
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) EE | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 13 | Yes | Rev #4
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) DR | 2023-09-13 | 2023-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | Comments | 13 | Yes | Rev #4
Fairway Dr Townhomes | BMG | CU23-09 | Country Club Estates Ph 1, Blk D Lts 1&2 | Optimal Housing Five LLC | J4 Engineering | Digital CP | 2023-09-14 | 2023-09-14 | UKN | UKN | N/A | N/A | 2023-09-15 | 2023-09-18 | N/A | 2023-10-04 | 2023-10-04 | Comments | 20 | No | ZFK comments 9/15/23; JEB comments 9/18/23 (jls)
Fairway Dr Townhomes | BMG | CU23-09 | Country Club Estates Ph 1, Blk D Lts 1&2 | Optimal Housing Five LLC | J4 Engineering | Digital EE | 2023-09-14 | 2023-09-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Comments | 20 | No | N/A
Fairway Dr Townhomes | BMG | CU23-09 | Country Club Estates Ph 1, Blk D Lts 1&2 | Optimal Housing Five LLC | J4 Engineering | Digital DL | 2023-09-14 | 2023-09-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Comments | 20 | No | N/A
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) CP | 2023-09-15 | 2023-09-18 | 2023-09-26 | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-27 | 2023-09-27 | Comments | 12 | Yes | KN comments 9/26/23; AM no comments 9/26/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) DR | 2023-09-15 | 2023-09-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Comments | 12 | Yes | N/A
Douglass Mitsubishi | BMG | SP23-18 | Garlyn Shelton Imports, Lt 1R | N Douglas Investments | JBS Engineering | Revised (Digital) DL | 2023-09-19 | 2023-09-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-26 | Comments | 7 | Yes | Rev #1; Notification of no further comments to be sent w/ SDRC notification/TxDOT has add'l comments (BMG)
CREI Storage | ENB | SP23-58 | Progress Park Ph 2, Blk 2 Lt 3 | CREI Storage 1820 Owner LP | J4 Engineering | Revised (Digital) CP | 2023-09-19 | 2023-09-19 | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | N/A | 2023-09-20 | 2023-09-20 | Approved | 1 | Yes | Rev #1; JEB met w/ J4 & Developer - WL was changed to private, eliminated public infrastructure; Submittal was for JEB to review changes prev. discussed & finalize; JEB no comments 9/19/23 (jls)
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) FIR | 2023-09-19 | 2023-09-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | Comments | 14 | Yes | N/A
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-09-20 | 2023-09-20 | 2023-09-26 | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-10-02 | 2023-10-02 | Comments | 12 | Yes | Rev#10; KN comments 9/26/2023
Tee Dr Townhomes | ENB | RP23-34 | Country Club Estates Ph 1, Blk D Lts 1R-6R | Optimal Housing Five LLC | J4 Engineering | Revised (Digital) CP | 2023-09-20 | 2023-09-20 | 2023-09-26 | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-20 | 2023-09-20 | Approved | 0 | Yes | Rev #2; JEB no comments 9/20/23; KN comments 9/26/23; AM no comments 9/26/23 (jls)
Starbucks | BMG | SP23-52 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Digital DL | 2023-09-20 | 2023-09-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | Comments | 0 | Yes | N/A
West Brazos Animal Clinic | BMG | SP23-59 | Windmill Park Subd., Blk 18 Lts 1&2 | 5J Land & Development LLC | Schultz Engineering | Digital DL | 2023-09-20 | 2023-09-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-26 | Comments | 6 | Yes | Comments sent w/ SDRC notification (BMG)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) CP | 2023-09-20 | 2023-09-20 | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | N/A | 2023-09-21 | 2023-09-21 | Comments | 1 | Yes | Rev #2; JEB comments 9/22/23; KN comments 9/26/23 (jls). Design engineer submitted prior to receiving verbal feedback on 9/21/23 after COB S&D dept surveyed site & spoke w/ COB engineering on desired change of storm infrastructure design. Disregard as storm piping is to change significantly from this design submittal. (KCS)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) DR | 2023-09-20 | 2023-09-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Comments | 2 | Yes | Rev #2; Design engineer submitted prior to receiving verbal feedback on 9/21/23 after COB S&D dept surveyed site & spoke w/ COB engineering on desired change of storm infrastructure design. Disregard as storm piping is to change significantly from this design submittal. (KCS)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) EE | 2023-09-20 | 2023-09-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-23 | 2023-09-23 | Comments | 3 | Yes | Rev #2
Starbucks | BMG | SP23-52 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Digital DL | 2023-09-28 | 2023-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Comments | 6 | Yes | Forwarded to TxDOT 10/4 (bmg)
Crossway Auto Center | ZFK | SP22-61 | Progress Park Ph 2, Blk 2 Lt 5 | Michael Kelly | Miguel Alvarado | Digital UL | 2023-10-03 | 2023-10-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Comments | 14 | Yes | Fire flow test for private hydrant needs to be conducted per standards
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) CP | 2023-10-04 | 2023-10-04 | 2023-10-06 | N/A | N/A | N/A | N/A | 2023-10-06 | N/A | 2023-10-12 | 2023-10-13 | Comments | 9 | Yes | Rev #3; KN no comments 10/6/23; AM no comments 10/6/23; JEB no comments 10/6/23 (jls)
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) EE | 2023-10-04 | 2023-10-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-13 | Comments | 9 | Yes | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) WL | 2023-10-04 | 2023-10-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-13 | Comments | 9 | Yes | N/A
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A, Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) CP | 2023-10-05 | 2023-10-05 | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | N/A | 2023-10-11 | 2023-10-11 | Comments | 6 | Yes | Rev #2; KN no comments 10/6/23 (jls)
Oakmont Ph 4A | KCS | FP22-41 | Oakmont Ph 4A, Blk 1&2 38 Lts | Adam Development Properties LP | McClure & Browne | Revised (Digital) DR | 2023-10-05 | 2023-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Comments | 6 | Yes | Rev #2
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Revised (Digital) CP | 2023-10-06 | 2023-10-13 | UKN | N/A | N/A | N/A | N/A | 2023-10-20 | N/A | 2023-10-20 | 2023-10-20 | Comments | 14 | Yes | Rev #1; JEB comments 10/16/23 (dms); ZFK no comments 10/20/23
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Revised (Digital) EE | 2023-10-06 | 2023-10-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | Comments | 14 | Yes | Rev #1
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Revised (Digital) DR | 2023-10-06 | 2023-10-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | Comments | 14 | Yes | Rev #1
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-10-11 | 2023-10-11 | 2023-10-12 | N/A | N/A | N/A | N/A | 2023-10-13 | N/A | 2023-10-16 | 2023-10-17 | Comments | 6 | Yes | Rev #10; JEB no comments 10/11/23; AM no comments 10/12/23; KN comments 10/13/23 (jls)
Fuel Station | BMG | SP23-63 | Midway Place Add'n, Blk 1 Lt 1R | El Elohim LLC | Mitchell & Morgan | Digital DL | 2023-10-11 | 2023-10-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-13 | Comments | 2 | Yes | N/A
Rock Pointe Ph 2 | ZFK | FP23-34 | Rock Pointe Ph 2, Blk 1 2 & 4 27 Lts | Brackmel Development LLC | J4 Engineering | Digital CP | 2023-10-12 | 2023-10-12 | 2023-10-16 | UKN | N/A | N/A | N/A | 2023-10-17 | N/A | 2023-10-25 | 2023-10-26 | Comments | 14 | Yes | JEB comments 10/16/23 (dms); KF no comments 10/17/23 (jls)
Rock Pointe Ph 2 | ZFK | FP23-34 | Rock Pointe Ph 2, Blk 1 2 & 4 27 Lts | Brackmel Development LLC | J4 Engineering | Digital EE | 2023-10-12 | 2023-10-12 | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | N/A | 2023-10-25 | 2023-10-26 | Comments | 14 | Yes | JEB comments on 10/16/23 (dms)
Rock Pointe Ph 2 | ZFK | FP23-34 | Rock Pointe Ph 2, Blk 1 2 & 4 27 Lts | Brackmel Development LLC | J4 Engineering | Digital DR | 2023-10-12 | 2023-10-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-26 | Approved | 14 | Yes | No comments
West Brazos Animal Clinic | BMG | SP23-59 | Windmill Park Subd., Blk 18 Lts 1&2 | 5J Land & Development LLC | Schultz Engineering | Revised (Digital) DL | 2023-10-16 | 2023-10-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | Approved | 4 | Yes | Rev #1
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) CP | 2023-10-18 | 2023-10-18 | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | N/A | 2023-10-31 | 2023-10-31 | Comments | 13 | Yes | JEB no comments 10/23/26; KN no comments 10/31/23 (jls)
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) WL | 2023-10-18 | 2023-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Approved | 13 | Yes | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) DL | 2023-10-18 | 2023-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Comments | 13 | Yes | N/A
SMBG Midtown Park | BMG | SP23-50 | Country Club Lake Add'n, Blk 1 Lt 2 | SMBG Bryan | Walker Partners | Revised (Digital) EE | 2023-10-18 | 2023-10-18 | UKN | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Comments | 13 | Yes | N/A
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Digital CP | 2023-10-19 | 2023-10-19 | 2023-10-23 | UKN | N/A | N/A | N/A | 2023-10-31 | N/A | 2023-11-08 | 2023-11-08 | Comments | 20 | No | KF no comments 10/23/23 (jls), Comments from Fire 11/08/23
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Digital EE | 2023-10-19 | 2023-10-19 | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | N/A | 2023-11-08 | 2023-11-08 | Comments | 20 | No | Digital copy submitted 10/18/23; Waited for full Construction Plan Set (jls); KN comments 10/30/23 (dms); JEB no comments 10/31/23 (jls)
Reveille Park Ph 1 | KCS | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Digital CP | 2023-10-20 | 2023-10-25 | N/A | UKN | N/A | N/A | 2023-10-27 | 2023-10-27 | N/A | 2023-11-01 | 2023-11-01 | Comments | 12 | Yes | Digital copy submitted 10/20/23; Waited for Final Plat submittal and SDRC; JEB comments 10/27/23; KN comments 11/6/23 (jls)
Reveille Park Ph 1 | KCS | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Digital EE | 2023-10-20 | 2023-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | Comments | 12 | Yes | N/A
Pre-School Parking | ENB | SP23-70 | Bryan Original Townsite, Blk 232 | SOYYO LLC | McClure & Browne | Digital CP | 2023-10-23 | 2023-10-23 | 2023-10-24 | N/A | N/A | N/A | 2023-11-02 | 2023-10-23 | N/A | 2023-10-27 | 2023-10-27 | Approved | 4 | Yes | JEB no comments 10/23/26; KF no comments 10/24/23; ZFK no comments 11/2/23 (jls)
Pre-School Parking | ENB | SP23-70 | Bryan Original Townsite, Blk 232 | SOYYO LLC | McClure & Browne | Digital EE | 2023-10-23 | 2023-10-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | Approved | 4 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) CP | 2023-10-23 | 2023-10-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Approved | 8 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) EE | 2023-10-23 | 2023-10-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Approved | 8 | Yes | N/A
Red River Townhomes | KCS | RP23-24 | Briar Meadows Creek Ph 5, Blk 4 Lts 1R-11 | The Ben Brown Group | Bleyl Engineering | Revised (Digital) DR | 2023-10-23 | 2023-10-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Approved | 8 | Yes | N/A
Northern Tools | BMG | RP23-33 | Boonville Town Center, Blk 2, Lt 2A-2R | Horton TX | Brittain & Crawford | Revised (Digital) CP | 2023-10-24 | 2023-10-24 | 2023-10-26 | N/A | N/A | N/A | N/A | 2023-10-26 | N/A | 2023-10-26 | 2023-10-26 | Approved | 2 | Yes | Rev #2; WS made comments after pre-con mtg; plan sheet submitted specifically to address a single issue; JEB no comments 10/25/23; KN no comments 10/26/23; PK no comments 10/26/23 (jls)
Blinn Admin Bldg | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-10-25 | 2023-10-25 | UKN | N/A | N/A | N/A | N/A | 2023-10-31 | N/A | 2023-11-01 | 2023-11-01 | Approved | 7 | Yes | Rev #11; KN no comments 10/31/23 (jls)
2818 Business Park | KCS | SQ23-11 | 2818 Business Park, Blk 1 Lt 1 | 2818 Investments | Schultz Engineering | SQ Permit | 2023-10-25 | 2023-10-25 | N/A | N/A | 2023-10-30 | 2023-10-30 | 2023-10-25 | 2023-10-25 | 2023-10-26 | 2023-11-02 | 2023-11-02 | Comments | 8 | Yes | N/A
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) DR | 2023-10-25 | 2023-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Comments | 6 | Yes | Rev #5
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) CP | 2023-10-25 | 2023-10-25 | 2023-10-26 | N/A | N/A | N/A | 2023-10-30 | 2023-10-27 | N/A | 2023-10-31 | 2023-10-31 | Comments | 6 | Yes | Rev #5; AM no comments 10/26/23; JEB no comments 10/27/23; KN comments 10/27/23; ZFK comments 10/30/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) EE | 2023-10-25 | 2023-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Comments | 6 | Yes | Rev #5
Twelve Oaks Reserve | KCS | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | Digital CP | 2023-10-26 | 2023-10-26 | 2023-10-31 | UKN | N/A | N/A | 2023-11-06 | 2023-11-06 | N/A | 2023-11-08 | 2023-11-08 | Comments | 13 | Yes | Digital copy submitted 10/25/23; Waited for Engineer's Estimate; JEB comments 10/31/23; KF comments 10/31/23; ZFK comments 11/6/23; KN commments 11/6/23 (jls)
Twelve Oaks Reserve | KCS | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | Digital EE | 2023-10-26 | 2023-10-26 | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | N/A | 2023-11-08 | 2023-11-08 | Comments | 13 | Yes | N/A
Stella Ranch Ph 1 | KCS | SQ23-12 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | SQ Permit | 2023-11-01 | 2023-11-01 | N/A | N/A | 2023-11-01 | 2023-11-07 | 2023-11-07 | 2023-11-01 | 2023-11-07 | 2023-11-08 | 2023-11-08 | Comments | 7 | Yes | N/A
Hardy Street Parking Lot | BMG | SP22-67 | Suber's Ph 5, Blk 2 Lt 10 | Catholic Diocese of Austin TX | Gessner Engineering | Digital DL | 2023-11-02 | 2023-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | Comments | 15 | No | N/A
Rock Pointe Ph 2 | ZFK | FP23-34 | Rock Pointe Ph 2, Blk 1 2 & 4 27 Lts | Brackmel Development LLC | J4 Engineering | Digital CP | 2023-11-02 | 2023-11-02 | UKN | N/A | N/A | N/A | N/A | 2023-11-08 | N/A | 2023-11-14 | 2023-11-14 | Comments | 12 | Yes | Rev #2
Rock Pointe Ph 2 | ZFK | FP23-34 | Rock Pointe Ph 2, Blk 1 2 & 4 27 Lts | Brackmel Development LLC | J4 Engineering | Digital EE | 2023-11-02 | 2023-11-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Approved | 12 | Yes | N/A
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised (Digital) CP | 2023-11-03 | 2023-11-03 | 2023-11-07 | N/A | N/A | N/A | N/A | 2023-11-07 | N/A | 2023-11-15 | 2023-11-15 | Comments | 12 | Yes | Rev #1; JEB comments 11/7/23; KF no comments 11/7/23 (jls)
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised (Digital) DR | 2023-11-03 | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | Comments | 12 | Yes | Rev #1; Digital copy submitted on 11/3/23, but some files blocked by COB email filter; Issue resolved 11/6/23 (jls).
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) CP | 2023-11-06 | 2023-11-06 | UKN | N/A | N/A | N/A | N/A | 2023-11-08 | N/A | 2023-11-10 | 2023-11-10 | Comments | 4 | Yes | Rev #4; JEB no comments 11/6/23; KN comments 11/8/23 (jls)
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) EE | 2023-11-06 | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | Approved | 4 | Yes | No comments
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) CP | 2023-11-06 | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | N/A | 2023-11-09 | 2023-11-09 | Approved | 3 | Yes | Rev #4; JEB no comments 11/7/23; KN comments 11/8/23 (jls)
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) EE | 2023-11-06 | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Approved | 3 | Yes | Rev #4
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) DR | 2023-11-06 | 2023-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Approved | 3 | Yes | Rev #4
Gourd Creek Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Digital CP | 2023-11-06 | 2023-11-09 | UKN | UKN | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-27 | 2023-11-27 | Comments | 21 | No | Digital copy submitted 11/6/23; Waited for Final Plat submittal; Waited on Engineer's Estimate; JEB comments 11/13/23; KN comments 11/21/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) CP | 2023-11-08 | 2023-11-08 | UKN | N/A | N/A | N/A | 2023-11-14 | 2023-11-09 | N/A | 2023-11-14 | 2023-11-14 | Approved | 6 | Yes | Rev #6; JEB no comments 11/9/23; ZFK no comments 11/14/23 (jls)
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) DR | 2023-11-08 | 2023-11-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Approved | 6 | Yes | Rev #6
TXB C-Store/Gas Station | BMG | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised (Digital) EE | 2023-11-08 | 2023-11-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Approved | 6 | Yes | Rev #6
Shiloh Dr Ind'l Bldg | ENB | SP23-60 | Brazos County Ind'l Pk Ph 3, Blk 1 Lt 5 | HPAM Capital Partners | McClure & Browne | Digital DR | 2023-11-08 | 2023-11-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-21 | Comments | 13 | Yes | N/A
Gourd Creek Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Digital EE | 2023-11-09 | 2023-11-09 | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-27 | 2023-11-27 | Approved | 14 | Yes | JEB comments 11/13/23; KN comments 11/21/23 (jls)
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised (Digital) CP | 2023-11-10 | 2023-11-10 | 2023-11-14 | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-28 | 2023-11-28 | Comments | 18 | No | Rev #1; KF no comments 11/14/23; KN comments 11/21/2023 (jls)
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Revised (Digital) CP | 2023-11-10 | 2023-11-10 | 2023-11-14 | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-21 | 2023-11-21 | Comments | 11 | Yes | Rev #1; KF no comments 11/14/23; KN comments 11/21/23 (jls)
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Digital WR | 2023-11-10 | 2023-11-10 | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-21 | 2023-11-21 | Comments | 11 | Yes | N/A
Opifex | ENB | SP23-68 | Park Heights Add'n, Lts 6-8 | Vaughn Development | Sam Thomas | Digital DR | 2023-11-15 | 2023-11-15 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2023-11-28 | Comments | 11 | Yes | N/A
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) EE | 2023-11-15 | 2023-11-15 | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-28 | 2023-11-28 | Comments | 9 | Yes | Rev #3; JEB comments 11/16/23; KN comments 11/21/23 (dms)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) CP | 2023-11-15 | 2023-11-15 | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-21 | N/A | 2023-11-28 | 2023-11-28 | Comments | 9 | Yes | Rev #3; JEB comments 11/16/23; KN comments 11/21/23 (dms)
4611 Winding Creek Rd | KCS | SQ23-13 | Maria Kegan | Sony New Homes LLC | Schultz Engineering | SQ Permit | 2023-11-16 | 2023-11-27 | N/A | N/A | 2023-11-30 | UKN | 2023-11-29 | 2023-11-27 | 2023-11-30 | 2023-11-30 | 2023-11-30 | Comments | 10 | Yes | N/A
Rock Pointe Ph 2 | ZFK | FP23-34 | Rock Pointe Ph 2, Blk 1 2 & 4 27 Lts | Brackmel Development LLC | J4 Engineering | Revised (Digital) CP | 2023-11-17 | 2023-11-17 | 2023-11-20 | N/A | N/A | N/A | N/A | 2023-11-21 | N/A | 2023-11-28 | 2023-11-28 | Approved | 7 | Yes | Rev #2; JEB no comments 11/17/23; KF no comments 11/20/23; KN no comments 11/21/23 (jls)
Fuel Station | BMG | SP23-63 | Midway Place Add'n, Blk 1 Lt 1R | El Elohim LLC | Mitchell & Morgan | Digital DL | 2023-11-17 | 2023-11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | Comments | 6 | Yes | Rev #1
Reveille Park Ph 1 | KCS | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-11-20 | 2023-11-20 | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | N/A | 2023-11-29 | 2023-11-29 | Comments | 5 | Yes | Rev #1; KN comments 11/21/23; JEB comments 11/22/23 (jls)
Texas Ave C-Store | KCS | SP22-13 | Bice Add'n, Lt 1 | Brazos Food Mart LLC | J4 Engineering | Revised (Digital) CP | 2023-11-21 | 2023-11-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Approved | 3 | Yes | Plans tentatively approved, but not stamped due to previous submittal missing a detail sheet. Resubmitted with missing sheet for approval (jls)
Nash St Signal Poles | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-11-21 | 2023-11-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Comments | 11 | Yes | N/A
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) CP | 2023-11-22 | 2023-11-22 | 2023-11-30 | N/A | N/A | N/A | N/A | 2023-12-01 | N/A | 2023-12-04 | 2023-12-04 | Comments | 6 | Yes | Rev #1; KF no comments 11/30/23; KN comments 12/1/23; JEB comments 12/1/23 (jls)
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) DR | 2023-11-22 | 2023-11-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Comments | 6 | Yes | Rev #1
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Digital DR | 2023-11-27 | 2023-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | Comments | 14 | Yes | N/A
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Digital SR | 2023-11-27 | 2023-11-28 | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | N/A | 2023-12-11 | 2023-12-11 | Comments | 14 | Yes | JEB comments 11/30/23; KN comments 12/6/23 (jls)
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Digital EE | 2023-11-27 | 2023-11-28 | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | N/A | 2023-12-11 | 2023-12-11 | Comments | 14 | Yes | JEB comments 11/30/23; KN comments 12/6/23 (jls)
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Digital CP | 2023-11-27 | 2023-11-28 | UKN | UKN | N/A | N/A | N/A | 2023-12-06 | N/A | 2023-12-11 | 2023-12-11 | Comments | 14 | Yes | JEB comments 11/30/23; KN comments 12/6/23 (jls)
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) FIR | 2023-11-28 | 2023-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-05 | 2023-12-05 | Comments | 7 | Yes | Rev #1
Shiloh Dr Ind'l Bldg | ENB | SP23-60 | Brazos County Ind'l Pk Ph 3, Blk 1 Lt 5 | HPAM Capital Partners | McClure & Browne | Revised (Digital) DR | 2023-11-28 | 2023-11-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | Approved | 10 | Yes | Rev #1
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | McClure & Browne | Digital CP | 2023-11-29 | 2023-11-29 | UKN | UKN | N/A | N/A | 2023-12-12 | 2023-12-14 | N/A | 2023-12-14 | 2023-12-14 | Comments | 15 | No | JEB comments 11/29/23; ZFK no comments 12/12/23; KN comments 12/14/23 (jls)
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | McClure & Browne | Digital EE | 2023-11-29 | 2023-11-29 | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | N/A | 2023-12-14 | 2023-12-14 | Comments | 15 | No | N/A
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | McClure & Browne | Digital DR | 2023-11-29 | 2023-11-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Comments | 15 | No | N/A
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | McClure & Browne | Digital WR | 2023-11-29 | 2023-11-29 | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | N/A | 2023-12-14 | 2023-12-14 | Comments | 15 | No | N/A
Reveille Park Ph 1 | KCS | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised (Digital) CP | 2023-11-30 | 2023-11-30 | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | N/A | 2023-12-06 | 2023-12-06 | Comments | 6 | Yes | Rev #2; KN comments 12/6/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) CP | 2023-11-30 | 2023-11-30 | UKN | N/A | N/A | N/A | N/A | 2023-12-11 | N/A | 2023-12-14 | 2023-12-14 | Comments | 14 | Yes | Rev #4; JEB no comments 11/30/23; KN no comments 12/11/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) DR | 2023-11-30 | 2023-11-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Comments | 14 | Yes | Rev #4
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | McClure & Browne | TxDOT Permit | 2023-12-01 | 2023-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-06 | Emailed to TxDOT | 5 | Yes | N/A
Stella Ranch Ph 1 | KCS | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | Digital CP | 2023-12-06 | 2023-12-07 | UKN | UKN | N/A | N/A | 2023-12-18 | 2023-12-19 | N/A | 2024-01-03 | 2024-01-03 | Comments | 20 | No | Digital copy submitted 11/29/23; Waited for Final Plat to be scheduled for SDRC (jls); ZFK comments 12/18/2023; KN comments 12/19/23; JEB comments 12/19/23 (jls)
Fuel Station | BMG | SP23-63 | Midway Place Add'n, Blk 1 Lt 1R | El Elohim LLC | Mitchell & Morgan | Revised (Digital) DL | 2023-12-06 | 2023-12-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-12 | Approved | 6 | Yes | Rev #2
Fuel Station | BMG | SP23-63 | Midway Place Add'n, Blk 1 Lt 1R | El Elohim LLC | Mitchell & Morgan | TxDOT Permit | 2023-12-06 | 2023-12-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-13 | Emailed to TxDOT | 7 | Yes | N/A
Stella Ranch Ph 1 | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) CP | 2023-12-06 | 2023-12-06 | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | N/A | 2023-12-14 | 2023-12-14 | Comments | 8 | Yes | Rev #2; KN comments 12/15/23 (jls)
Stella Ranch Ph 1 | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) EE | 2023-12-06 | 2023-12-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Comments | 8 | Yes | Rev #2
Stella Ranch Ph 1 | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) DR | 2023-12-06 | 2023-12-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Comments | 8 | Yes | Rev #2
Stella Ranch Ph 1 | BMG | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Digital CP | 2023-12-06 | 2023-12-06 | UKN | UKN | N/A | N/A | 2023-12-18 | 2023-12-19 | N/A | 2023-12-18 | 2023-12-19 | Comments | 13 | Yes | JEB comments 12/7/23 (jls); ZFK no comments 12/7/23; KN comments 12/19/23 (jls)
Stella Ranch Ph 1 | BMG | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Digital EE | 2023-12-06 | 2023-12-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-19 | Comments | 13 | Yes | JEB comments 12/7/23 (jls)
Stella Ranch Ph 1 | BMG | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Digital DR | 2023-12-06 | 2023-12-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-19 | Comments | 13 | Yes | N/A
Stella Ranch Ph 1 | ENB | RZ23-30 | J W Scott League | Adam Development Properties LP | Kimley-Horn & Assoc | Digital TIA | 2023-12-06 | 2023-12-07 | N/A | N/A | N/A | N/A | 2023-12-21 | N/A | N/A | 2023-12-21 | 2023-12-21 | Comments | 7 | Yes | ZFK comments 12/21/23 (jls)
Stella Ranch Ph 1 | ENB | RZ23-30 | J W Scott League | Adam Development Properties LP | Kimley-Horn & Assoc | Flood Study | 2023-12-06 | 2023-12-07 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-12 | 2024-01-12 | Comments | 28 | No | ENB waiting for SJV to complete comments; hope to have week of 1/8/24 (jls)
Stella Ranch Ph 1 | KCS | SQ23-14 | Reveille Park Ph 1, Blk 1-4 34 Lts | BCS Leasing LLC | McClure & Browne | SQ Permit | 2023-12-06 | 2023-12-11 | N/A | N/A | 2023-12-11 | UKN | 2023-12-12 | 2023-12-11 | UKN | 2023-12-13 | 2023-12-13 | Approved | 7 | Yes | N/A
Stella Ranch Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Revised (Digital) CP | 2023-12-07 | 2023-12-07 | 2023-12-11 | N/A | N/A | N/A | N/A | 2023-12-19 | N/A | 2023-12-21 | 2023-12-21 | Comments | 14 | Yes | KF comments 12/11/23; JEB comments 12/8/23; KN comments 12/19/23 (jls)
Stella Ranch Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Digital DR | 2023-12-07 | 2023-12-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | Approved | 14 | Yes | N/A
Stella Ranch Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Digital WR | 2023-12-07 | 2023-12-07 | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | N/A | 2023-12-21 | 2023-12-21 | Approved | 14 | Yes | N/A
Stella Ranch Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Digital SR | 2023-12-07 | 2023-12-07 | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | N/A | 2023-12-21 | 2023-12-21 | Comments | 14 | Yes | N/A
Stella Ranch Ph 1 | KCS | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | Digital EE | 2023-12-08 | 2023-12-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | Comments | 18 | No | N/A
Pre-School Parking | ENB | SP23-70 | Bryan Original Townsite, Blk 232 | SOYYO LLC | McClure & Browne | TxDOT Permit | 2023-12-11 | 2023-12-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-12 | Emailed to TxDOT | 1 | Yes | N/A
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised (Digital) CP | 2023-12-12 | 2023-12-12 | UKN | N/A | N/A | N/A | N/A | 2023-12-14 | N/A | 2023-12-18 | 2023-12-18 | Comments | 6 | Yes | Rev #2; JEB comments 12/12/23; KN comments 12/14/23 (jls)
Hardy Street Parking Lot | BMG | SP22-67 | Suber's Ph 5, Blk 2 Lt 10 | Catholic Diocese of Austin TX | Gessner Engineering | Revised (Digital) DL | 2023-12-12 | 2023-12-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Comments | 10 | Yes | Rev #1
Oaks on Riverside | KCS | SP23-30 | Oak Creek Ranch, Blk 1 Lt 1 | Oaks at Jones Rd | Mitchell & Morgan | Revised (Digital) CP | 2023-12-14 | 2023-12-14 | 2023-12-15 | N/A | N/A | N/A | N/A | 2023-12-15 | N/A | 2023-12-15 | 2023-12-15 | Approved | 1 | Yes | Rev #3; KF no comments 12/15/23; KN comments 12/15/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) CP | 2023-12-15 | 2023-12-15 | UKN | N/A | N/A | N/A | N/A | 2023-12-20 | N/A | 2023-12-21 | 2023-12-21 | Comments | 6 | Yes | JEB no comments 12/15/23; KN no comments 12/20/23 (jls)
Pattern Flex Homes | KCS | SP23-38 | Dellwood Park, Blk 8 Lt 1 | Old Town Builders | J4 Engineering | Revised (Digital) DR | 2023-12-15 | 2023-12-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | Comments | 6 | Yes | N/A
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised (Digital) CP | 2023-12-18 | 2023-12-18 | UKN | N/A | N/A | N/A | N/A | 2023-12-18 | N/A | 2023-12-21 | 2023-12-21 | Approved | 3 | Yes | Approval email being held until SDRC approval achieved
Nash St Signal Poles | ZFK | SP23-04 | Blinn College Subd., Blk 1 Lt 1R-R | Blinn College District | Garza EMC | Revised (Digital) CP | 2023-12-18 | 2023-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Approved | 11 | Yes | Rev #1
Opifex | ENB | SP23-68 | Park Heights Add'n, Lts 6-8 | Vaughn Development | Sam Thomas | Revised (Digital) DR | 2023-12-20 | 2023-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | Comments | 14 | Yes | Rev #1
Pleasant Hill Sec 3 Ph 2 | KCS | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised (Digital) CP | 2023-12-20 | 2023-12-20 | 2023-12-21 | N/A | N/A | N/A | N/A | 2023-12-28 | N/A | 2024-01-04 | 2024-01-04 | Comments | 8 | Yes | Rev #2; KF no comments 12/21/23 (jls); JEB & KN comments 12/28/23 (dms)
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised (Digital) CP | 2023-12-20 | 2023-12-20 | 2023-12-21 | N/A | N/A | N/A | N/A | 2023-12-28 | N/A | 2024-01-04 | 2024-01-04 | Comments | 12 | Yes | Rev #3; KF no comments 12/21/23 (jls); KN comments 12/28/23 (dms);
Pleasant Hill Sec 3 Ph 1 | KCS | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised (Digital) DR | 2023-12-20 | 2023-12-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Comments | 12 | Yes | Rev #3
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Revised (Digital) CP | 2023-12-27 | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | Comments | 12 | Yes | Rev #2
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Digital WR | 2023-12-27 | 2023-12-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | Comments | 12 | Yes | Rev #2
Tabor Rd Truck Stop | ZFK | SP23-07 | Woodville Acres Ph 3, Blk 1 Lts 1-4 | Firdous Ali | M Lanza Engineering | Revised (Digital) CP | 2023-12-27 | 2024-01-02 | UKN | N/A | N/A | N/A | N/A | 2024-01-05 | N/A | 2024-01-08 | 2024-01-08 | Approved | 11 | Yes | Rev #5; JEB no comments 1/2/24, KN no comments 1/5/24 (jls)
10.408

## 2024
Project Name | Project Eng | Case # | Subdivision | Applicant | Engineer | Digital Submittal | Date Submittal Received | Date Distr. | Inspector Comments Received | BTU Comments Received | Dev Srvcs Comments Received | Fire Comments Recv'd | Traffic Comments Recv'd | Water Comments Received | FP Coord Comments Received | Date Comments Prepared | Comments Sent to Applicant / Engineer | Status | Gross Review Days | Met Deadline? | Add'l Comments
Pleasant Hill Sec 3 Ph 3 | KCS SKG | FP24-01 | Pleasant Hill Sec 3 Ph 3, Blk 3 6&13 77 Lts | WBW Single Land Investment | Yalgo Engineering | CP | 2024-01-03 | 2024-01-03 | 2024-01-04 | UKN | N/A | N/A | 2024-01-18 | 2024-01-08 | N/A | 2024-01-29 | 2024-01-30 | Comments | 26 | No | Original documents submitted on 12/22/23; waited until FP is scheduled on SDRC & assigned to an engineer (dms); KF no comments 1/4/24; KN comments 1/8/24; ZFK comments 1/18/24 (jls)
Pleasant Hill Sec 3 Ph 3 | KCS SKG | FP24-01 | Pleasant Hill Sec 3 Ph 3, Blk 3 6&13 77 Lts | WBW Single Land Investment | Yalgo Engineering | EE | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-29 | 2024-01-30 | Comments | 26 | No | N/A
Pleasant Hill Sec 3 Ph 3 | KCS SKG | FP24-01 | Pleasant Hill Sec 3 Ph 3, Blk 3 6&13 77 Lts | WBW Single Land Investment | Yalgo Engineering | DR | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-30 | Comments | 26 | No | N/A
Pleasant Hill Sec 3 Ph 4 | KCS SKG | FP24-02 | Pleasant Hill Sec 3 Ph 4, Blk 8-12 96 Lts | WBW Single Land Investment | Yalgo Engineering | CP | 2024-01-03 | 2024-01-03 | 2024-01-04 | UKN | N/A | N/A | 2024-01-18 | 2024-01-08 | N/A | 2024-01-29 | 2024-01-30 | Comments | 26 | No | Original documents submitted on 12/22/23; waited until Ph 3&4 FP to be scheduled on SDRC (dms); KF no comments 1/4/24 (jls); KN comments 1/8/24; ZFK comments 1/18/24 (jls)
Pleasant Hill Sec 3 Ph 4 | KCS SKG | FP24-02 | Pleasant Hill Sec 3 Ph 4, Blk 8-12 96 Lts | WBW Single Land Investment | Yalgo Engineering | EE | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-29 | 2024-01-30 | Comments | 26 | No | N/A
Pleasant Hill Sec 3 Ph 4 | KCS SKG | FP24-02 | Pleasant Hill Sec 3 Ph 4, Blk 8-12 96 Lts | WBW Single Land Investment | Yalgo Engineering | DR | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-30 | Comments | 26 | No | N/A
Pleasant Hill Sec 3 Ph 1-4 | KCS SKG | PP23-21 | Pleasant Hill Sec 3 Ph 1-9 | WBW Single Land Investment | Yalgo Engineering | SR | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-29 | 2024-01-30 | Approved | 26 | No | Original documents submitted on 12/22/23; however waited until Ph 3&4 FP to be scheduled on SDRC (dms)
Pleasant Hill Sec 3 Ph 1-4 | KCS SKG | PP23-21 | Pleasant Hill Sec 3 Ph 1-9 | WBW Single Land Investment | Yalgo Engineering | WR | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-29 | 2024-01-30 | Approved | 26 | No | N/A
Villa Maria Townhomes | BMG | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Revised CP | 2024-01-03 | 2024-01-03 | UKN | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-18 | 2024-01-18 | Comments | 14 | Yes | Rev #1; KN comments 1/8/24; JEB no comments 1/8/24 (jls)
Villa Maria Townhomes | BMG | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Revised EE | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Comments | 14 | Yes | Rev #1
Villa Maria Townhomes | BMG | SP23-77 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Revised DR | 2024-01-03 | 2024-01-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Comments | 14 | Yes | Rev #1
Pleasant Hill Sec 3 Ph 3 & 4 | KCS SKG | PP23-21 | Pleasant Hill Sec 3 Ph 1-9 | WBW Single Land Investment | Yalgo Engineering | TIA | 2024-01-04 | 2024-01-04 | N/A | N/A | N/A | N/A | UKN | N/A | N/A | 2024-01-26 | 2024-01-26 | Approved | 21 | No | N/A
Reveille Park Ph 1 | KCS SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-01-04 | 2024-01-04 | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | N/A | 2024-01-11 | 2024-01-11 | Comments | 7 | Yes | Rev #3; KN comments 1/8/24; JEB comments 1/9/24 (jls)
Reveille Park Ph 1 | KCS SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised EE | 2024-01-04 | 2024-01-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | Comments | 7 | Yes | Rev #3
Copperfield Dr Apartments | ENB | RZ23-30 | J W Scott League | Adam Development Properties LP | Kimley-Horn & Assoc | Revised TIA | 2024-01-04 | 2024-01-04 | N/A | N/A | N/A | N/A | 2024-01-12 | N/A | N/A | 2024-01-12 | 2024-01-12 | Approved | 7 | Yes | Rev #1; ZFK comments 1/12/24 (jls)
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised CP | 2024-01-05 | 2024-01-05 | UKN | N/A | N/A | N/A | N/A | 2024-01-08 | N/A | 2024-01-23 | 2024-01-23 | Comments | 17 | No | Rev #1; KN comments 1/8/24; JEB no comments 1/8/24 (jls)
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised EE | 2024-01-05 | 2024-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Comments | 17 | No | Rev #1
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised WR | 2024-01-05 | 2024-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Comments | 17 | No | Rev #1
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised SR | 2024-01-05 | 2024-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Comments | 17 | No | Rev #1
Drew's Car Wash No 7 | BMG | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised DR | 2024-01-05 | 2024-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Comments | 17 | No | Rev #1
Oakmont Ph 4C | ENB | SQ24-01 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | SQ Permit | 2024-01-06 | 2024-01-11 | N/A | N/A | 2024-01-11 | N/A | 2024-01-16 | 2024-01-11 | UKN | 2024-01-17 | 2024-01-17 | Approved | 10 | Yes | Rev #1
Reveille Park Ph 1 | KCS SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | TxDOT Permit | 2024-01-07 | 2024-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-26 | Emailed to TxDOT | 49 | No | N/A
Rudder Pointe Ph 5 | KCS ENB | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised CP | 2024-01-08 | 2024-01-08 | 2024-01-17 | N/A | N/A | N/A | N/A | 2024-01-16 | N/A | 2024-01-18 | 2024-01-18 | Comments | 9 | Yes | Rev #3; KN comments 1/10/24 (jls); JEB no comments 1/16/24 (dms); PK no comments 1/17/24 (jls)
Rudder Pointe Ph 5 | KCS ENB | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised DR | 2024-01-08 | 2024-01-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Approved | 9 | Yes | N/A
Hardy Street Parking Lot | BMG | SP22-67 | Suber's Ph 5, Blk 2 Lt 10 | Catholic Diocese of Austin TX | Gessner Engineering | Revised DL | 2024-01-09 | 2024-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | Comments | 7 | Yes | Rev #2
Twin City Mission | BMG | SP23-64 | Twin City Mission Subd., Blk 1 Lt 1 | Twin City Mission | Patterson Architects | Revised EE | 2024-01-09 | 2024-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-12 | Approved | 2 | Yes | Rev #2
Gourd Creek Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Revised CP | 2024-01-10 | 2024-01-10 | 2024-01-12 | N/A | N/A | N/A | N/A | 2024-01-17 | N/A | 2024-01-18 | 2024-01-18 | Comments | 8 | Yes | Rev #2; KF comments 1/12/24 (jls)
Gourd Creek Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Revised SR | 2024-01-10 | 2024-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Comments | 8 | Yes | Rev #2
Oakmont Ph 4C | KCS ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised CP | 2024-01-11 | 2024-01-11 | UKN | N/A | N/A | N/A | N/A | 2024-01-22 | N/A | 2024-01-23 | 2024-01-24 | Comments | 12 | Yes | Rev #1; JEB comments 1/18/24; KN no comments 1/22/24 (jls)
Oakmont Ph 4C | KCS ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised DR | 2024-01-11 | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | Comments | 12 | Yes | Rev #1
Oakmont Ph 4C | KCS ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised WL | 2024-01-11 | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | Approved | 12 | Yes | Rev #1
Oakmont Ph 4C | KCS ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised SL | 2024-01-11 | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | Approved | 12 | Yes | Rev #1
Oakmont Ph 4C | KCS ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised EE | 2024-01-11 | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | Comments | 12 | Yes | Rev #1
Reveille Park Ph 1 | KCS SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-01-11 | 2024-01-11 | UKN | N/A | N/A | N/A | N/A | 2024-01-18 | N/A | 2024-01-26 | 2024-01-30 | Comments | 18 | No | Rev #4; JEB comments 1/18/24 (jls)
Reveille Park Ph 1 | KCS SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | DR | 2024-01-11 | 2024-01-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-30 | Comments | 18 | No | N/A
Pleasant Hill Sec 3 Ph 1 | KCS SKG | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | N/A | 2024-01-22 | 2024-01-30 | Comments | 14 | Yes | Rev #4; KN comments 1/22/24 (jls)
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised DR | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Comments | 13 | Yes | Rev #1
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised SR | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | N/A | 2024-01-29 | 2024-01-29 | Comments | 13 | Yes | Rev #1
Aspen St Condos | BMG | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised CP | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | N/A | 2024-01-29 | 2024-01-29 | Comments | 13 | Yes | Rev #1; JEB comments 1/16/24 (dms); KN comments 1/24/24 (jls)
Reveille Estates Ph 3 | KCS SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | DL | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-30 | Approved | 14 | Yes | N/A
Reveille Estates Ph 3 | KCS SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | SL | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-30 | Approved | 14 | Yes | N/A
Reveille Estates Ph 3 | KCS SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | WL | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-30 | Approved | 14 | Yes | N/A
Reveille Estates Ph 3 | KCS SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | CP | 2024-01-16 | 2024-01-16 | UKN | N/A | N/A | N/A | 2024-01-26 | 2024-01-25 | N/A | 2024-01-29 | 2024-01-30 | Comments | 14 | Yes | KN comments 1/25/24 (jls)
Clay St Sewer Line | ENB | RP23-43 | Highland Park Ph 2, Blk 10 Lt 1R | 4104 Oaklawn St | McClure & Browne | EE | 2024-01-16 | 2024-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Comments | 14 | Yes | N/A
Clay St Sewer Line | ENB | RP23-43 | Highland Park Ph 2, Blk 10 Lt 1R | 4104 Oaklawn St | McClure & Browne | CP | 2024-01-16 | 2024-01-16 | 2024-01-25 | N/A | N/A | N/A | 2024-01-26 | 2024-01-30 | N/A | 2024-01-30 | 2024-01-30 | Comments | 14 | Yes | KN comments 1/25/24 (jls); AM no comments (dms)
Twelve Oaks Reserve | KCS ENB | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | Revised CP | 2024-01-17 | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | N/A | 2024-01-29 | 2024-01-29 | Comments | 12 | Yes | Rev #1; KN comments 1/24/24 (jls)
Twelve Oaks Reserve | KCS ENB | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | Revised EE | 2024-01-17 | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Comments | 12 | Yes | Rev #1
Twelve Oaks Reserve | KCS ENB | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | SL | 2024-01-17 | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | N/A | 2024-01-29 | 2024-01-29 | Approved | 12 | Yes | N/A
Twelve Oaks Reserve | KCS ENB | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | WL | 2024-01-17 | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | N/A | 2024-01-29 | 2024-01-29 | Approved | 12 | Yes | KN comments 1/24/24 (dms)
Twelve Oaks Reserve | KCS ENB | FP23-41 | Twelve Oaks Reserve, Blk 1-4 43 Lts | Luminous Capital LLC | Kimley-Horn & Assoc | DR | 2024-01-17 | 2024-01-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-29 | Comments | 12 | Yes | N/A
Hardy Street Parking Lot | BMG | SP22-67 | Suber's Ph 5, Blk 2 Lt 10 | Catholic Diocese of Austin TX | Gessner Engineering | Revised DL | 2024-01-22 | 2024-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Approved | 1 | Yes | Rev #3
Gourd Creek Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Revised SR | 2024-01-22 | 2024-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Approved | 8 | Yes | Rev #3
Salad and Go | ZFK | SP23-24 | Midway Place Add'n, Blk 12 Lt 7R | Alma Gonzalez | Quiddity Engineering | Revised UR | 2024-01-22 | 2024-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Approved | 3 | Yes | No comments - ZFK
Copperfield Dr Apartments | ENB | RZ23-30 | J W Scott League | Adam Development Properties LP | Kimley-Horn & Assoc | Revised TIA | 2024-01-22 | 2024-01-29 | N/A | N/A | N/A | N/A | 2024-01-26 | N/A | N/A | 2024-01-26 | 2024-01-26 | Comments | 4 | Yes | Rev #2; TIA sent directly to engineer causing delay in routing (jls); comments returned 1/26/2024, with TxDOT comments as well
Rudder Pointe Ph 5 | ENB | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised CP | 2024-01-24 | 2024-01-24 | UKN | N/A | N/A | N/A | N/A | 2024-01-29 | N/A | 2024-01-29 | 2024-01-29 | Approved | 5 | Yes | Rev #4; KN comments 1/25/24; JEB no comments 1/29/24 (jls)
Rudder Pointe Ph 5 | ENB | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised EE | 2024-01-24 | 2024-01-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Approved | 5 | Yes | Rev #4
Opifex | ENB | SP23-68 | Park Heights Add'n, Lts 6-8 | Vaughn Development | Sam Thomas | Revised DR | 2024-01-24 | 2024-01-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-01 | Comments | 8 | Yes | Rev #2
Stella Ranch Ph 1 | SKG | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | Revised CP | 2024-01-24 | 2024-01-24 | UKN | N/A | N/A | N/A | N/A | 2024-01-31 | N/A | 2024-02-02 | 2024-02-06 | Comments | 13 | Yes | Rev #1; KN comments 1/31/24; JEB comments 1/30/24 (jls)
Stella Ranch Ph 1 | SKG | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | DR | 2024-01-24 | 2024-01-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Comments | 13 | Yes | N/A
Pleasant Hill Sec 3 Ph 1 | SKG | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-01-24 | 2024-01-24 | 2024-01-24 | N/A | N/A | N/A | N/A | 2024-01-25 | N/A | 2024-01-29 | 2024-01-30 | Comments | 6 | Yes | Rev #4; KF no comments 1/24/24, KN Comments 1/25/24 (jls)
PVD Development Ph 5 | JMH | SP24-03 | PVD Development, Blk 1 Lt 3 | PVD Development | Mitchell & Morgan | DR | 2024-01-24 | 2024-01-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | Comments | 7 | Yes | N/A
Oakmont Ph 4C | ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised CP | 2024-01-25 | 2024-01-26 | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | N/A | 2024-01-30 | 2024-01-30 | Comments | 5 | Yes | Rev #2; JEB comments 1/26/24; KN no comments 1/30/24 (dms)
Oakmont Ph 4C | ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised DR | 2024-01-25 | 2024-01-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Comments | 5 | Yes | Rev #2
Aspen St Condos | BMG JMH | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | WR | 2024-01-26 | 2024-01-26 | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | N/A | 2024-01-29 | 2024-01-29 | Comments | 3 | Yes | N/A
Rudder Pointe Ph 5 | ENB | FP22-31 | Rudder Pointe Ph 5, Blk 3-5 31 Lts | BORD Development | McClure & Browne | Revised EE | 2024-01-29 | 2024-01-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Approved | 0 | Yes | N/A
Francesca | BMG ENB | SP22-38 | Bryan Original Townsite, Blk 124 Lt 5R | NN Out Properties Ltd | J4 Engineering | EE | 2024-01-30 | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | N/A | 2024-02-13 | 2024-02-13 | Comments | 14 | Yes | Original documents submitted on 1/29/24; Waited on submittal of plans with detail sheets (jls)
Francesca | BMG ENB | SP22-38 | Bryan Original Townsite, Blk 124 Lt 5R | NN Out Properties Ltd | J4 Engineering | DL | 2024-01-30 | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | Approved | 14 | Yes | Original documents submitted on 1/29/24; Waited on submittal of plans with detail sheets (jls)
Francesca | BMG ENB | SP22-38 | Bryan Original Townsite, Blk 124 Lt 5R | NN Out Properties Ltd | J4 Engineering | WL | 2024-01-30 | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | N/A | 2024-02-13 | 2024-02-13 | Approved | 14 | Yes | Original documents submitted on 1/29/24; Waited on submittal of plans with detail sheets (jls)
Francesca | BMG ENB | SP22-38 | Bryan Original Townsite, Blk 124 Lt 5R | NN Out Properties Ltd | J4 Engineering | CP | 2024-01-30 | 2024-01-30 | UKN | UKN | N/A | N/A | UKN | 2024-01-30 | N/A | 2024-02-13 | 2024-02-13 | Comments | 14 | Yes | JEB & KN comments 1/30/24 (jls)
Gourd Creek Ph 1 | ZFK | FP23-43 | Gourd Creek Ph 1, Blk 1-4 46 Lts | Shian Cao | McClure & Browne | Revised EE | 2024-01-30 | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Approved | 0 | Yes | N/A
Copperfield Dr Apartments | ENB | RZ23-30 | J W Scott League | Adam Development Properties LP | Kimley-Horn & Assoc | Revised TIA | 2024-01-30 | 2024-01-30 | N/A | N/A | N/A | N/A | 2024-02-05 | N/A | N/A | 2024-02-05 | 2024-02-05 | Approved | 6 | Yes | Rev #1; ZFK no comments 2/5/24 (jls)
Fairway Dr Townhomes | BMG ENB | CU23-09 | Country Club Estates Ph 1, Blk D Lts 1&2 | Optimal Housing Five LLC | J4 Engineering | Revised CP | 2024-01-30 | 2024-01-30 | UKN | N/A | N/A | N/A | N/A | 2024-01-31 | N/A | 2024-02-02 | 2024-02-02 | Approved | 3 | Yes | Rev #1; JEB no comments 1/31/24 (jls)
Fairway Dr Townhomes | BMG ENB | CU23-09 | Country Club Estates Ph 1, Blk D Lts 1&2 | Optimal Housing Five LLC | J4 Engineering | Revised DL | 2024-01-30 | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | Approved | 3 | Yes | Rev #1
Oakmont Ph 4C | ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised EE | 2024-01-31 | 2024-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-07 | Approved | 7 | Yes | Rev #3
Oakmont Ph 4C | ENB | FP23-29 | Oakmont Ph 4C, Blk 34-36 20 Lts | Adam Development Properties LP | McClure & Browne | Revised CP | 2024-01-31 | 2024-01-31 | UKN | N/A | N/A | N/A | N/A | 2024-02-06 | N/A | 2024-02-07 | 2024-02-07 | Approved | 7 | Yes | Rev #3; KN no comments 2/6/24 (jls)
Fairway Dr Townhomes | BMG ENB | CU23-09 | Country Club Estates Ph 1, Blk D Lts 1&2 | Optimal Housing Five LLC | J4 Engineering | Revised EE | 2024-01-31 | 2024-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | Approved | 2 | Yes | Rev #1
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | DR | 2024-01-31 | 2024-01-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Comments | 14 | Yes | N/A
Miramont Sec 16 | JMH | RP24-02 | Miramont Sec 16, Blk 9 Lts 1-3 | Adam Development Properties LP | McClure & Browne | EE | 2024-01-31 | 2024-01-31 | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | N/A | 2024-02-16 | 2024-02-16 | Comments | 16 | No | N/A
Miramont Sec 16 | JMH | RP24-02 | Miramont Sec 16, Blk 9 Lts 1-3 | Adam Development Properties LP | McClure & Browne | CP | 2024-01-31 | 2024-01-31 | UKN | N/A | N/A | N/A | 2024-02-12 | 2024-02-16 | N/A | 2024-02-16 | 2024-02-16 | Comments | 16 | No | ZFK comments 2/12/24 (jls); KN comments 2/16/24 (jls)
Oscar & Sons Body Shop | SKG | SP24-04 | Shimen-Carrabba, Blk 4 Lt 16R | JOC Body Shops Inc | Goodwin-Lasiter-Strong | TxDOT Permit | 2024-01-31 | 2024-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-09 | Emailed to TxDOT | 9 | Yes | N/A
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-02-01 | 2024-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Comments | 13 | Yes | N/A
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-02-01 | 2024-02-01 | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | N/A | 2024-02-14 | 2024-02-14 | Comments | 13 | Yes | Rev #3; JEB comments 2/13/24 (jls)
Drew's Car Wash No 7 | JMH | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised DR | 2024-02-01 | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Approved | 14 | Yes | Rev #3, JMH no comments 2/15/24
Drew's Car Wash No 7 | JMH | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised SR | 2024-02-01 | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Approved | 14 | Yes | Rev #3, JMH no comments 2/15/24
Drew's Car Wash No 7 | JMH | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised WR | 2024-02-01 | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Approved | 14 | Yes | Rev #3, JMH no comments 2/15/24
Drew's Car Wash No 7 | JMH | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised EE | 2024-02-01 | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Approved | 14 | Yes | Rev #3, JMH no comments 2/15/24
Drew's Car Wash No 7 | JMH | SP23-67 | Coker Subd, Blk 1 Lts 1&2 | Drew's Car Wash No 7 LLC | Schultz Engineering | Revised CP | 2024-02-01 | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Approved | 14 | Yes | Rev #3, JMH no comments 2/15/24
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Revised UL | 2024-02-01 | 2024-02-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Comments | 13 | Yes | Rev #1
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | EE | 2024-02-07 | 2024-02-07 | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | N/A | 2024-02-20 | 2024-02-20 | Comments | 13 | Yes | JEB comments 2/8/24 (jls)
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | CP | 2024-02-07 | 2024-02-07 | UKN | UKN | N/A | N/A | 2024-02-20 | 2024-02-20 | N/A | 2024-02-20 | 2024-02-20 | Comments | 13 | Yes | JEB comments 2/8/24; ZFK no comments 2/20/24; KN comments 2/20/24 (jls)
Oscar & Sons Body Shop | SKG | SP24-04 | Shimen-Carrabba, Blk 4 Lt 16R | JOC Body Shops Inc | Goodwin-Lasiter-Strong | DL | 2024-01-26 | 2024-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Comments | 11 | Yes | Originally received 1/26/24, but it was overlooked and routed on 2/2/24 (jls)
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | SR | 2024-02-05 | 2024-02-05 | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | N/A | 2024-02-22 | 2024-02-22 | Comments | 17 | No | Comment Provided
Fuel Station | ENB | SP23-63 | Midway Place Add'n, Blk 1 Lt 1R | El Elohim LLC | Mitchell & Morgan | CP | 2024-02-05 | 2024-02-05 | 2024-02-06 | N/A | N/A | N/A | 2024-02-16 | 2024-02-06 | N/A | 2024-02-12 | 2024-02-12 | Comments | 7 | Yes | AM no comments 2/6/24; JEB comments 2/6/24; ZFK no comments 2/16/24 (jls)
Fuel Station | ENB | SP23-63 | Midway Place Add'n, Blk 1 Lt 1R | El Elohim LLC | Mitchell & Morgan | EE | 2024-02-05 | 2024-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Approved | 7 | Yes | N/A
Aspen St Condos | JMH | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised CP | 2024-02-06 | 2024-02-06 | 2024-02-16 | N/A | N/A | N/A | N/A | 2024-02-09 | N/A | 2024-02-16 | 2024-02-16 | Comments | 10 | No | Rev #3; JEB no comments 2/6/24; KN comments 2/9/24; AM no comments 2/16/24 (jls)
Aspen St Condos | JMH | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised EE | 2024-02-06 | 2024-02-06 | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | N/A | 2024-02-16 | 2024-02-16 | Comments | 10 | No | Rev #3; JEB no comments 2/6/24; KN comments 2/9/24 (jls); JMH Comments 2/16
Clay St Sewer Line | ENB | RP23-43 | Highland Park Ph 2, Blk 10 Lt 1R | 4104 Oaklawn St | McClure & Browne | Revised CP | 2024-02-08 | 2024-02-08 | 2024-02-16 | N/A | N/A | N/A | N/A | 2024-02-08 | N/A | 2024-02-15 | 2024-02-15 | Approved | 7 | Yes | Rev #1; JEB comments 2/8/24; KN comments 2/16/24; AM no comments 2/16/24 (jls)
Clay St Sewer Line | ENB | RP23-43 | Highland Park Ph 2, Blk 10 Lt 1R | 4104 Oaklawn St | McClure & Browne | Revised EE | 2024-02-08 | 2024-02-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Approved | 7 | Yes | Rev #1
Green Crossing C-Store | ENB | CU24-01 | Green Crossing, Blk 1 Lt 1 | STTC LLC | J4 Engineering | DR | 2024-02-08 | 2024-02-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Comments | 12 | Yes | N/A
Turkey Creek Sewer Ext | SKG | SP23-73 | John H Jones | BCS Turkey Creek LP | Mitchell & Morgan | CP | 2024-02-12 | 2024-02-12 | 2024-02-16 | N/A | N/A | N/A | N/A | 2024-02-20 | N/A | 2024-02-20 | 2024-02-21 | Comments | 9 | Yes | Rev #1; KF no comments 2/16/24; JEB comments 2/20/24; KN comments 2/20/24 (jls)
Turkey Creek Sewer Ext | SKG | SP23-73 | John H Jones | BCS Turkey Creek LP | Mitchell & Morgan | SL | 2024-02-12 | 2024-02-12 | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | N/A | 2024-02-20 | 2024-02-21 | Approved | 9 | Yes | N/A
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | WR | 2024-02-12 | 2024-02-12 | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | N/A | 2024-02-22 | 2024-02-22 | Comments | 10 | Yes | Comment Provided
Pleasant Hill Sec 3 Ph 1 | SKG | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-02-14 | 2024-02-14 | 2024-02-15 | N/A | N/A | N/A | N/A | UKN | N/A | 2024-02-20 | 2024-02-21 | Pending | 7 | Yes | KF no comments 2/15/24 (jls); Pending Approval of EE (skg)
Opifex | ENB | SP23-68 | Park Heights Add'n, Lts 6-8 | Vaughn Development | Sam Thomas | Revised DR | 2024-02-14 | 2024-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-21 | Approved | 7 | Yes | N/A
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | CP | 2024-02-14 | 2024-02-14 | UKN | N/A | N/A | N/A | N/A | 2024-02-22 | N/A | 2024-02-22 | 2024-02-22 | Comments | 8 | Yes | JEB comments 2/16/24 (jls)
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Revised UL | 2024-02-14 | 2024-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-16 | Approved | 2 | Yes | N/A
Woodson | ENB | SP24-08 | College Oaks Add'n, Blk 1 Lt 13-18 | Woodson Development | M3 Engineering | CP | 2024-02-14 | 2024-02-14 | 2024-02-26 | UKN | N/A | N/A | 2024-02-26 | 2024-02-25 | N/A | 2024-02-27 | 2024-02-28 | Comments | 14 | Yes | JEB comments 2/16/24 (jls); KN comments 2/25/24 (dms); AM no comments 2/26/24; ZFK comments 2/26/24 (jls)
Villa Maria Townhomes | ENB | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Revised CP | 2024-02-15 | 2024-02-15 | UKN | N/A | N/A | N/A | N/A | 2024-02-15 | N/A | 2024-02-20 | 2024-02-21 | Approved | 6 | Yes | Rev #2; JEB comments 2/15/24 (jls)
Villa Maria Townhomes | ENB | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Revised EE | 2024-02-15 | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-21 | Approved | 6 | Yes | Rev #2
Villa Maria Townhomes | ENB | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | Revised DR | 2024-02-15 | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-21 | Approved | 6 | Yes | Rev #2
Villa Maria Townhomes | ENB | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | UL | 2024-02-15 | 2024-02-15 | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | N/A | 2024-02-20 | 2024-02-21 | Approved | 6 | Yes | N/A
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-02-15 | 2024-02-15 | 2024-02-16 | N/A | N/A | N/A | N/A | UKN | N/A | 2024-02-22 | 2024-02-22 | Comments | 7 | Yes | Rev #4; KF no comments 2/16/24 (jls)
Reveille Estates Ph 3 | SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-02-16 | 2024-02-16 | UKN | N/A | N/A | N/A | N/A | 2024-02-25 | N/A | 2024-02-26 | 2024-02-26 | Comments | 10 | Yes | Rev #1; JEB comments 2/22/24 (jls); KN no comments 2/25/24 (dms)
Reveille Estates Ph 3 | SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | Revised DL | 2024-02-16 | 2024-02-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | Comments | 10 | Yes | Rev #1
Pleasant Hill Sec 3 Ph 1 | SKG | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-02-16 | 2024-02-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | Comments | 5 | Yes | N/A
Main Street Fire Line | SKG | SP24-01 | Bryan Original Townsite, Blk 101 Lt 1R | 315 Main OZ LP | Winchester Architects | CP | 2024-02-16 | 2024-02-16 | 2024-02-21 | N/A | N/A | N/A | N/A | 2024-02-21 | N/A | 2024-02-21 | 2024-02-21 | Approved | 5 | Yes | JEB comments 2/16/24; AM no comments 2/21/24; KN no comments 2/21/24 (jls)
PVD Development Ph 5 | JMH | SP24-03 | PVD Development, Blk 1 Lt 3 | PVD Development | Mitchell & Morgan | CP | 2024-02-19 | 2024-02-19 | 2024-02-20 | UKN | N/A | N/A | 2024-03-01 | 2024-02-20 | N/A | 2024-02-28 | 2024-02-28 | Comments | 9 | Yes | JEB comments 2/20/24; PK no comments 2/20/24; KN comments 2/20/24; ZFK no comments 3/1/24 (jls)
Villa Maria Townhomes | ENB | RP23-51 | Country Club Estates Ph 2, Blk A Lts 1R1-1R6 & R1-2R62 | 904 Welch LLC | J4 Engineering | TxDOT Permit | 2024-02-20 | 2024-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-26 | Emailed to TxDOT | 6 | Yes | Rev #1
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | Revised DR | 2024-02-20 | 2024-02-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Approved | 2 | Yes | Rev #1
Green Crossing C-Store | ENB | CU24-01 | Green Crossing, Blk 1 Lt 1 | STTC LLC | J4 Engineering | Revised DR | 2024-02-21 | 2024-02-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | Approved | -30 | Yes | Rev #1
Francesca | ENB | SP22-38 | Bryan Original Townsite, Blk 124 Lt 5R | NN Out Properties Ltd | J4 Engineering | Revised CP | 2024-02-22 | 2024-02-22 | 2024-02-26 | N/A | N/A | N/A | N/A | 2024-02-25 | N/A | 2024-03-04 | 2024-03-04 | Approved | 11 | Yes | Rev #1; JEB no comments 2/22/24 (jls); KN no comments 2/25/24 (dms); AM no comments 2/26/24 (jls)
Francesca | ENB | SP22-38 | Bryan Original Townsite, Blk 124 Lt 5R | NN Out Properties Ltd | J4 Engineering | Revised EE | 2024-02-22 | 2024-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | Approved | 11 | Yes | Rev #1
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Revised CP | 2024-02-22 | 2024-02-22 | UKN | N/A | N/A | N/A | N/A | 2024-02-25 | N/A | 2024-02-26 | 2024-03-04 | Comments | 11 | Yes | Rev #1, JEB comments 2/22/24 (jls); KN comments 2/25/24 (dms)
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | EE | 2024-02-22 | 2024-02-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | Approved | 8 | Yes | N/A
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-02-23 | 2024-02-23 | 2024-02-26 | N/A | N/A | N/A | N/A | 2024-02-25 | N/A | 2024-02-26 | 2024-02-26 | Comments | 3 | Yes | Rev #5; KN comments 2/25/24 (dms); KF no comments 2/2/24 (jls)
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-02-23 | 2024-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | Comments | 3 | Yes | Rev #5
Falcon Ridge | ENB | FP24-08 | Falcon Ridge (Marvin M Porters Addn), Lts 1-3 | Brackmel Development LLC | J4 Engineering | TIA | 2024-02-23 | 2024-02-23 | N/A | N/A | N/A | N/A | 2024-02-23 | N/A | N/A | 2024-02-23 | 2024-02-23 | Approved | 0 | Yes | ZFK no comments 2/23/24 (jls)
Pleasant Hill Sec 3 Ph 1 | SKG | FP23-32 | Pleasant Hill Sec 3 Ph 1, Blk 1-5&7 103 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-02-23 | 2024-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | Approved | 3 | Yes | Rev #2
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-02-23 | 2024-02-23 | UKN | N/A | N/A | N/A | N/A | 2024-02-25 | N/A | 2024-02-28 | 2024-02-29 | Comments | 6 | Yes | Rev #5; KN no comments & JEB comments 2/25/24 (dms)
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised EE | 2024-02-23 | 2024-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-29 | Comments | 6 | Yes | Rev #5
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised DR | 2024-02-23 | 2024-02-23 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Comments | 6 | Yes | Rev #5
Miramont Sec 16 | JMH | RP24-02 | Miramont Sec 16, Blk 9 Lts 1-3 | Adam Development Properties LP | McClure & Browne | Revised CP | 2024-02-26 | 2024-02-26 | N/A | N/A | N/A | N/A | N/A | UKN | N/A | 2024-03-05 | 2024-03-05 | Comments | 8 | Yes | Rev #1
Miramont Sec 16 | JMH | RP24-02 | Miramont Sec 16, Blk 9 Lts 1-3 | Adam Development Properties LP | McClure & Browne | Revised EE | 2024-02-26 | 2024-02-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | Comments | 8 | Yes | Rev #1
PVD Development Ph 5 | JMH | SP24-03 | PVD Development, Blk 1 Lt 3 | PVD Development | Mitchell & Morgan | Revised CP | 2024-02-27 | 2024-02-27 | 2024-02-27 | N/A | N/A | N/A | N/A | 2024-02-27 | N/A | 2024-02-28 | 2024-02-28 | Approved | 1 | Yes | Rev #1; JEB no comments 2/27/24; KN no comments 2/27/24; PK no comments 2/27/24 (jls)
PVD Development Ph 5 | JMH | SP24-03 | PVD Development, Blk 1 Lt 3 | PVD Development | Mitchell & Morgan | Revised DR | 2024-02-27 | 2024-02-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | Approved | 1 | Yes | Rev #1
PVD Development Ph 5 | JMH | SP24-03 | PVD Development, Blk 1 Lt 3 | PVD Development | Mitchell & Morgan | SL | 2024-02-27 | 2024-02-27 | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | N/A | 2024-02-28 | 2024-02-28 | Approved | 1 | Yes | N/A | u
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-02-27 | 2024-02-27 | 2024-02-28 | N/A | N/A | N/A | N/A | 2024-03-01 | N/A | 2024-03-01 | 2024-03-04 | Pending | 6 | Yes | Rev #6; KF no comments 2/28/24; JEB no comments 3/1/24; KN no comments 3/1/24 (jls)
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-02-27 | 2024-02-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-04 | Comments | 6 | Yes | Rev #6
Aspen St Condos | JMH | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised CP | 2024-02-27 | 2024-02-27 | 2024-03-01 | N/A | N/A | N/A | N/A | 2024-03-01 | N/A | 2024-03-01 | 2024-03-01 | Comments | 3 | Yes | Rev #4; KN no comments 3/1/24; AM no comments 3/1/24 (jls)
Aspen St Condos | JMH | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised EE | 2024-02-27 | 2024-02-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | Approved | 3 | Yes | Rev #4
Aspen St Condos | JMH | SP23-66 | Unity Subd., Blk 1 Lts 1-4 | Bluestone Partners | McClure & Browne | Revised WR | 2024-02-27 | 2024-02-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | Approved | 3 | Yes | Rev #4
TXB C-Store/Gas Station | BMG ZFK | SP22-54 | Fuller Subd., Blk A Lts 1&2 | Brightwork Real Estate | Cool Breeze Consultants | Revised DR | 2024-02-27 | 2024-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Comments | 2 | Yes | N/A
Pleasant Hill Sec 3 Ph 3 | KCS SKG | FP24-01 | Pleasant Hill Sec 3 Ph 3, Blk 3 6&13 77 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-02-29 | 2024-02-29 | 2024-03-01 | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | 2024-03-11 | 2024-03-11 | Comments | 11 | Yes | Rev #1; KF no comments 3/1/24; KN comments 3/5/24; JEB comments 3/8/24 (jls)
Pleasant Hill Sec 3 Ph 3 | KCS SKG | FP24-01 | Pleasant Hill Sec 3 Ph 3, Blk 3 6&13 77 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-02-29 | 2024-02-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Comments | 11 | Yes | Rev #1
Stella Ranch Ph 1 | SKG | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | Revised CP | 2024-02-29 | 2024-02-29 | UKN | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | 2024-03-07 | 2024-03-08 | Comments | 8 | Yes | Rev #2; KN comments 3/5/24; JEB comments 3/8/24 (jls)
Stella Ranch Ph 1 | SKG | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | Revised EE | 2024-02-29 | 2024-02-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-08 | Comments | 8 | Yes | Rev #2
Stella Ranch Ph 1 | SKG | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | Revised DR | 2024-02-29 | 2024-02-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-08 | Comments | 8 | Yes | Rev #2
Stella Ranch Ph 1 | SKG | FP23-44 | Stella Ranch Ph 1, Blk 1&2 51 Lts | Steep Hollow Land | Mitchell & Morgan | SR | 2024-02-29 | 2024-02-29 | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | 2024-03-07 | 2024-03-08 | Comments | 8 | Yes | N/A
Pleasant Hill Sec 3 Ph 4 | KCS SKG | FP24-02 | Pleasant Hill Sec 3 Ph 4, Blk 8-12 96 Lts | WBW Single Land Investment | Yalgo Engineering | Revised CP | 2024-03-01 | 2024-03-01 | UKN | N/A | N/A | N/A | N/A | 2024-03-01 | N/A | 2024-03-12 | 2024-03-13 | Comments | 12 | Yes | Rev #1; KN comments 3/1/24; JEB no comments 3/1/24 (jls)
Pleasant Hill Sec 3 Ph 4 | KCS SKG | FP24-02 | Pleasant Hill Sec 3 Ph 4, Blk 8-12 96 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-03-01 | 2024-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-13 | Comments | 12 | Yes | Rev #1
Pleasant Hill Sec 3 Ph 4 | KCS SKG | FP24-02 | Pleasant Hill Sec 3 Ph 4, Blk 8-12 96 Lts | WBW Single Land Investment | Yalgo Engineering | Revised DR | 2024-03-01 | 2024-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-13 | Comments | 12 | Yes | Rev #1
Pleasant Hill Sec 3 Ph 2 | SKG | FP23-33 | Pleasant Hill Sec 3 Ph 2, Blk 3&5-7 110 Lts | WBW Single Land Investment | Yalgo Engineering | Revised EE | 2024-03-05 | 2024-03-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Approved | 6 | Yes | Rev #7
The Croft | ENB | FP24-06 | Croft, Blk 1 Lts 1-21 | Robby Neal | J4 Engineering | CP | 2024-03-07 | 2024-03-07 | UKN | UKN | N/A | N/A | UKN | 2024-03-22 | N/A | 2024-03-21 | 2024-03-21 | Comments | 14 | Yes | JEB comments 3/8/24 (jls), KN comments 3/22/24 (enb)
The Croft | ENB | FP24-06 | Croft, Blk 1 Lts 1-21 | Robby Neal | J4 Engineering | EE | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | 2024-03-21 | 2024-03-21 | Comments | 14 | Yes | N/A
The Croft | ENB | FP24-06 | Croft, Blk 1 Lts 1-21 | Robby Neal | J4 Engineering | DR | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Comments | 14 | Yes | N/A
The Croft | ENB | FP24-06 | Croft, Blk 1 Lts 1-21 | Robby Neal | J4 Engineering | WL | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | 2024-03-21 | 2024-03-21 | Approved | 14 | Yes | N/A
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | Revised CP | 2024-03-07 | 2024-03-07 | UKN | N/A | N/A | N/A | N/A | UKN | N/A | 2024-03-12 | 2024-03-12 | Approved | 5 | Yes | Rev #3
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | Revised EE | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Approved | 5 | Yes | Rev #3
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | Revised DR | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Approved | 5 | Yes | Rev #3
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | Revised WR | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Approved | 5 | Yes | Rev #3
Bldg Add'n | JMH | SP24-02 | Parkwood Estates Ph 2, Blk 1 Lt 3 | Carl Hildebrandt | Center Pole Engineering | Revised SR | 2024-03-07 | 2024-03-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Approved | 5 | Yes | Rev #3
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-03-08 | 2024-03-08 | UKN | N/A | N/A | N/A | N/A | 2024-03-08 | N/A | 2024-03-13 | 2024-03-14 | Comments | 6 | Yes | Rev #6; JEB comments 3/8/24 (jls)
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised EE | 2024-03-08 | 2024-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-14 | Comments | 6 | Yes | Rev #6
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised DR | 2024-03-08 | 2024-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Comments | 6 | Yes | Rev #6
Texas Communication | JMH | SP24-17 | Brazos County Ind'l Park Ph 3 | Broadband Towers LLC | J4 Engineering | DL | 2024-03-08 | 2024-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Approved | 4 | Yes | No comments
Oakmont Ph 7 | ENB | FP23-40 | Oakmont Ph 7, Blk 37-41 97 Lts | Adam Development Properties LP | McClure & Browne | CP | 2024-03-08 | 2024-03-08 | UKN | UKN | N/A | N/A | 2024-03-20 | 2024-03-15 | N/A | 2024-03-21 | 2024-03-22 | Comments | 14 | Yes | KN comments 3/13/24; JEB comments 3/15/24 (jls); ZFK comments 3/20/24 (jls)
Oakmont Ph 7 | ENB | FP23-40 | Oakmont Ph 7, Blk 37-41 97 Lts | Adam Development Properties LP | McClure & Browne | EE | 2024-03-08 | 2024-03-08 | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-21 | 2024-03-22 | Comments | 14 | Yes | N/A
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Revised CP | 2024-03-12 | 2024-03-12 | UKN | N/A | N/A | N/A | N/A | 2024-03-12 | N/A | 2024-03-14 | 2024-03-14 | Approved | 2 | Yes | Rev #5; JEB no comments 3/12/24 (jls)
Reveille Estates Ph 3 | SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-03-14 | 2024-03-14 | UKN | N/A | N/A | N/A | N/A | UKN | N/A | 2024-03-19 | 2024-03-21 | Pending | 7 | Yes | Rev #2
Reveille Estates Ph 3 | SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | Revised DL | 2024-03-14 | 2024-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-21 | Pending | 7 | Yes | Rev #2
Reveille Estates Ph 3 | SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | EE | 2024-03-14 | 2024-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Comments | 7 | Yes | N/A
Starbucks | SKG | RP23-47 | Hudson at University Ph 2, Blk 1 Lt 8R1 | BW Texas University Plaza LLC | Cool Breeze Consultants | Revised EE | 2024-03-14 | 2024-03-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-18 | Approved | 4 | Yes | N/A
Randolph Townhomes | ENB | CU24-03 | Bryan Original Townsite, Blk 209, Lots 6-8 | Faustino & Amelia Castillo | J4 Engineering | CP | 2024-03-20 | 2024-03-20 | UKN | UKN | N/A | N/A | 2024-04-03 | 2024-04-03 | N/A | 2024-04-03 | 2024-04-03 | Comments | 13 | Yes | jeb comments 4/3/24 (enb), kn comments 4/3/24 (enb)
Randolph Townhomes | ENB | CU24-03 | Bryan Original Townsite, Blk 209, Lots 6-8 | Faustino & Amelia Castillo | J4 Engineering | EE | 2024-03-20 | 2024-03-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Comments | 13 | Yes | N/A
Randolph Townhomes | ENB | CU24-03 | Bryan Original Townsite, Blk 209, Lots 6-8 | Faustino & Amelia Castillo | J4 Engineering | DL | 2024-03-20 | 2024-03-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Comments | 13 | Yes | N/A
Reveille Estates Ph 3 | SKG | FP24-03 | Reveille Estates Ph 3, Blk 5 & 8-10 72 Lts | B/CS Leasing | McClure & Browne | Revised EE | 2024-03-26 | 2024-03-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | Approved | 0 | Yes | Rev #2
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised CP | 2024-03-28 | 2024-03-28 | UKN | N/A | N/A | N/A | N/A | UKN | N/A | 2024-04-03 | 2024-04-04 | Approved | 6 | Yes | Rev #7
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised EE | 2024-03-28 | 2024-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-04 | Approved | 6 | Yes | Rev #7
Reveille Park Ph 1 | SKG | FP23-42 | Reveille Park Ph 1, Blk 1-4 34 Lts | B/CS Leasing | McClure & Browne | Revised DR | 2024-03-28 | 2024-03-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-04 | Approved | 6 | Yes | Rev #7
2300 S College Ave | JMH | SP24-10 | C M Evans, Lts 15-24 | M5 Partners LP | Schultz Engineering | DL | 2024-04-03 | 2024-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Due 4/17/24 | -45385 | Yes
Kristen Distributing | SKG | SP24-16 | Gunler, Blk 1 Lt 1R | Kristen Distributing Co | Schultz Engineering | DL | 2024-04-03 | 2024-04-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Due 4/17/24 | -45385 | Yes
1224-1230 S College Ave | SKG | SQ24-02 | Smythe Add'n No 2, Blk 1 Lts 1-4 | Keith Linton | AECOM | SQ Permit | 2024-04-03 | 2024-04-03 | N/A | N/A | 2024-04-03 | UKN | N/A | 2024-04-03 | UKN | 2024-04-10 | 2024-04-10 | Approved | 7 | Yes
Turkey Creek Sewer Ext | SKG | SP23-73 | John H Jones | BCS Turkey Creek LP | Mitchell & Morgan | Revised CP | 2024-04-04 | 2024-04-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Approved | 0 | Yes | Submittal corrected minor issue before stamped release for construction.
Trafalgar | SKG | FP23-35 | Trafalgar Subd., Blk 1 Lts 1-6 | Summit Crossing | Quiddity Engineering | CP | 2024-04-04 | 2024-04-04 | UKN | UKN | N/A | N/A | 2024-04-16 | 2024-04-12 | N/A |  |  | Due 4/18/24 | -45386 | Yes | JEB comments 4/8/24; KN comments 4/12/24; ZFK comments 4/16/24 (jls)
Pagosa Springs Ph 1 | ZFK | FP23-15 | Pagosa Springs Ph 1, Blk 1-4 46 Lts | SE Investments | McClure & Browne | Revised DR | 2024-04-08 | 2024-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | Comments | 1 | Yes | Rev #1
Puebla Soccer Complex | JMH | SP23-79 | Puebla Soccer Complex Blk 1 Lt 1 | Leobardo Flores | Center Pole Engineering | DR | 2024-04-17 | 2024-04-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Due 5/1/24 | -45399 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes
[19 empty] | 0 | Yes