## Case Log
Scanned to Laserfiche (Y/N) | R No. | Active / Completed / Dead | Case No. | Applicant / Developer | Engineer / Surveyor / Agent | Subdivision Name | Address | Description (Type of Development) | Number of Lots (Replat & Final Plats) | Acres (Replats & Final Plats) | Date Submitted | SDRC Date | 2nd SDRC Date | 3rd SDRC Date | 4th SDRC Date | SDRC Appr | Board/Commission Date (HLC, P&Z, ZBA)
N | N/A | A | ANNEX15-03 | N/A | N/A | Texas Triangle Park | Multiple | Industrial | N/A | 182.731 | 2014-07-09 | Req | Req | Req | Req | Req | N/A
N | N/A | A | ANNEX15-02 | Karen Francis Snowden | Hester Engineering | Snowden Tract | Multiple | RD-5 | N/A | 8.3 | 2015-04-10 | Req | Req | Req | Req | Req | N/A
N | R95902 R95904 | SC | AP15-01 | Jodi Rehwinkel | Kerr Surveying | Lakeview Add'n, Lts 1R & 2R | 2316 & 2318 Frankline St | Residential | 2 | 0.957 | 2015-03-03 | 2015-03-10 | 2015-03-24 | N/A | N/A | 2015-03-24 | N/A
N | R22750 R22751 | SC | CU13-05 | P Burkart & D Riddle | N/A | Bryan Original Townsite, Blk 158 Lt 4&5 | 206 S Sims St | Residential | N/A | 0.48 | 2013-05-22 | 2013-06-04 | N/A | N/A | N/A | 2013-06-04 | P&Z 06/20/13
N | R39510 | SC | CU13-06 | Ramiro Quintero | Same as Applicant | Stephen F Austin # 9 | 1015 W 28th St | Residential & Auto Repair | N/A | N/A | 2013-06-19 | See Comments | N/A | N/A | N/A | N/A | P&Z 12/04/14
N | R22630 | SC | CU13-07 | James Collard | Vox Construction | Bryan Original Townsite, Blk 139 | 307 W 26th St | Tattoo Studio | N/A | 0.264 | 2013-07-17 | 2013-07-23 | N/A | N/A | N/A | 2013-07-23 | P&Z 08/01/13
N | R29123 | SC | CU13-08 | Armando Herrera | Contreras Construction | Cavitt's Hillcrest Subd, Blk 0 Lt 19 & pt of alley | 2202 Maloney St | Residential | N/A | N/A | 2013-07-26 | 2013-08-06 | 2013-08-13 | N/A | N/A | 2013-08-13 | P&Z 08/15/13
N | R16703 R107080 | SC | CU13-10 | Jesus & Gloria Vega | Luis Pedroza | J M Webb | 3600 Sandy Point Rd | Commercial | N/A | 5.5733 | 2013-12-09 | 2013-12-17 | N/A | N/A | N/A | 2013-12-18 | P&Z 01/16/14
N | R345362 | SC | CU14-03 | Multiple | Bleyl & Assoc | Briar Meadows Creek Ph 3, Lt 1-RB | Nash St | Multi-Family & Commercial | N/A | 9.18 | 2014-02-26 | 2014-03-04 | N/A | N/A | N/A | 2014-03-05 | P&Z 03/20/14
N | R37207 | SC | CU14-04 | William Travis Morace | N/A | Parkwood Estates, Blk 1 Lt 6 | 4041 Charles Ave | Mobile Home | N/A | 1.8 | 2014-03-03 | 2015-01-06 | N/A | N/A | N/A | 2014-04-15 | P&Z 05/01/14
N | R24674 R364290 | SC | CU14-05 | U&C Family Investments | Kerr Surveying | Coulter's Sub of Morille, Lt 6 | 1814 & 1816 Palasota | Residential / Commercial | N/A | 1.918 | 2014-04-22 | 2014-04-29 | 2014-07-01 | N/A | N/A | 2014-07-01 | P&Z 08/21/14
N | N/A | SC | CU14-07 | John Blackmon | N/A | Woodville Acres, Blk 4 Lts 1&2 | 3701 Rabbit Ln | Garage/Shop | N/A | N/A | 2014-05-29 | 2014-06-10 | N/A | N/A | N/A | 2014-06-10 | P&Z 06/19/14
N | R38609 | SC | CU14-10 | Johnny Ramirez Julia | N/A | Ramirez, Blk 1 Lt 1 | 1817 Sandy Point Rd | Home | N/A | 2 | 2014-07-02 | 2014-07-08 | N/A | N/A | N/A | 2014-07-08 | P&Z 08/07/14
N | R362396 | SC | CU14-11 | Mark W Bedgood | N/A | Department of Public Safety Area Office | 1003 N Earl Rudder Frwy | Commercial | N/A | 2 | 2014-07-31 | 2014-08-12 | N/A | N/A | N/A | 2014-08-12 | P&Z 09/18/14
N | R369665 | SC | CU14-13 | Hy-Lay Joint Venture | Gessner Engineering | Highland Hills Ph 2, Blk 1 Lt 1B | Boonville Rd @ Tom Light Dr | Auto Sales | N/A | 3 | 2014-08-27 | 2014-09-02 | 2014-09-23 | 2014-11-25 | #4 12/2 #5 12/9 | 2014-12-09 | P&Z 12/18/14
N | R304457 | SC | CU14-14 | Jen White | N/A | Traditions Ph 15, Blk 1 Lt 10 | 3138 Palmetto Trail | Casita | N/A | 1.1468 | 2014-08-28 | 2014-09-09 | N/A | N/A | N/A | 2014-09-09 | P&Z 10/09/14
N | R6037 | SC | CU14-15 | Trinity Crushed Concrete LLC | Same as Applicant | H Jones, Tract 3 | 4930 Sandy Point Rd | Trinity Crushed Concrete | N/A | 70.77 | 2014-08-27 | 2014-09-09 | 2014-11-18 | N/A | N/A | 2014-11-18 | P&Z 12/04/14
N | R29719 | SC | CU14-16 | JC Wall | Gattis Engineering | Watson Lane Townhome Subd., Blks 1-3 14 Lts | 3500 S College Ave | Townhomes | N/A | 2 | 2014-10-22 | 2014-10-28 | 2014-12-16 | 2014-12-23 | N/A | 2014-12-23 | P&Z 01/15/15
N | R33246 | SC | CU15-01 | Billy F Warren | Doug Krebs | Miltree Place, Lt 4, 7 & pt of 9&10 | 207 Dellwood St | Research facility | N/A | N/A | 2015-01-28 | 2015-02-03 | 2015-02-10 | N/A | N/A | 2015-02-10 | P&Z 02/19/15
N | R29725 | A | CU15-03 | Bona Fide Acquisitions LLC | Schultz Engineering | North Campus Subd., Blk 1 Lt 1-3 | Old College Rd | Detatched Dwelling Units | N/A | 6.39 | 2015-02-24 | 2015-03-03 | Req | Req | Req | Req | Req
N | R22625 | SC | CU15-04 | David Riddle | N/A | Bryan Original Townsite, Blk 138 Lts 6-8 & alley | 202 S Parker Ave | Office | N/A | 0.2204 | 2015-04-20 | 2015-04-28 | N/A | N/A | N/A | 2015-04-28 | P&Z 05/07/15
N | R22347 | A | CU15-05 | Jacqueline Hodge | Same as Applicant | Bryan Original Townsite, Blk 75 Lt 6-10 | 707 E 21st | "Adult Daycare" | N/A | 0.66 | 2015-05-29 | 2015-06-09 | Req | Req | Req | Req | Req
N | N/A | N/A | ER15-?? | Req | Req | Req | Req | Req | Req | Req | Req | Req | Req | Req | Req | Req | Req
N | R306953 | SC | FP11-04 | Bryan Traditions LP | Schultz Engineering | Traditions Ph 19A | Traditions Blvd | Residential | 19 | 6.26 | 2011-05-11 | 2011-05-17 | 2011-05-24 | N/A | N/A | 2011-05-24 | P&Z 06/02/11
N | R77913 | SC | FP13-01 | Carrabba Family Ltd | J4 Engineering | Pecan Ridge Add'n, Blk 1 Lt 1 | 3715 Mohawk Dr | AO | 1 | 4.697 | 2013-02-05 | 2013-02-12 | 2013-02-26 | 2013-03-12 | N/A | 2013-03-12 | P&Z 04/04/13
N | R349377 | SC | FP13-09 | Bryan Traditions LP | Schultz Engineering | Traditions Ph 8A, Blk 1 Lts 17-27 | Persimmon Ridge Ct | Residential | 10 | 5.51 | 2013-07-30 | 2013-08-06 | N/A | N/A | N/A | 2013-08-06 | P&Z 08/15/13
N | R14505 | SC | FP14-01 | GRT Interest | J4 Engineering | Carrabba Ind'l Park Ph 10A | Roughneck Dr | Industrial | 6 | 11.029 | 2014-02-12 | 2014-02-18 | 2014-05-27 | N/A | N/A | 2014-05-27 | P&Z 06/19/14
N | R10020 | SC | FP14-05 | 88 Joint Venture | Hester Engineering | Austin's Estates Ph 5B | Thornberry & Austin's Estates Dr | Residential | 6 | 11.15 | 2014-04-16 | 2014-04-22 | N/A | N/A | N/A | 2014-04-22 | P&Z 05/01/14
N | Req | SC | FP14-09 | WBW Land Investments | Yalgo Engineering | Edgewater Ph 1, Blk 1-11 166 Lts | Chick Lane & Autumn Lake | Residential | 166 | 50.1 | 2014-05-05 | 2014-05-13 | 2014-08-26 | 2014-10-14 | 2014-10-21 | 2014-10-21 | P&Z 11/06/14
N | R29725 | SC | FP14-12 | GH2M Ventures | Gessner Engineering | North Campus Subd., Blk 1 Lt 1-3 | Old College Rd | Residential | 1 | 4.44 | 2014-06-11 | 2014-06-17 | 2014-08-26 | 2014-10-14 | #4 11/4 #5 11/18 | 2014-11-25 | Req
N | R349980 | SC | FP14-15 | Carter Arden Development LP | McClure & Browne | Greenbrier Ph 5, Blk 12-15 30 Lts | Thornberry | Residential | 30 | 9.654 | 2014-07-23 | 2014-07-29 | 2014-12-04 | N/A | N/A | 2014-12-04 | P&Z 12/18/14
N | R40102 | SC | FP14-19 | Hwy 21 Joint Venture | Schultz Engineering | 6 at 21 Crossing Subd., Blk 1 Lt 1-4 | 3410 E SH 21 | Commercial | 4 | 7.219 | 2014-09-17 | 2014-09-23 | 2014-10-14 | N/A | N/A | 2014-10-14 | P&Z 11/06/14
N | R11410 | A | FP14-20 | Mission Companies | Payne Land Surveying LLC | Carrabba Road Subd., Lt 1-4 | 7664 E SH 21 | Commercial | 4 | 9.35 | 2014-10-08 | 2014-10-14 | Req | Req | Req | Req | Req
N | R105315 R306679 | SC | FP14-22 | 1179 Joint Venture | Hester Engineering | Stonebrier Ph 1, Lt 1-19 | Riverstone Dr | Residential | 19 | 5.92 | 2014-10-15 | 2014-10-21 | 2014-12-23 | N/A | N/A | 2014-12-23 | P&Z 01/15/15
N | R30097 | SC | FP15-01 | Brazos Trace LLC | Bleyl & Assoc | Briar Meadows Creek Ph 5, Blk 1-3 60 Lts | Red River Dr | Residential | 63 | 17.32 | 2015-01-07 | 2015-01-13 | 2015-02-03 | 2015-02-10 | 2015-04-07 | 2015-04-10 | P&Z 04/16/15
N | R368105 | SC | FP15-02 | Paul & Merrill Bonarrigo | CEC | Messina Hof Estates (ETJ), Lt 1-24 | Merka Rd | Residential | 24 | 36.5 | 2015-02-05 | 2015-02-17 | 2015-02-24 | N/A | N/A | 2015-02-24 | P&Z 03/05/15
N | R37955 | SC | FP15-03 | SMH Homes LLC | J4 Engineering | Porter's Meadow Ph 1, Blk 1-3 25 Lts | N/A | Residential | 25 | 6.732 | 2015-02-25 | 2015-03-03 | 2015-03-17 | 2015-04-14 | N/A | 2015-04-14 | P&Z 04/16/15
N | R40133 | SC | FP15-05 | Kenneth Crenshaw | Kerr Surveying | Crenshaw Add'n, Lts 1-3 | 2111 Nuches Ln | Industrial/Mixed Use | 3 | 3.308 | 2015-03-18 | 2015-03-24 | N/A | N/A | N/A | 2015-03-24 | P&Z 04/16/15
N | Req | A | FP15-07 | WBW Land Investments | Yalgo Engineering | Edgewater Ph 2 | Chick Ln & Autumn Lake | Residential |  | 65.67 | 2015-04-29 | 2015-05-05 | Req | Req | Req | Req | Req
N | R301609 R347647 | A | FP15-08 | Adam Development Properties LP | McClure & Browne | Miramont Sec 8 | FM158 & FM1179 | Residential | 28 | 9.873 | 2015-05-06 | 2015-05-12 | Req | Req | Req | Req | Req
N | R349980 | A | FP15-10 | Homewood LLC | McClure & Browne | Greenbrier Ph 1, Blk 17 Lts 1-15 & Blk 18 1-12 | Thornberry | Residential | 27 | 7.927 | 2015-05-12 | 2015-05-19 | Req | Req | Req | Req | Req
N | R11953 R11954 R354846 | A | FP15-11 | Parc Traditions LP | Schultz Engineering | Traditions Ph 28, Blk 1 Lt 1 | Club Dr & S Traditions Dr | Residential | 2 | 15.54 | 2015-05-13 | 2015-05-19 | 2015-06-02 | Req | Req | Req | Req
N | R105315 R306679 | A | FP15-12 | 1179 Joint Venture | Hester Engineering | Stonebrier Ph 2 | Riverstone Dr | Residential | 25 | 6.828 | 2015-05-29 | 2015-06-09 | Req | Req | Req | Req | Req
N | N/A | N/A | HLC15-?? | Req | Req | Req | Req | Req | N/A | N/A | Req | N/A | N/A | N/A | N/A | N/A | Req
N | N/A | N/A | LOE15-?? | Req | Req | Req | Req | Req | N/A | Req | Req | Req | N/A | N/A | N/A | Req | N/A
N | R87745 R14136 | SC | MP13-02 | G & C Anderson | Schultz Engineering | Legends Subd., Ph 1-4 | Off W Villa Maria Rd | Commercial / Residential | N/A | 34.11 | 2013-07-24 | 2013-07-30 | 2013-08-06 | N/A | N/A | 2013-08-06 | P&Z 08/28/13
N | R105315 R306679 | SC | MP14-04 | 1179 Joint Venture | Hester Engineering | Stonebrier Ph 1&2 | Stonebrier Dr | Residential | N/A | 14.05 | 2014-10-15 | 2014-10-21 | 2014-11-04 | N/A | N/A | 2014-11-04 | P&Z 11/20/14
N | R37955 | SC | MP14-05 | SMH Homes LLC | J4 Engineering | Porter's Meadow | Montana | Residential | 83 | 19.464 | 2014-11-05 | 2014-11-11 | 2015-02-17 | 2015-02-24 | 2015-03-04 | 2015-03-04 | P&Z 03/05/15
N | R15335 | A | MP15-01 | STTC LLC | J4 Engineering | Green's Crossing | N/A | Residential | 29 | 164.28 | 2015-05-13 | 2015-05-19 | Req | Req | Req | Req | Req
N | R37955 | C | PE15-01 | SMH Homes LLC | J4 Engineering | Porter's Meadow, Lt 4-10 | Montana | Residential | N/A | 19.464 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | P&Z 02/05/15
N | R12759 | SC | PP13-13 | Axis Pipe & Tube | Tetra Surveys | Texas Triangle Park | 1451 Louis E Mikulin Rd | Manufacturing | N/A | 182.731 | 2013-09-26 | 2013-09-07 | 2013-10-08 | N/A | N/A | 2013-10-08 | N/A
N | R349980 | SC | PP14-12 | Carter Arden Development LP | McClure & Browne | Greenbrier Ph 5, Blk 12-15 30 Lts | Thornberry | Residential | 30 | 9.654 | 2014-06-04 | 2014-06-10 | 2014-06-17 | N/A | N/A | 2014-06-17 | N/A
N | Req | SC | PP15-04 | WBW Land Investments | Yalgo Engineering | Edgewater Ph 2 | Chick Lane & Autumn Lake | Residential | 198 | 65.665 | 2015-02-25 | 2015-03-03 | 2015-03-17 | 2015-03-31 | N/A | 2015-03-31 | N/A
N | R11953 R11954 R354846 | SC | PP15-05 | Parc Traditions LP | Schultz Engineering | Traditions Ph 28, Blk 1 Lt 1 | Club Dr & S Traditions Dr | Commercial | 1 | 14.29 | 2015-03-11 | 2015-03-17 | 2015-03-24 | 2015-05-19 | N/A | 2015-05-19 | N/A
N | R30011 | A | PP15-06 | Central Church of Christ | Kerr Surveying | CCOC Add'n | 1600 E 29th St | Commercial | 2 | 5.43 | 2015-03-25 | 2015-03-31 | 2015-05-26 | 2015-06-02 | Req | Req | N/A
N | R397647 R112028 | A | PP15-07 | Adam Development Properties LP | McClure & Browne | Miramont Sec 8 | FM158 & FM1179 | Residential | 28 | 9.873 | 2015-04-01 | 2015-04-07 | Req | Req | Req | Req | N/A
N | R349980 | A | PP15-08 | Homewood LLC | McClure & Browne | Greenbrier Ph 6A & 6B | Thornberry | Residential | 37 | 8.19 | 2015-04-08 | 2015-04-14 | Req | Req | Req | Req | N/A
N | R357399 | A | PP15-11 | Grant Carrabba | Hester Engineering | Austin's Colony Ph 14 & 15 | Thornberry | Residential | 67 | 21.012 | 2015-05-06 | 2015-05-12 | Req | Req | Req | Req | N/A
N | R29732 R29733 | C | PV15-03 | S DHUKA LLC | Parviz Vessali | Mini Plaza, Lt 1 | 3800-3814 S College Ave | Commercial | N/A | N/A | 2015-05-12 | 2015-05-19 | N/A | N/A | N/A | N/A | P&Z 06/04/15
N | N/A | A | RA15-01 | Wayne Carroll Enterprises | Galindo Engineers | Bryan Original Townsite, Blk 38 | Multiple | N/A | N/A | N/A | 2015-04-14 | 2015-04-21 | 2015-05-26 | 2015-06-09 | Req | Req | Req
N | R2249 R307336 R307337 | A | RA15-02 | NN Out Properties LTD | J4 Engineering | Bryan Original Townsite, Blk 114 Lts 1-3 | 204-206 W 31st | Residential | 7 | 0.235 | 2015-05-27 | 2015-06-02 | 2015-06-09 | Req | Req | Req | Req
N | R30131 | SC | RP13-26 | Hy-Lay Joint Venture | Gessner Engineering | Highland Hills Ph 2, Blk 1 Lt 1 | 2502 Boonville Rd | Hotel | 1 | 2.3 | 2013-10-09 | 2013-10-15 | 2013-10-29 | 2013-12-10 | 2013-12-17 | 2013-12-17 | P&Z 12/19/13
N | R31684 | SC | RP14-03 | Pitman Enterprises & SNS Investments | McClure & Browne | Lone Oak Acres, Blk 1 Lt 6R & Blk 2 Lt 1R | 2814 Clarks Ln & 2900 Clarks Ln | Commercial | 2 | 7.653 | 2014-03-12 | 2014-03-18 | 2014-04-29 | N/A | N/A | 2014-04-29 | P&Z 06/05/14
N | R10020 | SC | RP14-10 | Highland Interests | Hester Engineering | Austin's Estates Ph 5A | Austin's Estates & Bravo Ct | Residential | 9 | 19.14 | 2014-05-07 | 2014-05-13 | 2014-05-27 | 2014-08-05 | 2014-08-12 | 2014-08-12 | P&Z 09/04/14
N | R369665 | A | RP14-12 | Hy-Lay Joint Venture | Gessner Engineering | Highland Hills Ph 2, Blk 1 Lt 1B | Boonville Rd @ Tom Light Dr | Commercial | 5 | 16.81 | 2014-05-14 | 2014-05-20 | 2015-01-27 | 2015-02-10 | #4 2/24 #5 3/17 #6 5/19 #7 5/26 | Req | Req
N | R35499 R35500 | SC | RP14-29 | Red Dog Investments | ATM Surveying | Oak Terrace (Bryan), Blk 4 Lt 2&3 | 4336 & 4400 Nagle St | Residential | 3 | 0.4812 | 2014-11-05 | 2014-11-11 | 2014-12-23 | 2015-01-06 | N/A | 2015-01-06 | P&Z 01/15/15
N | R22155 | A | RP15-02 | Wayne Carroll Enterprises | Galindo Engineers | Bryan Original Townsite, Blk 38 Lt 1R | 301 S Texas Ave | Office | 1 | 1.7481 | 2015-04-13 | 2015-04-21 | 2015-05-26 | 2015-06-09 | Req | Req | N/A
N | R28904 | A | RP15-04 | HIFAZA LLC | PACT Design Studio | Highland Park Ph 1, Blk 4 Lt 3 & pts of 2&4 | 4205 College Main | Legacy Townhomes | 2 | 0.2293 | 2015-01-07 | 2015-01-20 | 2015-03-10 | Req | Req | Req | Req
N | R36945 | SC | RP15-06 | Miguel Tavarez Nieto | J4 Engineering | Park Heights, Lt 6A | 2210 W SH 21 | Commercial Tire Center | 1 | 0.52 | 2015-01-28 | 2015-02-03 | 2015-04-07 | N/A | N/A | 2015-04-09 | N/A
N | Req | A | RP15-08 | Sam (Saeed) Mahdavi | Paul Williams Land Surveyor | Holick Ph 1, Blk 1 Lt 7&8 (Pts of) | 3700 Holick Ln | Residential | 2 | 0.327 | 2015-02-02 | 2015-02-10 | Req | Req | Req | Req | Req
N | R356758 R361021 | A | RP15-10 | Veerani Holding LLC & Kajani Sanders Veerani Properties LLC | J4 Engineering | Big Gas Truck Stop, Blk 1 Lt 1 & North Pt Business Park Ph 1, Blk 1 Lt 1 | 2890 N Harvey Mitchell/2815 N Earl Rudder Fwy | Commercial | 2 | 8.371 | 2015-05-27 | 2015-06-02 | Req | Req | Req | Req | Req
N | R2249 R307336 R307337 | A | RP15-11 | NN Out Properties LTD | J4 Engineering | Bryan Original Townsite, Blk 114 Lts 1-3 | 204-206 W 31st | Residential | 7 | 0.235 | 2015-05-27 | 2015-06-02 | 2015-06-09 | Req | Req | Req | Req
N | Req | A | RP15-12 | Bryan Traditions LP | Schultz Engineering | Traditions Ph ??, Blk 1, Lts 1&8, Blk 2 Lts 15-17 | Mahogany Dr | Residential | 30 | 3.3 | 2015-05-27 | 2015-06-02 | 2015-06-09 | Req | Req | Req | Req
N | R96916 | A | RP15-13 | COB-Robert Holmes | Civil Engineering Consultants | American Subd., Blk A 1-RA | Washington St | Cemetery | 1 | 18.145 | 2015-05-27 | 2015-06-02 | Req | Req | Req | Req | Req
N | R32173 R32174 | A | RZ13-12 | Texas LS Investments LLC | Garrett Engineering | Marino Estates Hwy 21E, Blk 1 Lt 8R | 5943 E SH 21 | I to C3 | N/A | 3.98 | 2013-07-18 | N/A | N/A | N/A | N/A | N/A | Req
N | R28907 | A | RZ14-03 | S&I Residential | Gessner Engineering | Highland Park Ph 1, Blk 4 Lt 8 & pts of 7&9 | 4204 Aspen St | PD-5 to PD-H | N/A | 0.25 | 2014-02-05 | 2014-02-11 | 2014-03-04 | 2014-03-25 | Req | Req | Req
N | R28907 | A | RZ14-06 | S&I Residential | Gessner Engineering | Highland Park Ph 1, Blk 6 Lt 5 & Blk 7 Lt 1 | 3907 & 4001 College Main | RD-5 to PD-H | N/A | 0.51 | 2014-02-19 | 2014-02-25 | Req | Req | Req | Req | Req
N | R39004 R107146 R107147 | A | RZ14-18 | Enclave Property Management LLC | Philip Bargas | Shops @ Brazos Valley | N Earl Rudder Fwy | Commercial | N/A | 186.9 | 2014-10-07 | 2014-10-14 | 2014-11-25 | 2014-12-22 | Req | Req | P&Z 11/06/14
N | R304552 | A | RZ14-19 | Teserra Venture LP | Diane Lorden | Ferrara's Add'n, Blk 1 Lt 2A | 2208 Finfeather | PD-M & C2 | N/A | 9.281 | 2014-10-24 | 2014-11-04 | Req | Req | Req | Req | Req
N | R28904 | A | RZ15-01 | HIFAZA LLC | PACT Design Studio | Highland Park Ph 1, Blk 4 Lt 3 & pts of 2&4 | 4205 College Main | Legacy Townhomes | N/A | N/A | 2014-12-31 | 2015-01-06 | 2015-03-10 | 2015-04-28 | Req | Req | Req
N | R13527 | A | RZ15-03 | Adam Development Properties LP | McClure & Browne | Oakmont | 5009 Boonville Rd | PD-M | N/A | N/A | 2015-02-04 | 2015-02-10 | Req | Req | Req | Req | Req
N | R84114 | A | RZ15-06 | Habitat For Humanity | CEC | Zeno Phillips Survey | Imperial Valley Dr | PD to RD-5000 | N/A | N/A | 2015-04-08 | 2015-04-14 | Req | Req | Req | Req | Req
N | R301609 R347647 | A | RZ15-08 | Adam Development Properties LP | McClure & Browne | Miramont Sec 8 | FM158 & FM1179 | PD-M | N/A | N/A | 2015-04-15 | 2015-04-21 | Req | Req | Req | Req | P&Z 06/04/15
N | R301568 | A | RZ15-09 | LEO 60 LP | Chris Peterson | Follett Subd | Leonard Rd | A-O to PD-M | N/A | N/A | 2015-04-29 | 2015-05-05 | 2015-05-19 | Req | Req | Req | Req
N | R375945 | A | RZ15-10 | Atlas Hotel LP | Schultz Engineering | Traditions Ph 27, Blk 1 Lt 1 | 4100 Lake | The Stella Hotel | N/A | N/A | 2015-04-15 | 2015-04-21 | Req | Req | Req | Req | P&Z 05/21/15
N | R15335 | A | RZ15-12 | STTC LLC | J4 Engineering | Green's Crossing (SFA #9) | N/A | A-O to PD-M | N/A | N/A | 2015-05-13 | 2015-05-19 | Req | Req | Req | Req | Req
N | R12160 | A | RZ15-13 | Dennis Thane | Gattis Engineering | Maria Kegan | 10099 SH 30 | A-o to C2 | N/A | N/A | 2015-05-26 | 2015-06-02 | Req | Req | Req | Req | Req
N | R103498 | SC | SP10-02 | John Boegner | Civil Development | Boegner Subd., Lt 3 | 1701 N Earl Rudder Frwy | Mini Warehouse Storage/Office | N/A | 2.16 | 2010-01-06 | 2010-01-12 | 2010-01-26 | 2010-02-09 | N/A | 2010-09-02 | N/A
N | N/A | SC | SP12-38 | RH Harrison Land Venture | Carney Engineers | Highland Hills, Blk A Lt 2R-3 | Off Wildflower Dr | Highland Villas Apts | N/A | 7.98 | 2012-08-08 | 2012-08-14 | 2012-08-28 | 2012-10-16 | #4 10/30 #5 11/6 | 2012-11-14 | N/A
N | N/A | SC | SP12-39 | Crossfulton Investments Ltd | Wal-Mart | Villa Maria Wal-Mart Add'n, Blk A Lt 1 | 643 N Harvey Mitchell Pkwy | Wal-Mart Shopping Center | N/A | 21.616 | 2012-08-08 | 2012-08-14 | 2012-09-25 | 2013-02-26 | 2013-07-23 | 2013-07-23 | N/A
N | R51177 | SC | SP13-05 | Crossfulton Investments Ltd | Dunaway Assoc | Villa Maria Wal-Mart Add'n, Blk B Lt 3 | 631 N Harvey Mitchell Pkwy | 7,700-SF Bldg Pad | N/A | 1.22 | 2013-01-22 | 2013-01-29 | 2013-07-02 | 2013-07-16 | N/A | 2013-07-16 | N/A
N | R51177 | SC | SP13-06 | Crossfulton Investments Ltd | Dunaway Assoc | Villa Maria Wal-Mart Add'n, Blk B Lt 9 | 1612 W Villa Maria Rd | 7,700-SF & 6,720-SF Bldg Pads | N/A | 2.54 | 2013-01-22 | 2013-01-29 | 2013-07-02 | 2013-07-16 | 2013-10-29 | 2013-10-29 | N/A
N | R365385 | SC | SP13-13 | Traditions Destinations LP | Schultz Engineering | Traditions Ph 16, Blk 1 Lt 3B | Off Club Dr | (16) Game-Day Cottages | N/A | 8.55 | 2013-04-03 | 2013-04-09 | 2013-04-16 | 2013-04-30 | N/A | 2013-04-30 | N/A
N | R38997 | SC | SP13-22 | Brady Brittain | McClure & Browne | Select Plaza, Blk 1 Lt 1 | 161 N Earl Rudder Frwy | Real Estate Office | N/A | 10.97 | 2013-05-21 | 2013-05-21 | 2013-12-10 | 2014-02-11 | 2014-03-11 | 2014-03-11 | N/A
N | R29978 | SC | SP13-23 | Congregation Beth Shalom | Gattis Engineering | John Austin Survey, Blk 1 Lts 1-3 | 101 N Coulter Ave | Synagogue | N/A | 1.74 | 2013-05-21 | 2013-05-28 | 2013-06-04 | N/A | N/A | 2013-06-04 | N/A
N | R12759 R79857 R83145 | SC | SP13-27 | Axis Pipe & Tube | H&M Architects & Engineers | Texas Triangle Park "L McLaughlin League" | 1451 Louis E Mikulin Rd | Axis Pipe & Tube Manufacturing Facility | N/A | 182.731 | 2013-06-04 | 2013-06-11 | 2013-09-17 | 2013-10-08 | N/A | 2013-10-08 | N/A
N | R13156 | A | SP13-28 | Ramiro Galindo | Kling Engineering | Regency Gardens Subd., Blk 1 Lt 1 | W Villa Maria Rd | Apartments | N/A | 6.512 | 2013-06-11 | 2013-07-18 | Req | Req | Req | Req | N/A
N | R95147 | SC | SP13-36 | Wellborn SUD | Terry Winn | Jones Road Interconnect Site, Blk 1 Lts 1&2 | 7025 Jones Rd | Water Utility Control Bldg | N/A | 0.5 | 2013-07-26 | 2013-08-06 | 2013-08-20 | N/A | N/A | 2013-08-29 | N/A
N | R97147 | SC | SP13-38 | Marcus Watkins | M L Hammons | Sherwood Ph 1, Blk 1 Lt 1 | 1401 Memorial Dr | Generations Center for Rehab | N/A | 4.3 | 2013-08-02 | 2013-08-13 | 2013-09-10 | N/A | N/A | 2013-09-10 | N/A
N | R32173 R32174 | A | SP13-48 | Texas LS Investments LLC | Garrett Engineering / RME | Marino Estates Hwy 21E, Blk 1 Lt 8R | 5943 E SH 21 | Aggieland Truck Stop | N/A | 3.98 | 2013-10-22 | 2013-10-29 | 2015-01-27 | Req | Req | Req | N/A
N | R33443 | SC | SP13-51 | Matt O'Banion | Fred Burris | Mitchell-Lawrence-Cavitt | 2707 S Texas Ave | Site Imprvmnts | N/A | N/A | 2013-10-31 | N/A | N/A | N/A | N/A | N/A | N/A
N | R28899 R20902 | SC | SP14-02 | John Fu | Constantin Barbu | Highland Park Ph 1, Blk 3 Lt 5R | 4301 College Main | Apartments | N/A | 0.179 | 2014-01-06 | 2014-01-14 | 2014-02-04 | N/A | N/A | 2014-02-04 | N/A
N | R30804 | SC | SP14-07 | Alfredo Sifuentes | Chad Grauke | La Brisa Ph 3, Blk A Lt 17 | 2006 Monito Way | New Fourplex | N/A | 0.2 | 2014-01-21 | 2014-01-28 | 2014-02-18 | 2014-02-25 | N/A | 2014-02-25 | N/A
N | N/A | A | SP14-17 | Mt Nebo Missionary Baptist Church | Patterson Architects | Richard Carter Survey, Blk 1 Lt 15 | 3610 Plainsman Ln | Church | N/A | N/A | 2014-03-26 | 2014-04-01 | 2015-01-20 | Req | Req | Req | N/A
N | R32832 | SC | SP14-18 | Michael Garratt | Gessner Engineering | Memorial Village, Blk 1 Lt 1 | 2611 E 29th St | Commercial | N/A | 0.3341 | 2014-04-02 | 2014-04-08 | 2014-04-15 | N/A | N/A | 2014-04-15 | N/A
N | R22546 | SC | SP14-21 | Servare Cross Country Ventures | Schultz Engineering | Bryan Original Townsite, Blk 121 Lt 9 | 210 W 24th St | Commercial | N/A | 0.132 | 2014-04-30 | 2014-05-06 | 2014-05-20 | N/A | N/A | 2014-05-20 | N/A
N | R98998 | SC | SP14-28 | Saint-Gobain NorPro | McClure & Browne | Brazos County Ind'l Park Ph 3, Blk 3 Lt 1 | 1500 Independence Ave | 5,000-sf Bldg | N/A | 12.96 | 2014-05-14 | 2014-05-20 | 2014-06-03 | 2014-06-03 | N/A | 2014-06-03 | N/A
N | N/A | SC | SP14-30 | Beacon Baptist Church | Gattis Engineering | John Austin Survey, Blk 14 Lt 10 | 2001 Villa Maria Rd | Church | N/A | 2 | 2014-05-22 | 2014-06-03 | 2014-06-24 | N/A | N/A | 2014-06-24 | N/A
N | R106628 | SC | SP14-31 | Brazos Valley Health Realty II | Schultz Engineering | Park Hudson Ph 1, Blk 1 Lt 4 | University & Coppercrest Dr | Orthopedic Medical Center | N/A | 4.76 | 2014-05-27 | 2014-06-03 | 2014-06-17 | 2014-07-01 | N/A | 2014-07-01 | N/A
N | R99075 | SC | SP14-35 | Hyatt Development | CEC | Brazos County Ind'l Park Ph 3, Blk 5 Lt 6-A | 1289 N Harvey Mitchell Pkwy | Scamardo Produce Warehouse/Office | N/A | 6.96 | 2014-06-25 | 2014-07-01 | 2014-07-15 | N/A | N/A | 2014-07-15 | N/A
N | R36925 | SC | SP14-39 | I-40 Group | Clark & Fuller | Asco Subd., Blk 1 Lt 1 | 1875 N Earl Rudder Frwy | Equipment Sales | N/A | 7.81 | 2014-07-02 | 2014-07-08 | 2014-07-22 | N/A | N/A | 2014-07-22 | N/A
N | N/A | SC | SP14-41 | Norman & Linda Holubec | Watson Law Firm | Isaac L Jacques (ICL) | SH 47 | COO - ROW Improvements | N/A | N/A | 2014-06-25 | N/A | N/A | N/A | N/A | N/A | N/A
N | R38122 R38123 | SC | SP14-42 | St Joseph Health Center | Mitchell & Morgan | St Joseph Regional Health Center, Blk E Lt 2 (pt of) | 1326 & 1328 Memorial Dr | ED & Trauma Center | N/A | 0.8181 | 2014-07-16 | 2014-07-22 | 2014-09-09 | 2014-10-21 | N/A | 2014-10-21 | N/A
N | R346114 R346115 | SC | SP14-44 | 21 Wings Inc | Mitchell & Morgan | 21 Wings, Lt 1&2 | 2612 E SH 21 | Wings & More Driveway Expsn | N/A | 2.62 | 2014-08-06 | 2014-08-12 | 2014-08-25 | N/A | N/A | 2014-08-26 | N/A
N | R33323 | SC | SP14-47 | Aria Hospitality | J4 Engineering | Aria Estate, Blk 1 Lt 1 | 1506 Nuches Ln | Bryan Inn & Suites | N/A | 2.815 | 2014-08-27 | 2014-09-02 | 2014-09-09 | N/A | N/A | 2014-09-09 | N/A
N | Multiple | A | SP14-48 | Burton Creek Development Ltd | Bleyl & Assoc | Briar Meadows Creek Ph 3, Blk 17 Lt 8-10, 12&13 | 2762 Nash St | Nash St Apartments | N/A | N/A | 2014-09-03 | 2014-09-09 | 2014-09-16 | 2014-10-14 | 2014-10-21 | Req | N/A
N | R47133 | A | SP14-50 | Bryan Highway 21 Property LLC | N/A | Get-N-Go, Blk 1 Lt 2R | 2909 W SH 21 | Convenience Store/Gas Station | N/A | 0.805 | 2014-09-02 | 2014-09-09 | Req | Req | Req | Req | N/A
N | R29124 | A | SP14-52 | Big Moose LTD | Earl Havel | Cavitt's Hillcrest Subd, Blk 5 Lt 1-5 | 1800 S Texas Ave | Eastep Auto Sales | N/A | 0.653 | 2014-09-10 | 2014-09-16 | 2014-12-09 | Req | Req | Req | N/A
N | R41553 | SC | SP14-53 | Linda S Warren | Schultz Engineering | Siegert #2 Subd., Blk 1 Lt 1 | 1960 N Earl Rudder Frwy | WC Tractor Office Bldg | N/A | 5.34 | 2014-09-10 | 2014-09-16 | 2014-10-28 | 2014-11-18 | 2014-12-09 | 2014-12-09 | N/A
N | R345362 | SC | SP14-55 | Burton Creek Development Ltd | Bleyl & Assoc | Briar Meadows Creek Ph 3, Lt 1-RB | 2103 E WJB Pkwy | Ducky's Car Wash | N/A | 1.99 | 2014-09-17 | 2014-09-23 | 2014-09-30 | 2014-10-07 | N/A | 2014-10-07 | N/A
N | N/A | SC | SP14-56 | Midway Express Car Wash LP | Goodwin-Lasiter Inc | Penner Place, Blk 1 Lt 2 | 2112 W Briargate Dr | Copper Top Car Wash | N/A | 1.61 | 2014-09-17 | 2014-09-23 | 2014-10-07 | N/A | N/A | 2014-10-09 | N/A
N | R40102 | SC | SP14-58 | Hwy 21 Joint Venture | Schultz Engineering | 6 at 21 Crossing Subd., Blk 1 Lt 1-4 | 3410 E SH 21 | Driveways | N/A | 8.446 | 2014-10-21 | 2014-10-28 | 2014-11-18 | 2015-03-03 | N/A | 2014-11-18 | N/A
N | R304853 R304854 | SC | SP14-59 | Blinn College | Bleyl & Assoc | Blinn College, Blk 1 Lt 1 | 2423 Blinn Blvd & 2530 E Villa Maria | Parking Lot | N/A | 79.337 | 2014-10-22 | 2014-10-28 | 2014-11-04 | N/A | N/A | 2014-11-04 | N/A
N | R35156 | SC | SP14-61 | Roy Rodriguez | J4 Engineering | Oak Grove Park Ph 2, Lt 18R | 1601 Sims Ave | Tire Shop | N/A | 0.74 | 2014-11-19 | 2014-11-25 | 2014-12-09 | N/A | N/A | 2014-12-09 | N/A
N | R14577 R14578 | A | SP14-62 | Hidden Creek RV Resort LLC | J4 Engineering | Stephen F Austin #10, Blk 18 Lt 78 | SH 21 | RV Park | N/A | 25.16 | 2014-11-19 | 2014-11-25 | 2015-01-20 | 2015-02-03 | Req | Req | N/A
N | R40242 | SC | SP14-63 | Ministerio de R.E. Church | Mitchell & Morgan | Salidiner Ph 1, Lt 9 | 5301 N Texas Ave | Ministerio de R.E. Church | N/A | 10.6 | 2014-11-19 | 2014-12-09 | 2015-01-13 | 2015-02-03 | 2015-02-27 | 2015-02-20 | N/A
N | R17752 R17753 | SC | SP15-01 | Stripes LLC | HFA | Beason Add'n, Blk 2 Lt 1R & 2R | 2000 S College Ave | Stripes C-Store/Gas Station | N/A | N/A | 2014-12-23 | 2015-01-06 | 2015-02-17 | 2015-03-03 | 2015-04-01 | 2015-04-01 | N/A
N | R107127 | A | SP15-02 | Stripes LLC | HFA | Tiffany Park Business Center | 4300 Boonville Rd | Stripes C-Store/Gas Station | N/A | N/A | 2014-12-18 | 2015-01-06 | 2015-03-03 | 2015-03-24 | Req | Req | N/A
N | N/A | A | SP15-03 | Trey Moore | Dyer Engineering | Windham Subd., Blk 1 Lt 3 | 2760 Osborn Ln | Commercial | N/A | N/A | 2014-12-31 | 2015-01-06 | 2015-01-20 | Req | Req | Req | N/A
N | R98979 | A | SP15-05 | Lubrizol | RME Engineers | Brazos County Ind'l Park, Blk 1 Lt 9 | 1331 Independence Ave | Industrial | N/A | N/A | 2015-01-14 | 2015-01-20 | Req | Req | Req | Req | N/A
N | R96926 | SC | SP15-06 | Brazos County | Mitchell & Morgan | Brazos County Public Works Ctr, Blk 1 Lt 1 | 2617 W SH 21 | Commercial | N/A | N/A | 2015-01-08 | 2015-01-20 | 2015-02-24 | 2015-03-24 | N/A | 2015-03-24 | N/A
N | N/A | A | SP15-07 | Jay W Lightfoot | N/A | Moses Baine Survey | 4411 N Texas Ave | Residential | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N | R369890 | A | SP15-08 | Atul & Rita Ratanji | Mitchell & Morgan | Highland Hills Ph 2, Blk 1 Lt 1A | 2891 Highpoint Dr | Super 8 Hotel | N/A | N/A | 2015-02-03 | 2015-02-10 | Req | Req | Req | Req | N/A
N | R36945 | SC | SP15-09 | Miguel Tavarez Nieto | J4 Engineering | Park Heights, Lt 6A | 2110 W SH 21 | Miguel's Tire Shop | N/A | N/A | 2015-01-30 | 2015-02-10 | 2015-04-07 | N/A | N/A | 2015-04-09 | N/A
N | R40016 | A | SP15-10 | Producers Coop Association | McClure & Browne | Producers Coop Assoc., Blk 1 Lt 2 | 1800 N Texas Ave | Feed Storage Facility | N/A | N/A | 2015-03-04 | 2015-03-10 | 2015-03-31 | 2015-04-21 | Req | Req | N/A
N | R11953 R11954 R354846 | A | SP15-11 | Parc Traditions LP | Schultz Engineering | Traditions Ph 28, Blk 1 Lt 1 | Club Dr & S Traditions Dr | Assisted Living Facility | N/A | N/A | 2015-03-04 | 2015-03-10 | 2015-03-24 | 2015-06-02 | Req | Req | N/A
N | R22215 | A | SP15-12 | Lessie Alva | Jason Shryock | Bryan Original Townsite, Blk 52 Lt 1-2 pt of 3) | 500 E WJB Pkwy | Art Gallery | N/A | N/A | 2015-03-11 | 2015-03-17 | Req | Req | Req | Req | N/A
N | R346077 | SC | SP15-13 | Toyo Ink | N/A | Bryan Ind'l Park Ph 3, Blk 1 Lt 1 | 2400 N Harvey Mitchell Pkwy | Toyo Ink | N/A | N/A | 2015-03-17 | 2015-03-24 | 2015-04-07 | 2015-04-10 | N/A | 2015-04-10 | N/A
N | R22450 | A | SP15-14 | Harriet Development | Chris Lawrence | Bryan Original Townsite, Blk 142 pts of Lts 3-8 | 304 N Parker | Townhomes | N/A | N/A | 2015-03-23 | 2015-03-31 | 2015-04-07 | Req | Req | Req | N/A
N | R29719 | SC | SP15-15 | JC Wall | Gattis Engineering | Watson Lane Townhome Subd., Blk 3 Lt 1 | 3500 S College Ave | Condos | N/A | N/A | 2015-03-30 | 2015-04-07 | 2015-04-28 | 2015-05-12 | N/A | 2015-05-12 | N/A
N | R20994 | SC | SP15-16 | Highland Interests | J4 Engineering | Carrabba Ind'l Park Ph 5, Blk 6 Lt 2 | 1723 Gooseneck Dr | Warehouse/Office | N/A | N/A | 2015-04-01 | 2015-04-07 | 2015-04-14 | N/A | N/A | 2015-04-14 | N/A
N | R40109 | SC | SP15-17 | Goosneck Trailer Manufacturing Co | J4 Engineering | Stephen F Austin #10, Blk 18 Lt 13 | 4400 E SH 21 | Manufacturing | N/A | N/A | 2015-04-01 | 2015-04-07 | 2015-04-14 | N/A | N/A | 2015-04-14 | N/A
N | R262404 | A | SP15-18 | Darling International Inc | Jones & Carter | Bryan Ind'l Park Ph 4, Blk 1 Lt 1 | 601 Liberty Dr | Bakery Feeds | N/A | N/A | 2015-04-08 | 2015-04-14 | 2015-05-26 | Req | Req | Req | N/A
N | R350205 | SC | SP15-19 | James Ford LLC | Bleyl & Assoc | Park Hudson Ph 7, Blk 1 Lt 4 | Coppercrest Dr | Specialties Photography | N/A | N/A | 2015-04-07 | 2015-04-14 | 2015-04-28 | 2015-05-12 | N/A | 2015-05-12 | N/A
N | R375945 | A | SP15-20 | Atlas Hotel LP | Schultz Engineering | Traditions Ph 27, Blk 1 Lt 1 | 4100 Lake | The Stella Hotel | N/A | N/A | 2015-04-15 | 2015-04-21 | 2015-05-12 | 2015-05-26 | 2015-06-02 | Req | N/A
N | R31684 | A | SP15-21 | Pitman Enterprises LLC | McClure & Browne | Lone Oak Acres, Blk 2 Lt 1R | 2814 Clarks Ln | Industrial | N/A | N/A | 2015-04-15 | 2015-04-21 | 2015-05-12 | Req | Req | Req | N/A
N | R97303 | A | SP15-22 | Quality Park Development | Garrett Engineering | Three D Subd., Blk 1 Lt 1 | 1800 Quality Park Cir | Bryan Hose & Gasket | N/A | N/A | 2015-04-15 | 2015-04-21 | 2015-05-19 | Req | Req | Req | N/A
N | R44994 | A | SP15-23 | Jose C Diaz | Garrett Engineering | Thomas Heights Add'n, Blk 1 Lt 2R | 1800 Groesbeck St | Diaz Office Complex | N/A | N/A | 2015-04-17 | 2015-04-28 | Req | Req | Req | Req | N/A
N | N/A | A | SP15-24 | James H Wood | Same as Applicant | Windham Subd., Blk 1 Lt 4 | 2770 Osborn Ln | Napa Auto Parts | N/A | N/A | 2015-04-29 | 2015-05-05 | 2015-05-19 | Req | Req | Req | N/A
N | N/A | SC | SP15-25 | Bryan ISD | N/A | BISD Subd (James Earl Rudder HS) | 3251 Austin's Colony Pkwy | Rudder HS Portable Bldgs | N/A | N/A | 2015-05-06 | 2015-05-12 | N/A | N/A | N/A | 2015-05-12 | N/A
N | R29726 | A | SP15-26 | Big Moose LTD | Bleyl & Assoc | Timberlake MH Park (J E Scott League) | 102 Lakeside Dr | Parking Lot | N/A | N/A | 2015-05-11 | 2015-05-19 | Req | Req | Req | Req | N/A
N | R49865 | A | SP15-27 | Chris Osgood | Galindo Engineers | Woodland Heights #2, pt of Blk 1 | 410 Bethel Ln | Brazos School for Inquiry Portable Bldgs | N/A | N/A | 2015-05-13 | 2015-05-19 | 2015-06-09 | Req | Req | Req | N/A
N | R33246 R33249 | A | SP15-28 | Tee Drive Investments LLC | RME Engineers | Miltree Place, Lt 4, 7 & pt of 9&10 | 207 Dellwood St | Shear Form | N/A | N/A | 2015-05-20 | 2015-05-26 | Req | Req | Req | Req | N/A
N | R364501 | A | SP15-29 | Joseph-Robert Holdings LLC | J4 Engineering | Canyon Creek Entertainment, Blk 1 Lt 2 | 1135 N Earl Rudder Fwy | Office building | N/A | N/A | 2015-05-27 | 2015-06-02 | 2015-06-09 | Req | Req | Req | N/A
N | R364121 | A | SP15-30 | Kristen Distributing Co | Gessner Engineering | Gunler Add'n, Blk 1 Lt 1 | 8301 N SH 6 | Industrial | N/A | N/A | 2015-06-03 | 2015-06-09 | Req | Req | Req | Req | N/A
N | N/A | SC | SQ15-01 | First Baptist Church of Bryan | Kling Engineering | Richard Carter Survey, Blk 2 Lt 37.6 | 3205 Cambridge Dr | Clearing & Grubbing | N/A | 5.33 | 2015-02-20 | N/A | N/A | N/A | N/A | N/A | N/A
N | N/A | SC | SQ15-02 | Darling International Inc | Jones & Carter | Bryan Ind'l Park Ph 4, Blk 1 Lt 1 | 601 Liberty Dr | Bakery Feeds | N/A | 9.028 | 2015-02-25 | N/A | N/A | N/A | N/A | N/A | N/A
N | R345362 | A | SQ15-04 | Burton Creek Development Ltd | Brazos Trace LLC | Briar Meadows Creek Ph 3, Lt 1-RB & 3 | Nash & Villa Maria | Apartments | N/A | 13.344 | 2015-03-19 | N/A | N/A | N/A | N/A | N/A | N/A
N | N/A | A | SU14-01 | Servare Cross Country Ventures | N/A | Bryan Original Townsite, Blk 121 Lt 9 | 210 W 24th St | Sign | N/A | N/A | 2014-10-27 | 2014-11-04 | N/A | N/A | N/A | Pending | N/A
N | N/A | N/A | SU15-?? | Req | Req | Req | Req | Req | N/A | N/A | Req | Req | Req | Req | Req | Req | N/A

## Engineer's Estimates (hidden)
SUBDIVISION EVALUATION
DATE ACCEPTED | SUBDIVISION | Residential # Lots | WATERLINE (Domestic) | SANITARY SEWER | STREETS | SIDEWALKS | DRAINAGE & STORM SEWER | TOTAL
2008-11-14 | 21 Wings: Wings N More | N/A | 25360 | 0 | 0 | 0 | 0 | 25360
| Ashford Place | N/A | 27628 | 21420 | 23735.52 | 6690 | 0 | 79473.52
| Austin's Colony, Phase 7B&C | 17 | 20324 | 24400 | 65935 | 0 | 0 | 110659
2009-02-20 | Austin's Colony, Phase 11A&C | 85 | 230276.67 | 230049.6 | 661574 | 120132.09 | 292697.24 | 1534729.6
| Austin's Colony Church: Faith United Church of Christ | N/A | 16070 | 0 | 0 | 1300 | 0 | 17370
| Austin's Estates, Phase 2 | 20 | 53100 | 0 | 143172.5 | 0 | 0 | #N/A
| Austin's Estates, Phase 3A | 20 | 0 | 118698.6 | 217280.75 | 0 | 0 | #N/A
| Auto Zone Sims: FMC Dialysis Center | N/A | 10650 | 2400 | 0 | 11470 | 0 | #N/A
| Autumn Lake, Phase 2B & 3 | 54 | 103748 | 105290 | 364887.5 | 28415.25 | 83681.25 | 686022
| Bice Addition | N/A | 0 | 0 | 0 | 0 | 0 | #N/A
2008-10-06 | Boonville Town Center | N/A | 152288.5 | 173072.9 | 464997.5 | 0 | 154134.5 | #N/A
| Boonville Town Center: Best Western Hotel | N/A | 66377 | 17659 | 0 | 0 | 0 | #N/A
| Boonville Town Center: IHOP Restaurant | N/A | 10075 | 12500 | 0 | 0 | 27011 | #N/A
| Brazos County Complex Ph 1: BC Detention Facility | N/A | 88202 | 0 | 0 | 0 | 0 | #N/A
2008-10-24 | Brazos Cnty Expo Center Ph 1: TAMU Equestrian Cntr | N/A | 15770 | 0 | 0 | 0 | 0 | #N/A
| Brazos Valley Welding | N/A | 13581 | 0 | 0 | 0 | 0 | #N/A
| Briar Meadows Creek Phase 1 | 18 | 45690 | 48748 | 75168 | 31324 | 37125 | #N/A
| Briarcrest Wal-Mart/ Recycling | N/A | 0 | 0 | 0 | 0 | 0 | #N/A
| Bryan Business Park-Koch | N/A | 99035 | 91307 | 0 | 0 | 0 | #N/A
2008-11-19 | Bryan Ind'l Park Ph 3: Toyo Ink Manufacturing | N/A | 0 | 0 | 0 | 0 | 0 | 0
2009-02-18 | Bryan Medical Building | N/A | 9474 | 13585 | 0 | 12047 | 0 | #N/A
2009-04-06 | Bryan Original Townsite: Burger King | N/A | 0 | 0 | 0 | 16320 | 0 | #N/A
| Bryan Original Townsite: Cotton Warehouse | N/A | 0 | 0 | 0 | 4537.5 | 0 | #N/A
| Bryan Original Townsite: St Andrews Episcopal Church | N/A | 0 | 0 | 0 | 4100 | 0 | #N/A
2009-02-18 | Bryan Original Townsite: St Joseph Elementary School | N/A | 23523 | 0 | 0 | 9210 | 0 | #N/A
| Bryan Original Townsite: 24th & Sims |  | 0 | 5699 | 0 | 174 | 0 | #N/A
| Bryan Original Townsite: 909 W WJB, Restaurant/Retail | 1 | 0 | 0 | 0 | 4888 | 0 | #N/A
| Bryan Original Townsite: Carter's Restaurant (Fannie's) | N/A | 0 | 0 | 0 | 5384 | 0 | #N/A
| Bryan Townhouses | N/A | 0 | 0 | 0 | 0 | 0 | 0
| Cavitt's Southmore Add'n | 2 | 0 | 0 | 0 | 4520 | 0 | 4520
| C-Hall Commercial: Brazos Moving & Storage | N/A | 0 | 0 | 0 | 0 | 0 | 0
| Colony Park Shopping Center: Chase Bank | N/A | 0 | 0 | 0 | 0 | 0 | 0
2008-11-14 | Cottage Grove: Phase 2B | 42 | 85164 | 56013 | 166489 | 29821 | 103014 | #N/A
| Eastside Re-Survey Addition | 3 | 0 | 0 | 0 | 3124 | 0 | #N/A
| Fox Meadows Subdivision | 24 | 31511 | 37618 | 67830.4 | 6934.5 | 31685 | #N/A
| Hollow Hill Center | N/A | 0 | 0 | 0 | 0 | 0 | #N/A
| High Country, Phase 3 | 55 | 27635 | 0 | 85498.5 | 0 | 0 | #N/A
| Hudson @ University | N/A | 25960 | 189020 | 0 | 0 | 149170 | #N/A
| Ice House: Mac Resource | N/A | 0 | 0 | 0 | 5088.75 | 0 | 5088.75
| Jerusalem Baptist Church | N/A | 0 | 0 | 0 | 0 | 0 | #N/A
| Margaret Wallace Subdivision, Block 20 Lot 7 | 1 | 0 | 0 | 0 | 1377.5 | 0 | 1377.5
| Mitchell-Lawrence-Cavitt: Horton Building | N/A | 0 | 0 | 0 | 2110 | 0 | #N/A
2009-02-20 | Park Hudson, Ph 8: Artisan Apts | N/A | 127014 | 0 | 0 | 0 | 0 | 127014
| Penner Place: Office Park | N/A | 13450 | 0 | 0 | 0 | 0 | 13450
| Porterfield-Watson: RV Park | N/A | 0 | 0 | 0 | 0 | 0 | #N/A
| Redden Thomas Subdivision: Kermit Street | 4 | 14610 | 0 | 0 | 0 | 0 | #N/A
| Richard Carter Survey: Tasco Auto Color | N/A | 0 | 0 | 0 | 450 | 0 | #N/A
| Sherwood Health Care | N/A | 0 | 0 | 37756 | 0 | 15310 | #N/A
2009-04-08 | Sierra Ridge Estates | 52 | 81518 | 107491 |  | 0 |  | #N/A
2008-10-28 | Silver Oaks Subd: Allen Academy | N/A | 0 | 0 | 0 | 0 | 0 | 0
| Symphony Park: America's Best Value Inn | N/A | 9291 | 0 | 0 | 6135 | 0 | 15426
| Thomas Subd: Law Office | N/A | 0 | 0 | 0 | 0 | 0 | #N/A
| Three R Subdivision | N/A | 0 | 9634 | 0 | 14016 | 0 | #N/A
| Tiffany Park Subdivision | N/A | 0 | 0 | 0 | 0 | 183961 | #N/A
| Utility Fleet Sales, Phase 2 | N/A | 23395 | 0 | 145936.25 | 0 | 0 | #N/A
| Utility Fleet Sales: FedEx Ground Distribution Center | N/A | 40638.4 | 0 | 0 | 0 | 0 | #N/A
| Villa Maria Plaza: Sulmar Center Additions | N/A | 0 | 0 | 0 | 1120 | 0 | #N/A
2009-01-28 | Villa Maria West: Fire Station #5 | N/A | 0 | 0 | 0 | 0 | 0 | 0
| Wilson Heights: Jimmy D Ford Bldg | N/A | 3220 | 0 | 0 | 6026 | 0 | #N/A
| Windover East, Ph 3: Westminster Presbyterian Church | N/A | 29253.4 | 0 | 0 | 0 | 0 | #N/A
| Winter's Estates | 8 | 0 | 0 | 0 | 2905 | 0 | #N/A
| Winter's Estates: First Christian Church | 0 | 0 | 0 | 0 | 2460.75 | 0 | #N/A
| Woodlawn Addition: Palasota Center | N/A | 0 | 0 | 0 | 3204 | 0 | #N/A
| Zeno Phillips League: First Presbyterian Church | N/A | 5850 | 0 | 0 | 0 | 0 | #N/A
GRAND TOTALS: |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A